## Data Migration
HAJT Data Migration | July 21 2018
Wednesday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 0 | 0 | 0 | 0
Functional Specification | 0 | 0 | Sr.Developer | 1 | 96 | 12 | 12 | 18.8125 | 19
Project Management | 15.05 | 1.8813 | Jr Developer | 0.5 | 96 | 14 | 7
Graphic Design | 0 | 0 | PM | 1 | 23.05 | 2.8813 | 2.8813
Working Prototype | 0 | 0 | QA | 2 | 17.05 | 2.1313 | 4.2625
Development |  |  | Total |  | 232.1 |  | 26.1438 | 209.15
Create Schedule | 8 | 1
Batch Conversion of Zip file | 8 | 1 | Total Delivery days | 16.1313
Data migrate one file | 8 | 1 | Total Man day Effort | 26.1438 | 19.6078
Data migrate 4 files @ 3 hrs each | 12 | 1.5
Data migrate remaining 55 files @ 1.5 hours each | 82.5 | 10.3125 | NOTE: Team will need a few days to get familiar with the technology before the project starts.
Backup files | 8 | 1 | Please provision this before you commit a start date to the client | [6 empty] | 82.5
Web interface for logs | 8 | 1
Manual correction & migration | 8 | 1
Error Logging | 8 | 1
Testing | 30.1 | 3.7625
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 211.65 | 26.4563
Assumptions
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions