## Data Migration
HAJT Data Migration | July 21 2018
Wednesday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 0 | 0 | 0 | 0
Functional Specification | 0 | 0 | Sr.Developer | 1 | 96 | 12 | 12 | 0 | 19
Project Management | 0 | 0 | Jr Developer | 0.5 | 96 | 14 | 7
Graphic Design | 0 | 0 | PM | 1 | 8 | 1 | 1
Working Prototype | 0 | 0 | QA | 2 | 2 | 0.25 | 0.5
Development |  |  | Total |  | 202 |  | 20.5 | 164
Create Schedule |  | 0
Batch Conversion of Zip file |  | 0 | Total Delivery days | 14.25
Data migrate one file |  | 0 | Total Man day Effort | 20.5 | 15.375
Data migrate 4 files @ 3 hrs each |  | 0
Data migrate remaining 55 files @ 1.5 hours each |  | 0 | NOTE: Team will need a few days to get familiar with the technology before the project starts.
Backup files |  | 0 | Please provision this before you commit a start date to the client | [6 empty] | 82.5
Web interface for logs |  | 0
Manual correction & migration |  | 0
Error Logging |  | 0
Testing | 0 | 0
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 16 | 2
Assumptions
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions