## Hajt Mobile App
| HAJT Mobile App | 2017-02-08
Wednesday
Sl. No. | Module | Hours | Days
| Initiation |  |  |  |  | No | Man hours | Man Days |  |  | Compensating for Landscape and portrait | Comments
1 | Requirements gathering and documentation (SRS) | 16 | 2 |  | Designer | 1 | 48 | 6 |  |  | 7.5 | x25%
2 | Functional Specification | 8 | 1 |  | API Developer | 1 | 0 | 0 | 43.375 | 43.375 | 0
3 | Project Management | 34.7 | 4.3375 |  | Web Developer | 1 | 122 | 15.25 |  |  | 19 | 1.50XDesign
4 | UI/UX Design (Android &IOS) | 48 | 6 |  | IOS Developer | 1 | 114 | 14.25 |  |  | 25.625 | 1.75XDesign
| Development |  | 0 |  | Android Developer | 1 | 111 | 13.875 |  |  | 26.3438 | 1.75XDesign
6 | API Development | 0 | 0 |  | PM | 1 | 34.7 | 4.3375 |  |  | 4.3375
7 | Android Development | 54 | 6.75 |  | BA | 1 | 24 | 3 |  |  | 3
| Android Design | 57 | 7.125 | 12.4688 | QA | 1 | 112.1 | 14.0125 |  |  | 17.5156 | x25%
8 | IOS Development | 62 | 7.75 |  | Total |  |  | 70.725
| IOS Design | 52 | 6.5 | 11.375 | Total Delivery days | 24.9208 |  |  |  |  | Total Delivery days | 38.9635
| Web Development | 102 | 12.75 |  | Total Effort | 70.725 |  |  |  |  | Total Effort | 103.3219
| Web Design | 20 | 2.5 | 3.75
56 | Testing & Deployment |  | 0
57 | Testing | 104.1 | 13.0125
58 | UAT | 8 | 1
| Deployment | 4 | 0.5
| Total Effort | 569.8 | 71.225
1 | Assumptions | 71.225 |  | By Product | Effort In days
2 | Client shalll buy the themes,skins or templates needed for customizing the look and feel |  |  | Web Interface
3 | Client shall provide logos, images & branding guidelines |  |  | Android App
4 | Client shall provide the text and assosiated images for languages other than English |  |  | IOS App
5 | Subscription to weather apps
6 | Cannot modify design elements once the app is deployed
7 | Static pages (privacy, About) and News updates can be updated via CMS
8 | This estimate is only for a portrait orientation on mobile phones (Not Tabs)
Payment gateway details will be shared by the client
Supporting OS: Android SDK V 19 (KitKat) and above
Does not support offline access or operations

## Detailed Req
Project name:Ajman Port
# | Page | Design,Coding and testing (In Hours) | [7 empty] | Comments
|  | Design | Web | Web Api | Android |  | iOS |  | Testing
[5 empty] | Design | Coding | Design | Coding
1 | Splash Screen |  |  |  | 0 | 0 | 0 | 0 |  | Without animation
2 | Dashboard | 4 | 8 | 0 | 8 | 4 | 6 | 4
3 | Basic setup |  | 4 | 0 |  | 8 |  | 8
4 | Language selection |  | 4 | 0 | 2 | 8 | 2 | 8
5 | Search | 4 | 8 | 0 | 4 | 4 | 4 | 4
6 | Container tracking facilities | 4 | 4 | 0 | 8 | 4 | 6 | 4
7 | Submit gate pass request |  | 0 | 0 | 6 | 4 | 6 | 4
8 | Submit berthing request |  | 0 | 0 | 6 | 4 | 6 | 4
9 | Payment getway integration |  | 0 |  |  | 0 |  | 0
10 | Show latest news, Announcement, etc. | 4 | 2 | 0 | 3 | 3 | 6 | 5
11 | Submit user(s) enquiry and feedback. |  | 4 | 0 | 4 | 3 | 4 | 5
12 | Provide a video on how to use the mobile application. |  | 0 | 0 | 0 | 0 | 0 | 0
13 | Should provide FAQ’s section |  | 8 | 0 | 6 | 4 | 4 | 4
14 | Should provide User’s Terms section |  |  |  | 6 | 2 | 4 | 4
15 | Should be easily refreshed to for latest updates/ information etc | 2 | 2 | 0 | 2 | 4 | 2 | 6 |  | Pull to refresh
16 | should provide function to activate or de-activate notification feature for vessel, container tracking, declaration status etc. through SMS or email | 2 | 6 | 0 | 2 | 2 | 2 | 2
17 | Should provide feature to rate the application. | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Should provide feature to share the application. |  |  |  | 0 | 0 | 0 | 0
19 | Application should provide latest weather report/details for at least 1 week. |  |  | 0 | 0 | 0 | 0 | 0
20 | Should provide Audit control for analysis.* | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Application elements should be modified easily |  | 6 | 0
22 | should be integrated with Content Management system for Publish/unpublished, edit, update, delete the data |  | 6 | 0
Screen orentiation and screens
23 | SMS, Email Gateway, OTP
| Testing |  | 40
Assumption
Subscription to weather apps
Cannot modify design elements once the app is deployed
Static pages (privacy, About) and News updates can be updated via CMS
This estimate is only for a portrait orientation on mobile phones (Not Tabs)
| Payment gateway details will be shared by the client |  |  | Web | API | Android | IOS
| Supporting OS: Android SDK V 19 (KitKat) and above |  | Total Hours | 122 | 0 | 111 | 114
| Does not support offline access or operations |  | Total Days | 15.25 | 0 | 13.875 | 14.25
|  |  | Delivery Timeline | 29.5

## Resource Loading
Resource Distribution in days (Quoted)
| Month1 | Month2 | Month3/2 | Total
UI/UX designer | 6 | 1 | 0.5 | 7.5 | Designer |  |  | 1 | 7.5
API Developer | 5 | 7 | 5.25 | 17.25 | API Developer |  |  | 1 | 17.25
Web Developer | 6 | 10 | 20 | 36 | Web Developer |  |  | 1 | 36
IOS Dev | 10 | 20 | 22 | 52 | IOS Developer |  |  | 1 | 52.4375
Android Dev | 10 | 20 | 20 | 50 | Android Developer |  |  | 1 | 50.4375
BA | 3 |  | 0 | 3 | PM |  |  | 1 | 10.8
QA | 5 | 10 | 27 | 42 | BA |  |  | 1 | 3
Proj Man | 5 | 3.4 | 3 | 11.4 | QA |  |  | 3 | 41.75
|  |  |  | 219.15 |  |  | Total |  | 219.175
Resource Distribution in days (Actual) | [5 empty] | Month1 |  |  |  | Month 2 |  |  |  | Month 3
| Month1 | Month2 | Month3/2 |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12
UI/UX designer | 12 | 2 | 2 | 16 | Activity (Days) | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60
API Developer | 5 | 6 | 5.5 | 16.5 | Project Initiation
Web Developer | 10 | 15 | 10 | 35 | Contract Sign off | [12 empty] | On going | bar: Month1 WK 1 5
IOS Dev | 10 | 20 | 20 | 50 | Project Contacts | bar: Month1 WK 1 5
Android Dev | 10 | 20 | 20 | 50 | Project Repository | bar: Month1 WK 1 5
BA | 6 | 5 | 5 | 16 | Project Planning | Month1 WK 2 10: 12 days
QA | 12 | 15 | 20 | 47 | Updated Schedule | bar: Month1 WK 2 10 to Month1 WK 4 20
Proj Man | 6 | 6 | 6 | 18 | Open Project | Month1 WK 1 5: - - Recurring - -
|  |  |  | 248.5 | Test Plan | bar: Month1 WK 2 10 to Month1 WK 4 20
[5 empty] | Req. Man | Month1 WK 1 5: 3-12 days
Req. Elicitation | bar: Month1 WK 2 10
SRS | bar: Month1 WK 3 15 to Month1 WK 4 20
Test Case Planning | bar: Month1 WK 3 15 to Month1 WK 4 20
RTS | bar: Month1 WK 4 20
[5 empty] | Design | Month1 WK 1 5: 20 Days
UI/UX (Wire Frames) | bar: Month1 WK 1 5 to Month1 WK 4 20
IOS (Prototype) | bar: Month1 WK 3 15 to Month1 WK 4 20
Android (Prototype) | bar: Month1 WK 3 15 to Month1 WK 4 20
Web (Prototype) | bar: Month1 WK 3 15 to Month1 WK 4 20
FS | bar: Month1 WK 2 10 to Month1 WK 4 20
Test Cases | bar: Month1 WK 2 10 to Month1 WK 4 20; Month 2 WK 6 30
[5 empty] | Development | Month1 WK 3 15: 25-30 Days
Web | bar: Month1 WK 3 15 to Month 2 WK 7 35
Android | bar: Month1 WK 3 15 to Month 3 WK 9 45
IOS | bar: Month1 WK 3 15 to Month 3 WK 10 50
API | bar: Month1 WK 3 15 to Month 2 WK 6 30
[5 empty] | QA | Month 2 WK 7 35: 30 Days
Testing | bar: Month 2 WK 7 35 to Month 3 WK 12 60
Bug Fixing | bar: Month 2 WK 7 35 to Month 3 WK 12 60
Acceptance | bar: Month1 WK 1 5 to Month 3 WK 12 60
Release | bar: Month1 WK 1 5 to Month 3 WK 12 60