## Mobile App-Android
17/08/2017
Thursday
Hanayen Group of Companies
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 16 | 2 | 2
Functional Specification | 8 | 1 | Web Developer | 1 | 68 | 8.5 | 8.5 | 21 | 21
Project Management | 8 | 1 | iOS Developer | 1 | 52 | 6.5 | 6.5
Graphic Design (Android App + Web application) | 8 | 1 | Android Developer | 1 | 48 | 6 | 6
Working Prototype (Web) | 8 | 1 | PM | 1 | 8 | 3 | 3
Development |  |  | QA | 1 | 34 | 4.25 | 4.25 | 250
Windows Service |  |  | Technical Writer | 1 | 8 | 1 | 1
Windows Service for email campaign | 16 | 2 | Total |  | 234 |  | 31.25
Mobile App (Android)
Splash screen | 4 | 0.5 | Total Delivery days | 22.25
Show the website in mobile app | 4 | 0.5 | Total Man day Effort | 31.25
Alert when the customer reach near the store | 16 | 2 | Installation & training | 3
Notifications on additions of new products, promotions, offers | 16 | 2
Accept basic details | 8 | 1
Mobile App (iOS)
Splash screen | 4 | 0.5
Show the website in mobile app | 4 | 0.5
Alert when the customer reach near the store | 20 | 2.5
Notifications on additions of new products, promotions, offers | 16 | 2
Accept basic details | 8 | 1
Web API
Accept basic details from customers for email campaign | 4 | 0.5
List the product for notification | 4 | 0.5
List the offers for notification | 4 | 0.5
List the promotions for notification | 4 | 0.5
Web
Login | 4 | 0.5
Add Store | 4 | 0.5
Add Products | 4 | 0.5
Add Offers | 4 | 0.5
Add Promotions | 4 | 0.5
Accept Basic Details | 4 | 0.5
Send Push Notification | 12 | 1.5
Testing & Deployment |  | 0
Testing | 33.6 | 4.2
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 249.6 | 31.2
Assumptions
The application would be tested in the Google Pixel
The promotions, offers and products will be entered through the custom web application