## Ijet
| Ijet Permit Tracker |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  | Total Hours | Hours/3 phases
| Initiation |  |  | Designer | 1 | 12 | 12 |  |  | 96 | 32
| Business analysis | 32 | 4 | Sr Developer | 1 | 35 | 35 | 37.75 | 110 | 280 | 93.3333
| Project Management | 41.66 | 5.2075 | Jr Developer | 1 | 50 | 50 |  |  | 400 | 133.3333
| Design and Prototype | 96 | 12 | Android | 1 | 25 | 25 |  |  | 200 | 66.6667
| Development |  |  | PM | 1 | #REF! | #REF! |  |  | #REF! | #REF!
| Application basic setup | 8 | 1 | BA | 1 | #REF! | #REF! |  |  | #REF! | #REF!
| Admin Module |  |  | Tech writer | 1 | 3 | 3 |  |  | 24 | 8
| Manage School departments or sections | 6 | 0.75 | QA | 2 | 6.6625 | 13.325 |  |  | 106.6 | 35.5333
| Manage Exercise categories for each department | 6 | 0.75 | Total |  |  | #REF!
| User Management | 12 | 1.5
| User Groups | 6 | 0.75
| Manage user entitlements and access rights | 8 | 1 | Total Delivery days | 68.6625
| Manage Exercises | 12 | 1.5 | Total Effort | #REF! | (+1 Day deployment)
| upload Photos, Videos, Image, Text | 12 | 1.5
| Add exercise tags for searching and indexing | 12 | 1.5
| Link Departments, staff, users etc | 6 | 0.75
| Exercise Content editor | 16 | 2 | Resource Loading
| Exercise content templates | 8 | 1 | Resource/Skill | Phase 1 | Phase 2 | Phase 3
| Approve new exercises (video, image, text etc) uploaded by staff | 6 | 0.75 | Project Manager | 52 | 40 | 40
| Receptionist module |  |  | Business Analyst | 48 | 32 | 32
| Login, Forgot password | 6 | 0.75 | User Experience | 52 | 32 | 32
| register patient | 8 | 1 | Application Architect | 24 | 8 | 8
| Register extenal patients | 8 | 1 | Lead Developer | 94 | 94 | 94
| Manage patient database | 8 | 1 | Developer | 134 | 134 | 134
| Staff Module |  |  | Database Architect | 24 | 8 | 8
| Login, Forgot password | 6 | 0.75 | IOS Developer | 67 | 67 | 67
| Add / manage new training videos, images and text | 6 | 0.75 | QA | 111 | 111 | 111
| Staff uploaded excercises available on staff dashboard | 6 | 0.75 | Tech Writer | 12 | 8 | 8
| Share excercises with other staff or external patients | 4 | 0.5 | Total Effort | 210.75 |  | 1686 | 200.75
| Mark excersices as favourite | 4 | 0.5 |  | sum(
| Share as links with patients via SMS | 8 | 1
| Print Excercises | 8 | 1
| Add Excersise notes while printing or sharing | 4 | 0.5 | lekshmi's Phase wise split
| General application features |  |  | phase start | Phase end | Days
| Simpple search & advanced search | 16 | 2 | 22-06-2017 | 2017-10-08 | 35
| Send Feedback | 6 | 0.75 | 2017-10-08 | 25/09/2017 | 33
| dashboard for staff, receptionist, admins (Fav, Viewed, History, Shared, recommended excersises, Excersice charts etc.) | 32 | 4 | 26/09/2017 | 2017-02-11 | 31
| Intranet Manual | 24 | 3
System features
| Authentication & authorization | 6 | 0.75
| Auditing & logging | 6 | 0.75
| Exception handling | 6 | 0.75
| Manage files and folders | 6 | 0.75
| Generate thumbnail for videos and images | 6 | 0.75
| Automatic backup |  | 0
| Subdomaining or domaining |  | 0
Quality Assurance
| QA & Bug Fixing | 90.6 | 11.325
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 586.26 | 73.2825
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Inspection -> Route map recording
Permissions of all usertypes
Inspection -> Inspection process should be recorded?
Mobile Devices - Android device with scanner and required SKD need to provide
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Sheet1
Client (Operator Pilot) | Admin |  | System | External System | Opration Staff
Register (Email) | Login |  | Email | AFTN | Login
Login(forgot password, Remember password, verify Email) | Approve Registration (Email Approval with link) |  | Generate PDF | ARINC | Requests Dashboard (delayed Permits)
Register Aircrafts (Air Craft Master Data) | Receive flight permissions (RPA) |  | generate Password | CAA | Issue Permits
List old flights |  | Email (Predefined Format) |  | Agents
Add Operator |  | Web Form |  | Payment Gateway
Request Flight: Add a new Trip (Operator, Aircraft Registration, Aircraft Type, MTOW, Call Sign, +SubCrafts, Add Legs: Flight #, Departure Airport, Departure Date and time, ETA, Purpose of flight, +More legs) |  | AFTN (Predefined Format) | Request Route
Request Flight Permit |  | ARINC (Predefined Format)
Choose Local Agent |  | Local Agents (Predefined Formats)
Pay fees (Based On Number of flights, Aircrafts and accounts) |  | CAA Systems (API)
Receive permit |  | Manual
Revise Schedule for flight | User Management
rate Agents | Master Data Management
In Process Trips |  | Airports
Route Details + Estimated route and FIR's |  | Aircrafts
Request services ( Landing Permit, Over-fligh Permits, Suggested over flight permits, Suggested Permits) |  | Countries
Permit Methods
Permit Requirements
Local Agents (Services Provided)
Payments for Agents
Services provided by CAA via API
Update Permit Status
Create Email templates
Create Reports