## Ijet
| Ijet Permit Tracker |  | 13/09/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  | Total Hours
| Initiation |  |  | Designer | 1 | 5 | 5 |  |  | 40
| Business analysis (SRS, Proj Plan, Weekly Status, Test Cases, User Manuals) | 32 | 4 | Sr Developer | 1 | 25 | 25 | 51.75 | 57 | 200 | 57 | 57
| Project Management | 63.504 | 7.938 | Jr Developer | 1 | 32 | 32 |  |  | 256
| Design and Prototype | 40 | 5 | PM | 1 | 7.938 | 7.938 |  |  | 63.504
| Development |  |  | BA | 1 | 4 | 4 |  |  | 32
| Application basic setup | 8 | 1 | Tech writer | 0 | 0 | 0 |  |  | 0
| Client (Operator Pilot) |  |  | QA | 2 | 10.69 | 21.38 |  |  | 171.04
| Client Registration (Verify Email) | 12 | 1.5 | Total |  |  | 95.318 |  |  | 762.544
| Client Login (Forgot PW, Remember PW) | 12 | 1.5
| Register Aircrafts (type, MTOW, Call Sign Etc) | 12 | 1.5
| Add Flight Information (Flight #, Departure Airport & DateTime, Arrival Airport & DateTime, | 12 | 1.5 | Total Delivery days | 47.69
| Add Route information | 12 | 1.5 | Total Effort | 95.318 | (+1 Day deployment)
| Add Legs | 12 | 1.5
| Select Route Using Flight Planner | 6 | 0.75
| Submit Documents or attachments | 12 | 1.5
| Select Local Service Agent (Based on country, Airport & Agent Ratings, Faster Than CAA, Less Requirments, Cost) | 16 | 2 | Resource Loading
| Request Flight Permit | 12 | 1.5
| Pay Fees (# of aircrafts, # of User Accounts, # Of international flights) | 40 | 5
| Receive Permit and email notifications (Permit #, Validity, Soft Copy, AFTN Message) | 8 | 1
| Recall Flight Schedule & Revise Schedule | 10 | 1.25
| Receive Tickets | 8 | 1
| Rate Agents | 12 | 1.5
| Client Dashboard (Requested, Approved, Comlpeted) | 16 | 2
External System Integration (Via API, RPA… TBD)
Payment Gateway (Potentially Multiple)
| ARINC |  | 0
| AFTN |  | 0
| CAA |  | 0
| Local Service Agents (Potentially) |  | 0
| Admin |  | 0
| Approve Registration (of Clients) | 6 | 0.75
| User Management | 24 | 3
| Receive Flight permissions from multiple sources (Email, AFTN, ARINC, CAA, by Phone) | 16 | 2
| Master Data Management ( Countries, Cities, Airports, Air Crafts, Operators, Permit Types ) | 32 | 4
| Flight Permit Requirments by :Carrier,Airport, Country etc | 10 | 1.25
| Add Local Agents (country, Airport & Agent Ratings, Faster Than CAA, Less Requirments, Cost etc.) | 10 | 1.25
| Manage Permit Status and permissions | 12 | 1.5
| Email Clients | 12 | 1.5
| Manage Email Templates | 12 | 1.5
| Admin Dashboard | 16 | 2
System features
| Authentication & authorization | 16 | 2
| Auditing & logging | 6 | 0.75
| Exception handling | 6 | 0.75
| Manage files and Attachments | 8 | 1
| Email | 8 | 1
| PDF Generation | 16 | 2
Operation Staff
| Operational Staff Dashboard | 16 | 2
| Issue Permits | 10 | 1.25
Quality Assurance
| QA & Bug Fixing | 155.04 | 19.38
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 770.544 | 96.318
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Inspection -> Route map recording
Permissions of all usertypes
Inspection -> Inspection process should be recorded?
Mobile Devices - Android device with scanner and required SKD need to provide
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Sheet1
Client (Operator Pilot) | Admin |  | System | External System | Opration Staff
Pilot or Operator Registeration (Email) | Login |  | Email | AFTN | Login
| Approve Registration (Email Approval with link) |  | Generate PDF | ARINC | Requests Dashboard (delayed Permits)
Register Aircrafts (Air Craft Master Data) | Receive flight permissions (RPA) |  | generate Password | CAA | Issue Permits
|  | Email (Predefined Format) |  | Agents
Add Operator |  | Web Form |  | Payment Gateway
Request Flight: Add a new Trip (Operator, Aircraft Registration, Aircraft Type, MTOW, Call Sign, +SubCrafts, Add Legs: Flight #, Departure Airport, Departure Date and time, ETA, Purpose of flight, +More legs) |  | AFTN (Predefined Format) | Request Route
Request Flight Permit |  | ARINC (Predefined Format)
Choose Local Agent |  | Local Agents (Predefined Formats)
Pay fees (Based On Number of flights, Aircrafts and accounts) |  | CAA Systems (API)
Receive permit |  | Manual
Revise Schedule for flight | User Management
Rate Agents | Master Data Management
In Process Trips |  | Airports
Route Details + Estimated route and FIR's |  | Aircrafts
Request services ( Landing Permit, Over-fligh Permits, Suggested over flight permits, Suggested Permits) |  | Countries
Permit Methods
Permit Requirements
Local Agents (Services Provided)
Payments for Agents
Services provided by CAA via API
Update Permit Status
Create Email templates
Create Reports
Add Local Agents (For Country, City & Airport, Faster than CAA, )
Flight Permit Requirments per airport and aircraft
Note on A3: Prashant: What are the registration Details? Are they separate for Pilot and Operator?
Note on A5: Prashant: Aircraft details for registration. Approximate number of fields.
Note on J5: Prashant: How?
Note on A7: Prashant: Determine Operator Details? Can we have a relationship drawn on paper. Relationship between operator, flights, routes, operators, Pilots, Operation Staff, Agents etc
Note on A11: Prashant: Fee calculation is too vague to provide an estimate
Note on A13: Prashant: Wouldn’t this require the whole process to be repeated in some cases
Note on D15: Prashant: Should include documentation requirments for issuing permits
Note on C26: Prashant: there should be more criteria based on document requirements