## Jeheziya
| Jaheziya CRM Solution |  | April 20 2017
Thursday
Sl. No. | Module | Man Hours | Man Days
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 5 | 5
2 | Functional Specification | 8 | 1 | Sr Developer | 1 | 5 | 5 | 23.5 | 24
3 | Project Management | 8 | 1 | Jr Developer | 1 | 19 | 19
4 | Finalising and purchase of HTML Theme & Images | 0 | 0 | PM | 1 | 3 | 3
5 | Complete running prototype | 40 | 5 | QA | 2 | 5 | 10
| Development | 0 |  | Total |  |  | 42
| Dash Board | 8 | 1
| Reports* | 24 | 3 | Total Delivery days | 32
5 | Meetings Calender | 16 | 2 | Total Effort | 42 | + ~1 day for deployment
6 | Inbox | 16 | 2
8 | Accounts | 8 | 1
9 | Notes | 8 | 1
10 | Manage Account | 8 | 1
11 | Manage Contacts | 8 | 1
12 | Manage Leads | 8 | 1
13 | Manage Oppurtunities (Sales & Inquiries) | 24 | 3
14 | Manage Tasks (Workflow & Approvals) | 24 | 3
15 | Add Notes | 8 | 1
16 | Manage Marketing Campaigns | 24 | 3
17 | Admin
18 | Manage Users | 4 | 0.5
19 | Testing & Deployment
20 | Testing | 75.2 | 9.4
21 | UAT | 12 | 1.5
22 | Deployment | 4 | 0.5
23 | Total Effort |  | 42.9
24 | Assumptions
25 | Running prototype: 10 screens with 4hrs each for development
26 | Reports: mxumum of 3 simple reports
27 | Contacts & leads are created without any predefined criteria or business logic
28 | Marketing campaign : Hardcoded template based emails send to a mailing list
29 | Accounts will have contacts, leads & opportunities
30 | Opportunities can have multiple tasks
31 | Tasks will be send for approval based on a dropdown list of contacts
32 | Dashboard : Static non configurable dashboard with predefined objects on the layout
`