## Lulu Mall
| Lulu Mall |  | 2017-09-05
Tuesday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 13.625 | 13.625
2 | Functional Specification | 24 | 3 | Sr Developer | 1 | 18 | 18 | 57.75 | 58 | 192.5
3 | Project Management | 64 | 8 | Jr Developer | 1 | 40 | 40
4 | Finalize and purchase Responsive Umbraco Theme |  | 0 | PM | 1 | 8 | 8 | [6 empty] | 12.5
5 | Complete running prototype | 109 | 13.625 | BA | 1 | 6 | 6
| Development |  |  | QA | 2 | 15.9 | 31.8
| Homepage Elements (Design) | 8 |  | Total |  |  | 117.425
1 | Take Over Banner : Featured Story | 2 | 0.25
2 | Social Media Integration | 2 | 0.25 | Total Delivery days | 60.525 |  |  |  | Resource/Skill | Month 1 | Month 2 | Month 3
3 | Text with image Blocks (Events, Movie, Offers, Blog, Lulu Hyper market, Fashion store,Lulu Connect, Lulu Celebrate) | 4 | 0.5 | Total Effort | 117.425 | (+1 Day deployment) |  |  | Proj. Manager | 32 | 24 | 24 | 80
4 | Rolling Ribbon product Banner | 1 | 0.125 | [5 empty] | Architect | 40 | 4 | 4
5 | Search | 3 | 0.375 | [5 empty] | Business Analyst | 48 | 12 | 12 | 72 | 48
6 | Corporate Menu (Site Map, Gallery, Newsroom, Feedback, Careers, Marriot, Offers, Store Locator) | 2 | 0.25 | [5 empty] | User Experience | 80 | 17 | 12 | 109 | 109
7 | Corporate Menu small (Services, Location Map, Events, Leasing Enquiries, Contact Us, Privacy Policy) | 3 | 0.375 | Suggestions |  |  |  |  | Team Lead Web | 80 | 160 | 80 | 720 | 464
8 | Main Events Start and stopt time (Ex. Film, Food, Fun, Hypermarket, Fashion) | 2 | 0.25 | Live videos |  |  |  |  | Web Developer | 80 | 160 | 160
9 | Main Menu Top (Home, Offers & promotions, Brands, Lulu Happiness, Image Gallery, Services, Feedback, Contact Us, Blog, Coorporate-The Mall, Leasing Enquiries, Careers) | 3 | 0.375 | Corpoate Sites | hours | days |  |  | QA | 56 | 100 | 100 | 256 | 254.4
10 | Main Menu Featured with Icons(Fashion, Food, Fun, Film , E-Magazine, Floor Plan) | 3 | 0.375 | Effort for corporate site (4hrs*28 pages) | 112 | 14 |  |  | Total Effort |  |  | 1285
11 | Admin Section for managing the page | 24 | 3 | Additional Effort per site | @.25 | 3.5 | [5 empty] | 939.4
| Fashion Main Page (Design) | 8 |  | 11 sites | days | 35
12 | Ribbon Banner | 3 | 0.375 | total (org + addnl) |  | 49 |  |  | 840
13 | New Deals | 3 | 0.375 | Mall sites | Hours | days
14 | Opening Soon | 1 | 0.125 | Effort per site | 944 | 118
15 | Search inside Fashion Category | 4 | 0.5 | Additional Effort per site | @.15 | 29.5 |  |  | Resource/Skill | Month 1 | Month 2 | Month 3
16 | Images of all fashion retailers with roll over desciption of location in Mall, business description, Phone No , email Address & web address | 3 | 0.375 | 18 sites | days | 531 |  |  | Proj. Manager | 32 | 24 |  | 56
17 | Page management | 24 | 3 | Total |  | 649 |  |  | Architect | 40 | 4
| Food Main Page ( Content updateable by Lulu Staff) - Design | 3 | [6 empty] | Business Analyst | 48 | 12 |  | 60 | 48
18 | Ribbon Banner | 1 | 0.125 | Grand Total |  | 698 | days |  | User Experience | 80 | 17 |  | 97 | 109
19 | New Deals | 1 | 0.125 |  |  | 837600 |  |  | Team Lead Web | 80 | 160 |  | 560 | 464
20 | Opening Soon | 1 | 0.125 |  |  | 586320 | 840 |  | Web Developer | 160 | 160
21 | Search inside Fashion Category | 1 | 0.125 |  |  | 513728 | 28.5326 |  | QA | 56 | 160 |  | 216 | 254.4
22 | Images of all fashion retailers with roll over desciption of location in Mall, business description, Phone No , email Address & web address | 1 | 0.125 |  |  | 17714.7586 |  |  | Total Effort |  |  | 1033
23 | Page management | 16 | 2 |  |  | 452080.64 | [5 empty] | 0
| Fun Main Page ( Content updateable by Lulu Staff) - Design | 3 |  |  |  | 15588.9876
24 | Ribbon Banner | 1 | 0.125
25 | New Deals | 1 | 0.125
26 | Opening Soon | 1 | 0.125
27 | Search inside Fashion Category | 1 | 0.125
28 | Images of all fashion retailers with roll over desciption of location in Mall, business description, Phone No , email Address & web address | 1 | 0.125
29 | Page management | 16 | 2
| Movie Main Page ( Content updateable by Lulu Staff) - Design | 6
30 | Ribbon Banner | 1 | 0.125
31 | Search by name or category (Bollywood, Hollywood , Tollywood etc) | 8 | 1
32 | Thumbnail image along with large image | 4 | 0.5
33 | Movie Title, Language, Ratings, Movie Schedule, Length, Description, Censor rating explanation | 8 | 1
34 | Page management | 24 | 3
| Emagazine Main Page ( Content updateable by Lulu Staff) - Design | 6
35 | Ribbon Banner | 1 | 0.125
36 | Drop down by year | 4 | 0.5
37 | Subscribe or invite friend (Name & Email address, Invitation button) | 4 | 0.5
38 | Scrolling magazine images for selected year. Clicking will open a PDF magazine | 4 | 0.5
39 | Page Management | 16 | 2
| Floor Plan Main Page ( Content updateable by Lulu Staff) - Design | 5
40 | Tabbed Images for Ground, First, Second and third floor | 4 | 0.5
41 | Key to Map Symbols | 1 | 0.125
42 | Shops on the floor by category | 8 | 1
43 | Page management | 16 | 2
| Offers and Promotions Main Page ( Content updateable by Lulu Staff) - Design | 8
44 | Updateable Promotions (images or text) | 4 | 0.5
45 | Tilable Images | 3 | 0.375
46 | Promotion Details | 3 | 0.375
47 | Page management | 8 | 1
| Brands Main Page ( Content updateable by Lulu Staff) - Design | 8
48 | Brand descriptions | 3 | 0.375
49 | Updateable Brand Images (images or text) | 2 | 0.25
50 | Scrollable Images | 3 | 0.375
51 | Page management | 8 | 1
| Lulu Happiness Page ( Content updateable by Lulu Staff) - Design | 4
52 | Banner image | 3 | 0.375
53 | Main Content and images | 3 | 0.375
54 | Page management | 8 | 1
| Image Gallery Page ( Content updateable by Lulu Staff) - Design | 4
55 | Scrollable Event master pages | 3 | 0.375
56 | Scrollable event detail Pages with Image pop up | 2 | 0.25
57 | Page management | 8 | 1
| Services Page ( Content updateable by Lulu Staff) -Design | 4
58 | List Services (Scrollable) | 2 | 0.25
59 | Add new services | 2 | 0.25
60 | Service detail pages and links to content pages | 2 | 0.25
61 | Page management | 8 | 1
| Feed back page ( Content updateable by Lulu Staff) -Design | 5
62 | Feed back form with ~ 20 fields and submit button | 8 | 1
63 | Contact Details | 1 | 0.125
64 | Header image | 1 | 0.125
65 | Captcha | 1 | 0.125
66 | Page management | 16 | 2
| Contact US page ( Content updateable by Lulu Staff) | 5
67 | Google map with pins | 3 | 0.375
68 | Address and contact details | 1 | 0.125
69 | Banner image + other images of the mall | 2 | 0.25
70 | Page management | 8 | 1
| Blog | 8
71 | Wordpress or Umbraco based blog with preselected theme | 48 | 6
| Other Pages | 8
72 | The Mall Page | 4 | 0.5
73 | Leasing Enquiries Page with content and form | 4 | 0.5
74 | Simple Career listing page | 4 | 0.5
75 | News with downloadable images and featured news sections | 8 | 1
76 | Location Map with directions | 4 | 0.5
77 | Events Page with tabbed events (current, coming soon and past) | 6 | 0.75
78 | Privacy Policy | 4 | 0.5
| Analytics Dashboard | 8
79 | Umbraco extension for Analytics (Via Google) Or through Google API | 8 | 1
80 | Demographics by Country, Language | 6 | 0.75
81 | Cohort Analysis | 6 | 0.75
82 | Demographics by Age and gender | 6 | 0.75
83 | Audience Overview | 6 | 0.75
84 | By network referrals | 6 | 0.75
85 | Most visits by time of day | 4 | 0.5
86 | Most used key words | 4 | 0.5
87 | Most visited page | 4 | 0.5
| Admin | 8
88 | Admin Dashboard | 16 | 2
89 | Create And manage Users | 4 | 0.5
90 | Manage User groups | 4 | 0.5
91 | Create New pages | 4 | 0.5
92 | Create categories | 4 | 0.5
93 | Create tags | 4 | 0.5
94 | Set content Expiration for pages | 4 | 0.5
95 | Customizable content pages | 4 | 0.5
96 | Add custom Images | 4 | 0.5
97 | Add movie categories and link movies | 4 | 0.5
98 | Add news | 4 | 0.5
99 | Add Deal Type | 4 | 0.5
100 | Add Deals (fashion, Food, Brands, fun) | 4 | 0.5
101 | Add custom Video | 4 | 0.5
System Features
102 | Authentication and Authorization | 4 | 0.5
103 | Permission based access levels | 4 | 0.5
104 | Bilingual website | 3 | 0.375
105 | Microsoft Word Integration for publishers | 3 | 0.375
106 | Version Rollback | 2 | 0.25
107 | Sheduled Publishing | 2 | 0.25
108 | Mobile friendly site | 2 | 0.25
109 | SEO Friendly | 4 | 0.5
110 | Advanced workflow and appoval process | 6 | 0.75
111 | Blog posts linked to social media | 5 | 0.625
112 | User Friendly content management for editors | 6 | 0.75
113 | Auditing and logging | 6 | 0.75
| Quality Assurance |  | 0
114 | QA | 246.4 | 30.8
115 | UAT | 8 | 1
116 | Penetration testing | 8 | 1
117 | Deployment | 8 | 1
118 | Training & Development for Core Members | 8 | 1
| Total Effort | 1094.4 | 136.8
| Estimate Assumptions. Effort does not include languages other than English and Arabic. Creatives will be supplied by Client Development Contingent upon timely feedback from client Blog estimation assumes a simple blog similar to the current site (design included) Analytics is based on Google. Effort quoted for integration. Free without Integration | 136.8