## MECRC
| MECRC |  | Feb 08 2017
Wednesday
Sl. No. | Module | Man Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer
1 | Requirements gathering and documentation (SRS) | 16 | 2
2 | Functional Specification | 20 | 2.5
3 | Finalising and purchase of HTML Theme & Images | 0 | 0 | Sr. Developer
4 | Complete running prototype | 40 | 5 | Junior Developer
5 | Development & Testing (PHP-codeigniter) | 0 |  | QA
6 | MECRC Admin | 0 |  | Total |  |  | 0
7 | Manage User | 4 | 0.5
8 | Manage Permission | 8 | 1 | Total Delivery days
9 | Manage Customer | 4 | 0.5 | Total Effort
10 | Manage Generator | 4 | 0.5
11 | Dashboard | 4 | 0.5
12 | Manage Bookings | 4 | 0.5
13 | Manage Hiring | 8 | 1
14 | Confirm | 0
15 | Generate Reciept | 0
16 | Send Alert SMS& Email | 0
17 | Generator Dispatch Gate out | 8 | 1
18 | Check Status | 0
19 | Generate Reciept | 0
20 | Send Alert Email | 0
21 | Generator Receive Gate In | 4 | 0.5
22 | DG Set Dispatch Slip | 0
23 | Customer | 0
24 | Login | 0 | 0
25 | Dashboard & Search | 8 | 1
26 | Add credit | 4 | 0.5
27 | Genset Booking | 8 | 1
28 | Genset Hiring | 8 | 1
29 | Confirm booking & Payment | 4 | 0.5
30 | Generate QR code, Print & email | 8 | 1
31 | Inbox | 4 | 0.5
32 | Online tracking | 4 | 0.5
33 | Payment gateway integration | 16 | 2
34 | SMS Gateway integration | 16 | 2
35 | Payment Receipt | 4 | 0.5
36 | Status updates (email, SMS, System update) | 4 | 0.5
37 | API development | 20 | 2.5
38 | Develop Hybrid app | 24 | 3
39 | Testing & Bug fixing | 48 | 6
40 | Total Effort | 304 | 38
Assumption
Client will purchase HTML theme
Only one language - English
API will be provided to update genset location
Assuming Customer Will need access via the web also

## Native Android App
Module | Design and Api integration | Design and Api integration
| Man Hours (Android default Screen Design) | Man Days
Login | 4 | 0.5
Navigation menu | 4 | 0.5
Dashboard | 12 | 1.5
Booking | 8 | 1
Hiring | 8 | 1
Booking confirmation | 4 | 0.5
Confirm QR code | 4 | 0.5
Inbox | 8 | 1
Make Payment page | 4 | 0.5
Payment getway integration | 32 | 4
QR code generater library integration (optional) | 16 | 2
Online tracking and expected time | 16 | 2
Setting up project environment | 8 | 1
Testing | 32 | 4
Total | 160 | 20