## MECRC
| MECRC |  | Feb 08 2017
Wednesday
Sl. No. | Module | Man Hours | Man Days | Hybrid App Only
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 5 | 5
2 | Functional Specification | 20 | 2.5 | Sr Developer | 1 | 7 | 7 | 22.5
3 | Finalising and purchase of HTML Theme & Images | 0 | 0 | Jr Developer | 1 | 16 | 16
4 | Complete running prototype | 40 | 5 | PM | 1 | 4.5 | 4.5
| Development |  |  | QA | 2 | 3 | 6
5 | MECRC Admin | 0 |  | Total |  |  | 38.5
6 | Manage User | 4 | 0.5
7 | Manage Permission | 8 | 1 | Total Delivery days | 28.5 | + 2 (UAT+Deployment)
8 | Manage Customer | 4 | 0.5 | Total Effort | 39
9 | Manage Generator | 4 | 0.5
10 | Dashboard | 4 | 0.5
11 | Manage Bookings | 4 | 0.5
12 | Manage Hiring | 8 | 1
13 | Confirm | 0
14 | Generate Reciept | 0
15 | Send Alert SMS& Email | 0
16 | Generator Dispatch Gate out | 8 | 1
17 | Check Status | 0
18 | Generate Reciept | 0
19 | Send Alert Email | 0
20 | Generator Receive Gate In | 4 | 0.5
21 | DG Set Dispatch Slip | 0
22 | Customer (Hybrid Application) | 0
23 | Login | 0 | 0
24 | Dashboard & Search | 8 | 1
25 | Add credit | 4 | 0.5
26 | Genset Booking | 8 | 1
27 | Genset Hiring | 8 | 1
28 | Confirm booking & Payment | 4 | 0.5
29 | Generate QR code, Print & email | 8 | 1
30 | Inbox | 4 | 0.5
31 | Online tracking | 4 | 0.5
32 | Payment gateway integration | 16 | 2
33 | SMS Gateway integration | 16 | 2
34 | Payment Receipt | 4 | 0.5
35 | Status updates (email, SMS, System update) | 4 | 0.5
36 | API development | 20 | 2.5
37 | Develop Hybrid app | 24 | 3
38 | Testing & Deployment
| Testing | 48 | 6
39 | UAT | 8 | 1
| Deployment | 8 | 1
| Total Effort | 320 | 40
40
Assumption
Client will purchase HTML theme
Only one language - English
API will be provided to update genset location
Payment gateway needs to purchased by client
SMS Push service to be provided by client
Qrcode reader will not be provided