## MELI-Web
| MELI |  | 23/04/2018
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
1 | Business analysis | 40 | 5 | Sr Developer | 1 | 110 | 110 | 217.75 | 220
2 | Project Management | 173.4 | 21.675 | Jr Developer | 1 | 110 | 110
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 | PM | 1 | 21.675 | 21.675
4 | Complete running prototype | 80 | 10 | BA | 1 | 11 | 11
| Functional Spec | 24 | 3 | Tech writer | 1 |  | 0
| Development |  |  | QA | 2 | 38.3562 | 76.7125
| Student Portal |  |  | Total |  |  | 339.3875
1 | Student Registration | 8 | 1
2 | Student Fees - Pay online | 24 | 3
6 | Student fee notification | 8 | 1 | Delivery days | 158.3562
7 | Student transfer | 8 | 1 | Total effort | 339.3875
8 | Student awards | 6 | 0.75
9 | Student Exam online Written | 16 | 2
10 | Student Exam online Verbal | 16 | 2
11 | Student Exam results | 6 | 0.75
12 | Exam Results Certificates | 6 | 0.75
13 | Exam Results: Digital signature of examiner | 6 | 0.75
14 | Exam repeat for failed students | 12 | 1.5
15 | Reason for missing exam and Exam approval | 12 | 1.5
16 | Admission Withdrawal | 12 | 1.5
17 | Attendance management |  | 0
18 | Student ID cards | 16 | 2
19 | Biometric Attendance System | 16 | 2
20 | Student Attendance Metrics | 8 | 1
21 | SMART TV for classes (for students and teachers) | 24 | 3
22 | Feedback | 8 | 1
| Faculty Portal |  | 0
| Class management | 16 | 2
| Subject management | 16 | 2
| Class Fee managemnt | 16 | 2
| Class notifications | 8 | 1
| Class assignment record | 8 | 1
| Leave request | 8 | 1
| Comment box | 8 | 1
| Performance chart | 16 | 2
| Admin Module (Academic Director) |  | 0
23 | Campus management | 24 | 3
24 | Exam Management | 24 | 3
25 | Digital signature management | 24 | 3
27 | Faculty management | 24 | 3
29 | Timetable management | 32 | 4
30 | Fee schedule | 24 | 3
31 | Fess management | 24 | 3
| Attendance management (faculty + Students + Staff) | 32 | 4
32 | Calander management | 32 | 4
| Recruitment Subsystem : (Staff portal) |  | 0
33 | Personal Information | 8 | 1
34 | Salary by steps and grades (??) | 12 | 1.5
35 | Tax | 6 | 0.75
36 | Security(???) | 8 | 1
37 | Employee Status | 6 | 0.75
| Performance appriasal : (Staff portal) |  | 0
38 | Performance Appraisal Period wise | 8 | 1
39 | Increment /Promotion | 8 | 1
40 | Employee with “X” performance rating | 8 | 1
41 | Appraisal not receive | 8 | 1
42 | Performance Position Summary | 8 | 1
43 | Confirmation Due | 8 | 1
44 | First Increment Du | 8 | 1
| Employee Transfer (current + future location) : (Staff portal) |  | 0
45 | Teachers | 8 | 1
46 | Staff | 8 | 1
47 | Privileges: Accommodation + Travel Expenses | 12 | 1.5
| Manpower Planning : (Staff Portal) |  | 0
48 | Skills | 6 | 0.75
49 | Separation List | 6 | 0.75
50 | Job function wise Analysis | 16 | 2
51 | Grade wise Separation | 12 | 1.5
52 | Employee Eligibility for gratuity | 12 | 1.5
53 | Experience Status | 8 | 1
54 | Background | 8 | 1
55 | Employee growth Report | 8 | 1
| Promotions and increment : (Staff Portal) |  | 0
56 | Branch wise Assessment | 6 | 0.75
57 | Employee Stagnation Report | 6 | 0.75
58 | Increment and promotion Trend | 6 | 0.75
59 | List of Promoters | 6 | 0.75
60 | Job function wise Increment | 6 | 0.75
61 | Grade wise Assessment Summary | 6 | 0.75
| Payroll : (Staff Portal) |  | 0
62 | Attendance | 12 | 1.5
63 | Payroll Summary | 16 | 2
64 | Meal Charges | 12 | 1.5
65 | Payroll Employee Slip wise | 16 | 2
66 | Note: tax and Security +Meal should be deducted from Employee Salary. | 12 | 1.5
| Recruitment : (Staff Portal) |  | 0
57 | Recruitments Requisition Form | 12 | 1.5
68 | Applicants List | 6 | 0.75
69 | Note: in the Applicant list there should be option for Pending, Selected, Rejected |  | 0
70 | Standard Letters such as interview letter and Rejected Letters. | 24 | 3
| Dashboards |  | 0
71 | Student Dashboard | 32 | 4
72 | Teacher dashboard | 32 | 4
| Request Forms |  | 0
74 | Leave Request | 8 | 1
75 | Increment Salary Request | 8 | 1
76 | Over time Request | 8 | 1
77 | Promotion /Demotion Request | 8 | 1
78 | Vacancy Request | 8 | 1
79 | Resignation request | 8 | 1
80 | Transfer Request | 8 | 1
81 | Taxi form | 8 | 1
82 | Purchase Request Form | 8 | 1
83 | Item request Form | 8 | 1
84 | Request for Daily wages | 8 | 1
85 | Employee Complain Request | 8 | 1
86 | Student Complain Request | 8 | 1
87 | Request for Fuel | 8 | 1
88 | Request for transfer for staff /students | 8 | 1
89 | Request for IT ticketing | 8 | 1
90 | Maintenances Request | 8 | 1
| Inventory Management |  | 0
| Separate categories | 8 | 1
| Create and manage multiple stores per employee | 8 | 1
| Edit inventory | 8 | 1
| Regular updates on out of stock products | 8 | 1
| Informative dashboard to get all inventory info at a click of a button | 12 | 1.5
| Map stores by importing valid areas, sections, shelves, categories, etc. | 12 | 1.5
| Update inventory package as data is received from the customer | 12 | 1.5
| Basic and advanced report generating feature to give up to date info on the inventory status | 16 | 2
| Feature to export reports on to Excel, PDF and other external file formats | 12 | 1.5
| File barcode can be mapped against each ‘SKU’ and many more… | 12 | 1.5
| Item classification into divisions, sections, departments. | 12 | 1.5
| Item detail with multiple attribute and categories. | 12 | 1.5
| View reports with images | 12 | 1.5
| Sample management | 12 | 1.5
| Dead on arrival (defective items received) | 12 | 1.5
| Real time view of inventory levels with in depth inventory analysis | 12 | 1.5
| Track floor stock, warehouse stock | 12 | 1.5
| Track goods movement through various stages at barcode and package level | 12 | 1.5
| Inventory valuation on FIFO, LIFO, Average and Last purchase. | 12 | 1.5
| Inventory movement (opening, purchase, sales, consumption, closing) at quantity and value | 12 | 1.5
| Road permit tracking for all inwards and outward movement of goods | 12 | 1.5
| Inter-stock point transfer and reconciliation entries | 12 | 1.5
| Negative stock alert on each inventory movement: instead it should be freeze | 12 | 1.5
| Project Management |  | 0
| Flexibly assign resources at the project level | 12 | 1.5
| View the entire project plan with an easy-to-read chart view | 12 | 1.5
| Identify and view task assignments in an intuitive chart format | 12 | 1.5
| Record project issues down to the task level, and track them with descriptions | 12 | 1.5
| Generate pricing estimates for pre-sale projects from underlying project plan and staffing model | 12 | 1.5
| Track changes to the project plan over time using baseline functionality | 12 | 1.5
| Manually override user cost at the project level | 12 | 1.5
| View pipeline reports, gaining visibility into future enterprise revenue and profit opportunities | 12 | 1.5
| create project-level and date-based budgets | 12 | 1.5
| budget categories to identify different budget items within the total budget amount | 12 | 1.5
| Asset Management |  | 0
| Asset Register with options for automatic depreciation (straight line and reducing balance) | 40 | 5
| Reporting |  | 0
| Performance charts | 40 | 5
| HR management reports | 40 | 5
| System Features |  | 0
91 | School ID Setup | 32 | 4
92 | Biometric Setup | 32 | 4
93 | Payment gateway | 32 | 4
94 | Email | 12 | 1.5
95 | SMS | 12 | 1.5
96 | Auditing & logging | 12 | 1.5
97 | Exception handling | 12 | 1.5
| Quality Assurance |  | 0
| QA & Bug Fixing | 609.7 | 76.2125
| UAT | 4 | 0.5
| Deployment | 4 | 0.5
| Total Effort | 2701.1 | 337.6375
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions

## MELI-Mobile
| Hours | Mandays
Prototype design | 80 | 10
Student Portal |  | 0
Student Registration |  | 0
Student Fees - Pay online |  | 0
Student fee notification |  | 0
Student transfer |  | 0
Student awards |  | 0
Student Exam online Written |  | 0
Student Exam online Verbal |  | 0
Student Exam results |  | 0
Exam Results Certificates |  | 0
Exam Results: Digital signature of examiner |  | 0
Exam repeat for failed students |  | 0
Reason for missing exam and Exam approval |  | 0
Admission Withdrawal |  | 0
Attendance management |  | 0
Student ID cards |  | 0
Biometric Attendance System |  | 0
Student Attendance Metrics |  | 0
SMART TV for classes (for students and teachers) |  | 0
Feedback |  | 0
Faculty Portal |  | 0
Class management |  | 0
Subject management |  | 0
Class Fee managemnt |  | 0
Class notifications |  | 0
Class assignment record |  | 0
Leave request |  | 0
Comment box |  | 0
Performance chart |  | 0
Staff Portal |  | 0
Recruitment |  | 0
Personal Information |  | 0
Salary by steps and grades (??) |  | 0
Tax |  | 0
Security(???) |  | 0
Employee Status |  | 0
Performance appriasal |  | 0
Performance Appraisal Period wise |  | 0
Increment /Promotion |  | 0
Employee with “X” performance rating |  | 0
Appraisal not receive |  | 0
Performance Position Summary |  | 0
Confirmation Due |  | 0
First Increment Du |  | 0
Employee Transfer (current + future location) |  | 0
Teachers |  | 0
Staff |  | 0
Privileges: Accommodation + Travel Expenses |  | 0
Manpower Planning |  | 0
Skills |  | 0
Separation List |  | 0
Job function wise Analysis |  | 0
Grade wise Separation |  | 0
Employee Eligibility for gratuity |  | 0
Experience Status |  | 0
Background |  | 0
Employee growth Report |  | 0
Promotions and increment |  | 0
Branch wise Assessment |  | 0
Employee Stagnation Report |  | 0
Increment and promotion Trend |  | 0
List of Promoters |  | 0
Job function wise Increment |  | 0
Grade wise Assessment Summary |  | 0
Payroll |  | 0
Attendance |  | 0
Payroll Summary |  | 0
Meal Charges |  | 0
Payroll Employee Slip wise |  | 0
Note: tax and Security +Meal should be deducted from Employee Salary. |  | 0
Recruitment |  | 0
Recruitments Requisition Form |  | 0
Applicants List |  | 0
Note: in the Applicant list there should be option for Pending, Selected, Rejected |  | 0
Standard Letters such as interview letter and Rejected Letters. |  | 0