## MELI-Web
| MELI |  | 23/04/2018
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
1 | Business analysis | 40 | 5 | Sr Developer | 1 | 118 | 118 | 235.05 | 236
2 | Project Management | 161.2 | 20.15 | Jr Developer | 1 | 118 | 118
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 | PM | 1 | 20.15 | 20.15
4 | Complete running prototype | 80 | 10 | BA | 1 | 11 | 11
| Functional Spec | 24 | 3 | Tech writer | 1 |  | 0
| Development |  |  | QA | 2 | 31.875 | 63.75
| Student Portal |  |  | Total |  |  | 340.9
1 | Student Registration | 8 | 1
2 | Student Fees - Pay online | 8 | 1 | Web Application Development
6 | Student fee notification | 8 | 1 | Delivery days | 159.875
7 | Student transfer | 8 | 1 | Total effort | 340.9
8 | Student awards | 6 | 0.75
9 | Student Exam online Written | 16 | 2 | Andorid App development | 95.475
10 | Student Exam online Verbal | 16 | 2 | IOS Application development | 109.7962
11 | Student Exam results | 6 | 0.75
12 | Exam Results Certificates | 6 | 0.75
13 | Exam Results: Digital signature of examiner | 6 | 0.75
14 | Exam repeat for failed students | 6 | 0.75
15 | Reason for missing exam and Exam approval | 6 | 0.75
16 | Admission Withdrawal | 8 | 1
17 | Attendance management |  | 0
18 | Student ID cards | 12 | 1.5
19 | Biometric Attendance System | 12 | 1.5
20 | Student Attendance Metrics | 8 | 1
21 | SMART TV for classes (for students and teachers) | 12 | 1.5
22 | Feedback | 6 | 0.75
| Faculty Portal |  | 0
| Class management | 16 | 2
| Subject management | 16 | 2
| Class Fee managemnt | 16 | 2
| Class notifications | 8 | 1
| Class assignment record | 8 | 1
| Leave request | 8 | 1
| Comment box | 8 | 1
| Performance chart | 16 | 2
| Admin Module (Academic Director) |  | 0
23 | Campus management | 24 | 3
24 | Exam Management | 24 | 3
25 | Digital signature management | 24 | 3
27 | Faculty management | 24 | 3
29 | Timetable management | 32 | 4
30 | Fee schedule | 24 | 3
31 | Fess management | 24 | 3
| Attendance management (faculty + Students + Staff) | 24 | 3
32 | Calander management | 12 | 1.5
| Recruitment Subsystem : (Staff portal) |  | 0
33 | Personal Information | 8 | 1
34 | Salary by steps and grades (??) | 12 | 1.5
35 | Tax | 6 | 0.75
36 | Security(???) | 8 | 1
37 | Employee Status | 6 | 0.75
| Performance appriasal : (Staff portal) |  | 0
38 | Performance Appraisal Period wise | 8 | 1
39 | Increment /Promotion | 8 | 1
40 | Employee with “X” performance rating | 8 | 1
41 | Appraisal not receive | 8 | 1
42 | Performance Position Summary | 8 | 1
43 | Confirmation Due | 8 | 1
44 | First Increment Du | 8 | 1
| Employee Transfer (current + future location) : (Staff portal) |  | 0
45 | Teachers | 8 | 1
46 | Staff | 8 | 1
47 | Privileges: Accommodation + Travel Expenses | 12 | 1.5
| Manpower Planning : (Staff Portal) |  | 0
48 | Skills | 6 | 0.75
49 | Separation List | 6 | 0.75
50 | Job function wise Analysis | 16 | 2
51 | Grade wise Separation | 12 | 1.5
52 | Employee Eligibility for gratuity | 12 | 1.5
53 | Experience Status | 8 | 1
54 | Background | 8 | 1
55 | Employee growth Report | 8 | 1
| Promotions and increment : (Staff Portal) |  | 0
56 | Branch wise Assessment | 6 | 0.75
57 | Employee Stagnation Report | 6 | 0.75
58 | Increment and promotion Trend | 6 | 0.75
59 | List of Promoters | 6 | 0.75
60 | Job function wise Increment | 6 | 0.75
61 | Grade wise Assessment Summary | 6 | 0.75
| Payroll : (Staff Portal) |  | 0
62 | Attendance | 12 | 1.5
63 | Payroll Summary | 16 | 2
64 | Meal Charges | 12 | 1.5
65 | Payroll Employee Slip wise | 16 | 2
66 | Note: tax and Security +Meal should be deducted from Employee Salary. | 12 | 1.5
| Recruitment : (Staff Portal) |  | 0
57 | Recruitments Requisition Form | 12 | 1.5
68 | Applicants List | 6 | 0.75
69 | Note: in the Applicant list there should be option for Pending, Selected, Rejected |  | 0
70 | Standard Letters such as interview letter and Rejected Letters. | 16 | 2
| Dashboards |  | 0
71 | Student Dashboard | 32 | 4
72 | Teacher dashboard | 32 | 4
| Request Forms |  | 0
74 | Leave Request | 8 | 1
75 | Increment Salary Request | 8 | 1
76 | Over time Request | 8 | 1
77 | Promotion /Demotion Request | 8 | 1
78 | Vacancy Request | 8 | 1
79 | Resignation request | 8 | 1
80 | Transfer Request | 8 | 1
81 | Taxi form | 8 | 1
82 | Purchase Request Form | 8 | 1
83 | Item request Form | 8 | 1
84 | Request for Daily wages | 8 | 1
85 | Employee Complain Request | 8 | 1
86 | Student Complain Request | 8 | 1
87 | Request for Fuel | 8 | 1
88 | Request for transfer for staff /students | 8 | 1
89 | Request for IT ticketing | 8 | 1
90 | Maintenances Request | 8 | 1
| Inventory Management |  | 0
| Separate categories | 8 | 1
| Create and manage multiple stores per employee | 8 | 1
| Edit inventory | 8 | 1
| Regular updates on out of stock products | 8 | 1
| Informative dashboard to get all inventory info at a click of a button | 12 | 1.5
| Map stores by importing valid areas, sections, shelves, categories, etc. | 12 | 1.5
| Update inventory package as data is received from the customer | 12 | 1.5
| Basic and advanced report generating feature to give up to date info on the inventory status | 16 | 2
| Feature to export reports on to Excel, PDF and other external file formats | 12 | 1.5
| File barcode can be mapped against each ‘SKU’ and many more… | 12 | 1.5
| Item classification into divisions, sections, departments. | 12 | 1.5
| Item detail with multiple attribute and categories. | 12 | 1.5
| View reports with images | 6 | 0.75
| Sample management | 12 | 1.5
| Dead on arrival (defective items received) | 6 | 0.75
| Real time view of inventory levels with in depth inventory analysis | 12 | 1.5
| Track floor stock, warehouse stock | 12 | 1.5
| Track goods movement through various stages at barcode and package level | 12 | 1.5
| Inventory valuation on FIFO, LIFO, Average and Last purchase. | 12 | 1.5
| Inventory movement (opening, purchase, sales, consumption, closing) at quantity and value | 12 | 1.5
| Road permit tracking for all inwards and outward movement of goods | 12 | 1.5
| Inter-stock point transfer and reconciliation entries | 12 | 1.5
| Negative stock alert on each inventory movement: instead it should be freeze | 8 | 1
| Project Management |  | 0
| Flexibly assign resources at the project level | 12 | 1.5
| View the entire project plan with an easy-to-read chart view | 12 | 1.5
| Identify and view task assignments in an intuitive chart format | 12 | 1.5
| Record project issues down to the task level, and track them with descriptions | 12 | 1.5
| Generate pricing estimates for pre-sale projects from underlying project plan and staffing model | 12 | 1.5
| Track changes to the project plan over time using baseline functionality | 12 | 1.5
| Manually override user cost at the project level | 12 | 1.5
| View pipeline reports, gaining visibility into future enterprise revenue and profit opportunities | 12 | 1.5
| create project-level and date-based budgets | 12 | 1.5
| budget categories to identify different budget items within the total budget amount | 12 | 1.5
| Asset Management |  | 0
| Asset Register with options for automatic depreciation (straight line and reducing balance) | 40 | 5
| Reporting |  | 0
| Performance charts | 40 | 5
| HR management reports | 40 | 5
| System Features |  | 0
91 | School ID Setup | 24 | 3
92 | Biometric Setup | 24 | 3
93 | Payment gateway | 32 | 4
94 | Email | 12 | 1.5
95 | SMS | 12 | 1.5
96 | Auditing & logging | 12 | 1.5
97 | Exception handling | 12 | 1.5
98 | Mobile API | 260.4 | 32.55
Quality Assurance
| QA & Bug Fixing | 486 | 60.75
| UAT | 24 | 3
| Deployment | 8 | 1
| Total Effort | 2727.6 | 340.95

## MELI-Mobile
| Hours | Mandays
Prototype design | 80 | 10
Student Portal |  | 0
Login | 8 | 1
Student Registration | 6 | 0.75
Student Fees - Pay online | 32 | 4
Student fee notification | 4 | 0.5
Student transfer | 8 | 1
Student awards | 8 | 1
Student Exam online Written | 12 | 1.5
Student Exam online Verbal | 24 | 3
Student Exam results | 6 | 0.75
Exam Results Certificates | 6 | 0.75
Exam Results: Digital signature of examiner | 6 | 0.75
Exam repeat for failed students | 8 | 1
Reason for missing exam and Exam approval | 6 | 0.75
Admission Withdrawal | 6 | 0.75
Attendance management |  | 0
Student ID cards | 16 | 2
Biometric Attendance System | 32 | 4
Student Attendance Metrics | 16 | 2
Feedback | 8 | 1
Faculty Portal |  | 0
Login | 4
Class management | 8 | 1
Subject management | 8 | 1
Class Fee managemnt | 4 | 0.5
Class notifications | 4 | 0.5
Class assignment record | 4 | 0.5
Leave request | 6 | 0.75
Comment box | 4 | 0.5
Performance chart | 12 | 1.5
Staff Portal |  | 0
Login | 2
Recruitment |  | 0
Personal Information | 8 | 1
Salary by steps and grades (??) |  | 0
Tax | 8 | 1
Security |  | 0
Employee Status | 2 | 0.25
Performance appriasal |  | 0
Performance Appraisal Period wise | 8 | 1
Increment /Promotion | 8 | 1
Employee with “X” performance rating | 8 | 1
Appraisal not receive | 4 | 0.5
Performance Position Summary | 12 | 1.5
Confirmation Due | 4 | 0.5
First Increment Du | 8 | 1
Employee Transfer (current + future location) |  | 0
Teachers | 8 | 1
Staff | 4 | 0.5
Privileges: Accommodation + Travel Expenses | 4 | 0.5
Manpower Planning |  | 0
Skills | 16 | 2
Separation List | 8 | 1
Job function wise Analysis | 8 | 1
Grade wise Separation | 8 | 1
Employee Eligibility for gratuity | 8 | 1
Experience Status | 4 | 0.5
Background | 16 | 2
Employee growth Report | 12 | 1.5
Promotions and increment |  | 0
Branch wise Assessment | 8 | 1
Employee Stagnation Report | 6 | 0.75
Increment and promotion Trend | 8 | 1
List of Promoters | 4 | 0.5
Job function wise Increment | 6 | 0.75
Grade wise Assessment Summary | 8 | 1
Payroll |  | 0
Attendance | 8 | 1
Payroll Summary | 12 | 1.5
Meal Charges | 8 | 1
Payroll Employee Slip wise | 8 | 1
Note: tax and Security +Meal should be deducted from Employee Salary. |  | 0
Recruitment |  | 0
Recruitments Requisition Form | 8 | 1
Applicants List | 8 | 1
Note: in the Applicant list there should be option for Pending, Selected, Rejected |  | 0
Standard Letters such as interview letter and Rejected Letters. |  | 0
QA | 157.8 | 22.5
Total | 763.8 | 95.475