## Android
| Ministry Of Community Development |  | 2018-09-21
# | Module | Hours | Man Days |  | No | Man Days | Total Effort
| Project Management | 65.6 | 8.2 | Designer | 1 | 12 | 12
| Business Analysis & Documentation | 40 | 5 | Android | 1.5 | 55 | 82.5 | 82 | 82.5
| UI/UX | 96 | 12 | IOS | 1.5 | 55 | 82.5
| Ui Design |  |  | PM | 1 | 8.2 | 8.2
| Page Design in XML | 247 | 30.875 | BA | 1 | 5 | 5
| Development |  |  | QA (IOS + Android) | 2 | 16.4 | 32.8
1 | Basic Setup | 8 | 1 | Total |  |  | 223
2 | Splash Screen | 1 | 0.125
3 | Registration | 2 | 0.25
4 | Forgot password | 1 | 0.125 | Total Delivery days | 83.4
5 | Login | 1 | 0.125 | Total Effort | 223
6 | Home Screen | 1 | 0.125
7 | logout | 1 | 0.125
8 | Language selection page | 6 | 0.75
9 | Profile add,edit | 2 | 0.25
10 | Privacy policy | 2 | 0.25
11 | Contact us | 2 | 0.25
12 | Settings | 2 | 0.25
13 | Suggestion | 2 | 0.25
14 | Nomow APP | 2 | 0.25
| add child | 2 | 0.25
| Generate Qr code | 2 | 0.25
| Child list page edit deleate | 4 | 0.5
| Assesment page | 8 | 1
15 | AlSanaa
| Dash board | 6 | 0.75
| Search | 2 | 0.25
| Search list | 1 | 0.125
| Product detail page | 6 | 0.75
| Cart | 6 | 0.75
| Check out page | 4 | 0.5
| Payment gateway | 24 | 3
| Add address | 1 | 0.125
| Bulk order | 1 | 0.125
16 | Tawasul APP |  | 0
| home Screen | 16 | 2
| Category page | 6 | 0.75
17 | Edaad APP
| Personal information | 2 | 0.25
| Lecture list (View ,Download ,PDF,PPT) | 6 | 0.75
18 | Edkhar APP |  | 0
| Dash board | 6 | 0.75
| Add income | 2 | 0.25
| Spending | 3 | 0.375
| Add spending | 2 | 0.25
| Add new target | 6 | 0.75
| Reports | 8 | 1
| Reminder list | 2 | 0.25
| Add reminder | 1 | 0.125
19 | Medical agenda APP |  | 0
| Appointment with search | 2 | 0.25
| add appoinment | 2 | 0.25
| Medicine list with search | 1 | 0.125
| add medicine | 1 | 0.125
| social activity list with search | 1 | 0.125
| add social activity | 1 | 0.125
| independant daily activity list with search | 1 | 0.125
| add independant daily activity | 1 | 0.125
| Notes list with search | 1 | 0.125
| Add notes | 1 | 0.125
| Back up to drop box | 6 | 0.75
| Settings | 13 | 1.625
| calender | 3 | 0.375
| calender detail page | 1 | 0.125
| Check list | 5 | 0.625
| Report | 3 | 0.375
20 | Kessas Ana Wa Akhi APP
| Dashboard | 1 | 0.125
| home screen | 1 | 0.125
| Detail page | 6 | 0.75
21 | Kessas Ejtimaeiaa lel Atfal APP |  | 0
| Dashboard | 1 | 0.125
| home screen | 1 | 0.125
| Detail page | 5 | 0.625
22 | Kessas Ejtimaeiaa lel Atfal APP1 |  | 0
| Dashboard | 1 | 0.125
| home screen | 1 | 0.125
| Detail page | 4 | 0.5
23 | Kon Sadiqi magazine |  | 0
| Dashboard | 6 | 0.75
| Home screen | 6 | 0.75
| Print email,menu | 8 | 1
| View change | 3 | 0.375
24 | MOCD APP |  | 0
| Dashboard | 6 | 0.75
| Photo list | 2 | 0.25
| Vedio list | 2 | 0.25
| you tube integration | 4 | 0.5
| Photo viewer | 2 | 0.25
| News detail page | 2 | 0.25
| Cutomer service directory | 8 | 1
| Up coming events | 4 | 0.5
| View location in google maps | 4 | 0.5
| Most used services | 4 | 0.5
| Right side menu and its page | 20 | 2.5
Api Integration
| Api integration | 104 | 13
QA
| UAT + QA | 262.4 | 32.8
| Total effort | 688 | 140
Assumptions
Games are not considered in this estimation
This estimation is based on the asumption that device orientation is on portrait mode in phones.
This estimation may vary based on additional functionalities and is currently based on description from playstore/app store.
In android it will work with kitkat and above and iOS 9.0+.