## memo printing
| Memo Printing | Sep 01 2017
Friday
Sl. No. | Module | Man Days
1 | Create SRS
2 | Create FS
3 | Project Management
4
7 | Design
11 | Create prototype of the website (except print layout) | 2
12 | Conduct meetings to discuss and finalize the prototype | 0
13 | Development and Production
15 | Set up development environment and server - PHP | 0.5
| Dashboard | 1
| Manage Customers | 1
Manage Memo Print
| Checque Deposit :: Design print layout compatible to dot metrix printer | 5
| Checque Deposit :: Manage Memo printing data | 2
| Cash Deposit :: Design print layout compatible to dot metrix printer | 3
| Cash Deposit :: Manage Memo printing data | 1.5
| CSV upload :: Checque Deposit | 2
19 | Testing and training
20 | Test for full functionality on all major and active browsers | 4
26 | Total | 22
Assumptions
Need Hard Copy of the "Memo" before starting the project
Need required printer availabe in deveopment center before starting the project
Only one language available (English)
Out Of Scope
Dynamic form creation / template