## memo printing
| Memo Printing | Sep 05 2017
Friday
Sl. No. | Module | Man Hours | Man Days
[5 empty] | No | Man hours | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 24 | 3 | 3
2 | Functional Specification | 8 | 1 | Sr.Developer | 1 | 40 | 5 | 5 | 20 | 20
3 | Project Management | 16 | 2 | Jr Developer | 1 | 120 | 15 | 15
| Design |  |  | PM | 1 | 32 | 4 | 4
4 | Design | 16 | 2 | QA | 1 | 52 | 6.5 | 6.5
5 | Prototype | 8 | 1 | Total |  | 268 |  | 33.5 | 268
Development
6 | Set up development environment and server - PHP | 4 | 0.5 | Total Delivery days | 24.5
7 | Dashboard | 8 | 1 | Total Man day Effort | 33.5 | 28.5
8 | Manage Customers | 8 | 1 | Installation & training | 1
9 | Manage Memo Print
10 | Checque Deposit :: Design print layout compatible to dot matrix printer | 40 | 5
11 | Checque Deposit :: Manage Memo printing data | 16 | 2
12 | Cash Deposit :: Design print layout compatible to dot matrix printer | 24 | 3
13 | Cash Deposit :: Manage Memo printing data | 12 | 1.5
14 | CSV upload :: Checque Deposit & Cash Deposit | 16 | 2
15 | Print page (Cash & Cheque) | 4 | 0.5
16 | Bulk Printing | 4 | 0.5
17 | Report to show all history memo’s (cash and cheque deposit) printed with filters on dates, user and reference number | 20 | 2.5
18 | Settings for font, font size, printer selection etc | 4 | 0.5
Testing and Deployment
19 | Testing | 48 | 6
20 | UAT | 4 | 0.5
21 | Deployment & support | 4 | 0.5
| Total Effort | 272 | 34
Assumptions
Need Hard Copy of the "Memo" before starting the project
Need required printer availabe in deveopment center before starting the project
Only one language available (English)
Out Of Scope
Dynamic form creation / template