## MEService
| MEServices |  | Feb 16 2017
Thursday
Sl. No. | Module | Man Hours | Man Days |  | No | Proj Duration | Man days
| Employeee Self Service Portal (Phase 1) |  |  | Designer | 2 | 7 | 14
1 | WBS, Project Schedule, Comm plan, FS , SRS) | 40 | 5 | Sr .Net developer | 1 | 20 | 20
2 | Finalising and purchase of HTML Theme & Images |  | 0 | Sr JS Developer | 1 | 20 | 20 | 83 | 83
3 | Complete running & approved prototype | 112 | 14 | Junior .Net developer | 1 | 22 | 22
4 | ADMIN |  |  | Junior JS Developer | 1 | 21 | 21
5 | Approximately 10 master setting pages | 40 | 5 | PM | 1 | 5 | 5
6 | Login | 8 | 1 | QA | 2 | 15 | 30
7 | Employee registration | 16 | 2 | Total |  | 49 | 132
8 | Customizable Dashboards | 40 | 5
9 | Workflows | 104 | 13 | Project Completion time |  | 49 Man Days + 1 day for deployment
10 | Audit Trail | 16 | 2 | Total Effort |  | 132 man Days
11 | Access employees profile | 40 | 5
12 | Manage employee non critical data | 24 | 3
13 | Have an approval cycle to verify the employee information modification | 16 | 2
14 | Allow employee to create request for leave | 24 | 3
15 | Allow managers to approve the leave | 16 | 2
16 | Update the HR (ERP) system with the new approved leaves [Require APIs and the documentation] | 24 | 3
17 | Send notification to the employee regarding the leave request status | 8 | 1
18 | Follow up on his leave request | 8 | 1
19 | Request for salary certificate | 32 | 4
20 | Request for purchase | 40 | 5
21 | Allow the workflow of approvals for the purchase request | 40 | 5
22 | Update the procurement (ERP) system with the approved purchase requests[Require APIs and the documentation] | 24 | 3
23 | Send notification regarding the purchase request status to the employee | 8 | 1
24 | Timesheet/attendance view | 40 | 5
25 | Employee evaluation sheets | 32 | 4
26 | Receive expense claims | 24 | 3
27 | Integration with the HR and Payroll to retrieve information about the employee.[Require APIs and the documentation] | 40 | 5
28 | Testing and QA | 240 | 30
27 | UAT & GoLive | 8 | 1
| Total | 1064 | 133
| Internet Recruitment Portal (Phase 2) |  |  |  | No | Proj Duration | Man days
1 | WBS, Project Schedule, Comm plan, FS , SRS) | 40 | 5 | Designer | 2 | 7 | 14 | 13
2 | Finalising and purchase of HTML Theme & Images |  |  | Sr .Net developer | 1 | 13 | 13 | 58 | 58
3 | Complete running & approved prototype | 104 | 13 | Sr JS Developer | 1 | 13 | 13
4 | Customizable Dashboards | 32 | 4 | Junior .Net developer | 1 | 16 | 16
5 | Customizable Workflows | 120 | 15 | Junior JS Developer | 1 | 16 | 16
6 | Audit Trail | 16 | 2 | PM | 1 | 5 | 5
7 | Job seeker Registration | 24 | 3 | QA | 2 | 11 | 22
8 | List of available jobs for the job seeker | 32 | 4 | Total |  | 39 | 99
9 | Upload CV and update profile for the job seeker | 32 | 4
10 | View history of applied job | 32 | 4 | Project Completion time |  | 39 Man Days + 1 day for deployment
11 | Apply for job | 24 | 3 | Total Effort |  | 99 man Days
12 | Search for jobs | 32 | 4
13 | Employer Registration | 24 | 3
14 | The employer can create a new job | 16 | 2
15 | View list of his created jobs | 16 | 2
16 | View list of candidates who have applied for his jobs | 8 | 1
17 | Based on employer registration type he can view list of job seekers resumes. | 8 | 1
18 | Online payment for the job seeker to upgrade his registration type. | 24 | 3 |  |  |  |  | 15
19 | In case of jobs that is posted by MeServices, it shall be integrated into the recruitment system in the ERP [Require APIs and the documentation] | 24 | 3 |  |  |  |  | 15
20 | Testing & Bug fixing | 185.6 | 23.2 |  |  |  |  | 13
21 | UAT & GoLive | 8 | 1
22 | Total | 801.6 | 100.2
| Intranet Recruitment Portal (Phase 3) |  |  |  | No | Proj Duration | Man days
1 | WBS, Project Schedule, Comm plan, FS , SRS) | 40 | 5 | Designer | 2 | 7 | 14
2 | Finalising and purchase of HTML Theme & Images |  | 0 | Sr .Net developer | 1 | 18 | 18 | 76 | 76
3 | Complete running & approved prototype | 112 | 14 | Sr JS Developer | 1 | 15 | 15
4 | Customizable Dashboards | 32 | 4 | Junior .Net developer | 1 | 23 | 23
5 | Customizable Workflows | 104 | 13 | Junior JS Developer | 1 | 20 | 20
6 | Audit Trail | 16 | 2 | PM | 1 | 5 | 5
7 | Handle different companies (Add different companies) | 8 | 1 | QA | 2 | 15 | 30
8 | Handle jobs and vacancies for different companies | 16 | 2 | Total |  | 47 | 125
9 | Ability to set different hiring process/workflow for each company | 64 | 8
10 | Ability set different screening and selection criteria for each company's job | 40 | 5 | Project Completion time |  | 47 Man Days + 1 day for deployment
11 | Ability to manage the received candidate's information. | 32 | 4 | Total Effort |  | 125 man Days
12 | Should allow/have document management facility to store candidate's documents. | 16 | 2
13 | Handle the interview cycle with different workflow based on the job conditions and company | 48 | 6
14 | Allow a smart search and analytics for existing resumes. | 28 | 3.5
15 | Handle the hiring cycle | 24 | 3
16 | Give notification for next actions to be taken | 12 | 1.5
17 | Have KPIs for the recruiters performance | 56 | 7
18 | Integrate with email | 8 | 1
19 | Should give alerts for companies contract needs that are below their threshold. | 48 | 6
20 | Powerful reporting module | 56 | 7
21 | Testing & Bug fixing | 243.2 | 30.4
22 | UAT & GoLive | 8 | 1
| Total | 1011.2 | 126.4
Assumptions
Data Migration tasks have not been included in Phase 3 as the functionality and complexity of the task is not well understood. If the task is trivial, it will be completed in phase 3
|  | 16 | 2
|  | 8 | 1
|  | 8 | 1
|  | 24 | 3
|  | 24 | 3
|  | 32 | 4

## EMP_SELF_SERVICE
| Employeee Self Service Portal |  | 0
1 | Complete running & approved prototype | 160 | 20
2 | ADMIN
3 | Approximately 10 master setting pages | 40 | 5
4 | Login | 8 | 1
5 | Employee registration | 16 | 2
6 | Customizable Dashboards | 40 | 5
7 | Workflows | 120 | 15
8 | Audit Trail | 16 | 2
9 | Access employees profile | 40 | 5
10 | Manage employee non critical data | 24 | 3
11 | Have an approval cycle to verify the employee information modification | 16 | 2
12 | Allow employee to create request for leave | 32 | 4
13 | Allow managers to approve the leave | 16 | 2
14 | Update the HR (ERP) system with the new approved leaves [Require APIs and the documentation] | 24 | 3
15 | Send notification to the employee regarding the leave request status | 8 | 1
16 | Follow up on his leave request | 8 | 1
17 | Request for salary certificate | 32 | 4
18 | Request for purchase | 40 | 5
19 | Allow the workflow of approvals for the purchase request | 48 | 6
20 | Update the procurement (ERP) system with the approved purchase requests[Require APIs and the documentation] | 24 | 3
21 | Send notification regarding the purchase request status to the employee | 8 | 1
22 | Timesheet/attendance view | 40 | 5
23 | Employee evaluation sheets | 32 | 4
24 | Receive expense claims | 24 | 3
25 | Integration with the HR and Payroll to retrieve information about the employee.[Require APIs and the documentation] | 48 | 6
26 | Testing and QA | 256 | 32
27 |  | 1120 | 140

## Sheet1
1 | Intranet Recruitment Portal (Phase 2)
2 | Project Plan (WBS, Sched mgmt plan, Comm plan, FS , SRS) | 40 | 5 |  | No | Proj Duration | Man days
3 | Finalising and purchase of HTML Theme & Images |  | 0 | Designer | 2 | 7 | 14
4 | Complete running & approved prototype | 112 | 14 | Sr .Net developer | 1 | 18 | 18 | 76 | 76
5 | Customizable Dashboards | 32 | 4 | Sr JS Developer | 1 | 18 | 18
6 | Customizable Workflows | 104 | 13 | Junior .Net developer | 1 | 20 | 20
7 | Audit Trail | 16 | 2 | Junior JS Developer | 1 | 20 | 20
8 | Handle different companies (Add different companies) | 8 | 1 | PM | 1 | 5 | 5
9 | Handle jobs and vacancies for different companies | 16 | 2 | QA | 2 | 15 | 30
10 | Ability to set different hiring process/workflow for each company | 64 | 8 | Total |  | 47 | 125
11 | Ability set different screening and selection criteria for each company's job | 40 | 5
12 | Ability to manage the received candidate's information. | 32 | 4 | Project Completion time |  | 47 Man Days + 1 day for deployment
13 | Should allow/have document management facility to store candidate's documents. | 16 | 2 | Total Effort |  | 125 man Days
14 | Handle the interview cycle with different workflow based on the job conditions and company | 48 | 6
15 | Allow a smart search and analytics for existing resumes. | 28 | 3.5
16 | Handle the hiring cycle | 24 | 3
17 | Give notification for next actions to be taken | 12 | 1.5
18 | Have KPIs for the recruiters performance | 56 | 7
19 | Integrate with email | 8 | 1
20 | Should give alerts for companies contract needs that are below their threshold. | 48 | 6
21 | Powerful reporting module | 56 | 7
| Testing & Bug fixing | 243.2 | 30.4
1 | UAT & GoLive | 8 | 1
2 | Total | 1011.2 | 126.4

## RECRT_PORTAL_INTRNET
| Recruitment Portal (Intranet) |  | 0
1 | Complete running & approved prototype | 160 | 20
2 | Customizable Dashboards | 32 | 4
3 | Customizable Workflows | 120 | 15
4 | Audit Trail | 16 | 2
5 | Handle different companies (Add different companies) | 8 | 1
6 | Handle jobs and vacancies for different companies | 16 | 2
7 | Ability to set different hiring process/workflow for each company | 72 | 9
8 | Ability set different screening and selection criteria for each company's job | 40 | 5
9 | Ability to manage the received candidate's information. | 32 | 4
10 | Should allow/have document management facility to store candidate's documents. | 16 | 2
11 | Handle the interview cycle with different workflow based on the job conditions and company | 48 | 6
12 | Allow a smart search and analytics for existing resumes. | 28 | 3.5
13 | Handle the hiring cycle | 24 | 3
14 | Give notification for next actions to be taken | 12 | 1.5
15 | Have KPIs for the recruiters performance | 56 | 7
16 | Integrate with email | 8 | 1
17 | Should give alerts for companies contract needs that are below their threshold. | 48 | 6
18 | Powerful reporting module | 56 | 7
|  | 792 | 99

## RECRT_PORTAL_PUBLIC
Recruitment Public Portal
1 | Complete running & approved prototype | 160 | 20
2 | Customizable Dashboards | 32 | 4
3 | Customizable Workflows | 120 | 15
4 | Audit Trail | 16 | 2
5 | Job seeker Registration | 24 | 3
6 | List of available jobs for the job seeker | 32 | 4
7 | Upload CV and update profile for the job seeker | 32 | 4
8 | View history of applied job | 32 | 4
9 | Apply for job | 24 | 3
10 | Search for jobs | 32 | 4
11 | Employer Registration | 24 | 3
12 | The employer can create a new job | 16 | 2
13 | View list of his created jobs | 16 | 2
14 | View list of candidates who have applied for his jobs | 8 | 1
15 | Based on employer registration type he can view list of job seekers resumes. | 8 | 1
16 | Online payment for the job seeker to upgrade his registration type. | 24 | 3
| In case of jobs that is posted by MeServices, it shall be integrated into the recruitment system in the ERP [Require APIs and the documentation] | 24 | 3
| Testing & Bug fixing | 185.6 | 23.2
|  | 624 | 78