## EoI
| MoF Exchange of Information |  | 2018-03-07
Thursday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 3 | 3
| Business analysis (SRS, Project Plan, Test cases) | 24 | 3 | Sr Developer | 1 | 21 | 21 | 39.25 | 44 | 44 | 44
| Project Management | 34.4 | 4.3 | Jr Dev | 1 | 23 | 23
| Design and Prototype | 24 | 3 | PM | 1 | 4.3 | 4.3
| Development |  |  | BA | 1 | 3 | 3
| Application Basic Setup | 8 | 1 | QA | 1.5 | 9.0667 | 13.6
| Admin |  |  | Total |  |  | 67.9
1 | Master Data (Legal Basis of Request, Countries, Request Urgency, Type of Tax, Type of Information requested, Status, UAE Stakeholders:emails) | 24 | 3
4 | Manage Application Users | 16 | 2
| Registration Request |  |  | Total Delivery days | 33.0667 | 6.6133
6 | Registration Request Form | 16 | 2 | Total Effort | 67.9 | (+1 Day deployment)
7 | Parse templated Documents (Simple Spread sheet with a single tab, no formulas or special formatting that might hinder data retrieval) (optional) | 18 | 2.25
8 | RPA Implementation per document type X 1 | 12 | 1.5
9 | SMS & Email; Request receipt | 16 | 2
10 | Save documents | 4 | 0.5 | Contingency: +/- 15%
11 | Save status | 4 | 0.5
Validation
11 | Verify and Validate Data (API Services @ (4-16 Hrs per service) X 2 | 32 | 4
12 | RPA Implementation (Scraping per entity @ 4-8 hrs per instance) X 2 | 16 | 2
13 | Validation checklist | 16 | 2
14 | Update status | 4 | 0.5 | Optional Items | Change to 0 to get new estimate
| Analysis & Allocation |  |  |  | and update the proposal
15 | Generate Document (excel or PDF @ 16-24 per instance) X 1 | 24 | 3
16 | Generate Email from template @ 8 hrs per instance X 1 | 8 | 1
17 | Create forms for agencies to respond | 16 | 2
18 | Email notifications | 6 | 0.75
19 | Status updates | 4 | 0.5
| Responses & Preparation |  | 0
20 | Generate main report for requestor | 16 | 2
21 | Other reports @ 6 hrs / Report X 2 | 12 | 1.5
22 | Compose Email from template & attachments | 24 | 3
System features
27 | Authentication & Authorization | 6 | 0.75
28 | Auditing & logging | 6 | 0.75
29 | Exception handling | 6 | 0.75
| manage email templates @ 6 hrs / template | 6 | 0.75
| Manage Excel Templates @ 8 Hrs / template | 8 | 1
30 | Document management | 16 | 2
| Email & SMS | 8 | 1
Quality Assurance
31 | QA & Bug Fixing | 100.8 | 12.6
32 | UAT | 8 | 1
33 | Deployment | 8 | 1
| Total Effort | 551.2 | 68.9
Assumptions
Does not manage Inventory
Does not generate Purchase Order or Invoices
Prices are managed per instance of the item
Reports included limited to a maximum of 3
Note on B19: Prashant: competitive offer at 3-5 hrs / type for additional types
Note on B29: Prashant: 4-16 hrs after the first instance, depends on complexity
Note on B30: Prashant: 2-6 hrs for additional instances. Depends on complexity
Note on B31: Prashant: 4-16 for additional forms