## MOFA
| MOFA |  | 2019-10-04
Wednesday
| Module | Hours | Man Days |  | No of resources | Man Days | Adjusted Del Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10 | 10
1 | Business analysis | 80 | 10 | Developer | 1.5 | 55 | 36.6667 | 55 | #REF! | 60.8 | 55
2 | SRS | 40 | 5 | PM | 1 | 5.8 | 5.8 | 5.8
| UI/UX | 80 | 10 | BA | 1 | 15 | 15 | 15
3 | Project Management | 46.4 | 5.8 | QA | 1.5 | 23.2 | 15.4667 | 23.2
| Design and Development |  |  |  | Sum |  |  | 109
| Configuration and Implementation | 160 | 20 | Training |  | 3 |  | 112
1 | Data Migration | 80 | 10
2 | Development | 160 | 20 | Delivery Days | 62.1333
3 | integration | 40 | 5 | Total Effort | 109
4 | Training | 24 | 3 | Training & Deployment | 112
5 | QA & Bug Fixing | 185.6 | 23.2
6 | Total Effort | 896 | 112
7
8 | Configuration and Implementation
9 | The costs involved in installing, configurating and testing the software as well as implemeting your organization's workflows. This can usually be done in-house but may require external resources in cases where technical experise is not available. This should also include the cost of data backup / restoring processes and contingency plans if the software becomes unavailable due to power/Internet outages and hardware failures.
10 | Data Migration
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48