## MOJ-web
| Ministry of Justice-Web |  | 2018-04-09
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 15 | 15
| Business Analysis | 120 | 15 | Sr Developer | 1.5 | 45.2833 | 67.925 | 165.4375 | 189.0437 | 169.8125 | 169.8125
| Project Management | 153.85 | 19.2313 | Jr Developer | 1.5 | 67.925 | 101.8875
| Design(creative,innovative,Userfriendly) and Prototype | 120 | 15 | PM | 1 | 19.2313 | 19.2313
| Documentation (SRS, FS, Weekly Reports) | 60 | 7.5 | BA | 1 | 15 | 15
| Z |  | ` | TechWriter | 1 | 7.5 | 7.5
| Application Basic Setup | 12 | 1.5 | QA | 2 | 45.3088 | 90.6175
| Website Reference: https://moj.gov.ae/web/ejusticesite/home |  |  | Total |  |  | 317.1612
Key website modules
1 | Service Directory (List of services for public, MOJ, Legal community) |  | 0
| Services |  |  |  | Days | Months
| Legal Community |  |  | Total Delivery days | 128.2337 | 6.4117
| Electronic filing | 29 | 3.625 | Total Effort | 317.1612 | 15.8581
| Lawyer Registration | 31 | 3.875
| Translator Registration | 28 | 3.5
| Trainee Registration | 28 | 3.5 |  | Website | 25.6875
| Expert Registration | 28 | 3.5 | need clarification | Services
| ITJS Magazine | 28 | 3.5 |  | Legal Community | 24
| Registered Users | 20 | 2.5 |  | MOJ Users | 33.625
| Public Users |  |  |  | Public | 22.375
| E-notary+B109 | 25 | 3.125 |  | CMS | 13.75
| Lawyer-Lawfirm search | 18 | 2.25 |  | Search | 4.375
| Case Status Search | 16 | 2 |  | Migration | 11.25
| E-calendar | 17 | 2.125 |  | Accesibility | 33.25
| Contact Minister | 15 | 1.875
| E-zawaj | 36 | 4.5
| Minor Affairs | 24 | 3 | need clarification
| E-refund System | 28 | 3.5
MOJ Users
| E-notary | 26 | 3.25 | Need to check the feasibility. Now we can go ahead with Drupal
| CMS | 80 | 10
| E-judge | 35 | 4.375
| E-legislation | 25 | 3.125
| E-zawaj system | 25 | 3.125
| MOJ Dashboard | 28 | 3.5
| Comparative Legislations | 26 | 3.25
| Minors | 24 | 3
Web Site
About MOJ
| Our Strategy | 8 | 1
| Organizational Structure | 4 | 0.5
| Employee Gate | 0 | 0
| Careers | 0 | 0
| Legal References | 4 | 0.5
| Latest Legislation and Laws | 14 | 1.75
E-Participation
| Social Media | 4 | 0.5
| General Survey | 8 | 1
| Opinions | 6 | 0.75
| Contact Minister | 3 | 0.375
| Contact Inspection Department | 3 | 0.375 | External Link
| Legal in your help | 3 | 0.375
| Suggestions and complaints | 0 | 0
| Services Guide | 6 | 0.75 | External Link
| Services Form | 6 | 0.75 | External Link
| Facebook | 0 | 0 | External Link
| Twitter | 0 | 0 | External Link
| Youtube | 0 | 0
| Instagram | 0 | 0
Open Data
| Statistics | 16 | 2
| Policy | 6 | 0.75
Media Center
| Events & Future activities | 3 | 0.375
| Media gallery for images published on portal | 18 | 2.25
| News | 12 | 1.5
| Campaign | 15 | 1.875
| Events | 16 | 2
| Initiatives | 12 | 1.5
| Media Kit | 8 | 1
General
| Disclaimer | 0.5 | 0.0625
| Accessibility | 0.5 | 0.0625
| Privacy policy | 0.5 | 0.0625
| Archive | 4 | 0.5
| Copyright | 0.5 | 0.0625
| Terms and Conditions | 0.5 | 0.0625
| Sitemap | 8 | 1
| FAQ | 8 | 1
| Customer happiness formula | 0.5 | 0.0625
| Glossary | 0.5 | 0.0625
| Feedback form | 3 | 0.375
| Contact Us | 1 | 0.125
| Toll Free | 1 | 0.125
| Location Map | 1 | 0.125 | Browser Print - no aditional coading
| Useful links | 1 | 0.125 | Same as Events
| Print page | 0 | 0
| events calendar |  | 0
| Google Analytics |  | 0
| Follow TRA Guidelines |  | 0
| Responsive web app that scales well on tablets mobile and desktop browsers |  | 0
| Content Management System | 110 | 13.75
21 | Personalized content |  | 0
22 | Unlimited structure(Pages,News,Galleries,Publications,etc.) |  | 0
23 | Content editor – Should be able to copy & paste from word |  | 0
24 | User roles with different permissions |  | 0
25 | CMS search facility |  | 0
26 | CMS insight reports(identify non-translated contents and missing items) |  | 0
27 | Image/Document Library: |  | 0
| Image with localized Alt text |  | 0
| Media gallery for images published on portal |  | 0
28 | Related Items: Associated articles |  | 0
29 | Login/Logout |  | 0
Advanced Search
30 | Comprehensive search | 35 | 4.375
| Keyword search,date filter,Autocomplete & suggestions,contents(pages,services,news,etc |  | 0
Other Features
31 | Migrate existing website contents | 90 | 11.25
32 | Integrate google auto translate, localize content(UN recommend top 6 languages) | 20 | 2.5
33 | META description for all pages to support SEO (Friendly URLS for pages, images etc) | 20 | 2.5
34 | Integrate text to speech add-on | 32 | 4
35 | Integrate happiness meter supported by PMO Systems | 32 | 4
36 | Integrate MOJ socialmedia | 20 | 2.5
37 | Integrate MOJ Live chat service | 16 | 2
38 | Surveys & Polls | 32 | 4
| Create & publish unlimited surveys & polls |  | 0
| Archive section |  | 0
40 | Cross browser compatibility | 12 | 1.5
41 | XML site map | 23 | 2.875
42 | Accessibility features | 24 | 3
| font size,night reading,color blindness,text to speech, 3 color themes |  | 0
43 | English & Arabic site | 35 | 4.375
Quality Assurance
43 | QA & Bug Fixing | 724.94 | 90.6175
44 | UAT |  | 0
45 | Deployment per instance |  | 0
| Total Effort |  | 317.1612
Assumptions
The effort might change after a detailed system study

## Phases
Phase 1 |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | 0
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 |  | 0
BA |  | Month 1 Week 1: SYSTEM ANALYSIS; Month 3 Week 11: TESTING / BUG FIXING |  | 0
UI/UX |  | Month 1 Week 2: DESIGN |  |  | legal | 24
Developer 1 | CMS | Month 1 Week 4: CMS |  |  | MOJ | 33
Developer 2 | Migration | Month 2 Week 6: MIGRATION; Month 3 Week 10: Accessibility |  |  | Public | 22
Developer 3 | Website | Month 2 Week 6: WEBSITE
Developer 1 | Search | Month 2 Week 7: SEARCH
Developer 1 | Accessibility etc. | Month 2 Week 8: ACCESSIBILITY
QA 1 |  | Month 2 Week 5: TESTING
QA 2 |  | Month 2 Week 5: TESTING
Phase 2 |  | Month 1 Week 1: Month 3; Month 2 Week 5: Month 4; Month 3 Week 9: Month 5 | Month 6 |  |  |  | Month 7
|  | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
BA |  | Month 3 Week 9: SYSTEM ANALYSIS; Month 6 Week 24: TESTING / BUG FIX
UI/UX |  | Month 3 Week 10: DESIGN
Developer 1 | Legal Community | Month 4 Week 13: LEGAL COMMUNITY SERVICES
Developer 2 | bar: Month 4 Week 13 to Month 4 Week 16; Month 6 Week 24 to Month 7 Week 26
Developer 3 | MOJ Users | Month 4 Week 16: MOJ USER SERVICES
Developer 1 | bar: Month 4 Week 16 to Month 5 Week 20; Month 6 Week 24 to Month 7 Week 26
Developer 2 | Public | Month 5 Week 20: PUBLIC SERVICES
Developer 4 | bar: Month 5 Week 20 to Month 7 Week 26
Developer 4 | Mobile API | Month 3 Week 9: Mobile API Services
QA 1 |  | Month 4 Week 16: TESTING
QA 2 |  | Month 4 Week 16: TESTING
Phase 3 Parallel to Phase 2 |  | Month 3 Week 9: Month 4; Month 4 Week 13: Month 5; Month 5 Week 17: Month 6; Month 6 Week 21: Month 7
|  | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
UI / UX |  | Month 4 Week 13: Design; Month 6 Week 23: TESTING / BUG FIX
IOS Developer |  | Month 4 Week 16: IOS APP
Android Developer |  | Month 4 Week 16: ANDROID APP
QA 3 |  | Month 5 Week 20: IOS TESTING
QA 4 |  | Month 5 Week 20: ANDROID TESTING

## MoJ-Mobile
2019-09-04
MOJ-Mobile Application
|  | Android |  | iOS
| Module | Hours | Man Days | Hours | Man Days |  | No | hours | days | total
| Initiation |  |  |  |  | Designer | 1 | 40 | 5 | 5
| Business Analysis |  | 0 |  | 0 | Sr Mobile developer | 1 | 246 | 30.75 | 30.75 | 31.75 | 30.75
| Project Management |  | 0 |  | 0 | PM | 1 |  | 0 | 0
| Design and Prototype | 40 | 5 | 40 | 5 | BA | 1 |  | 0 | 0
| Documentation (SRS, FS, Weekly Reports) |  | 0 |  | 0 | TechWriter | 1 |  | 0 | 0
| Development |  |  |  |  | QA | 2 | 127 | 15.875 | 31.75
| Application Basic Setup | 8 | 1 | 8 | 1 | Total |  |  |  | 67.5
| Mobile Application features | [5 empty] | IOS | Android
1 | Informational Pages | 16 | 2 | 16 | 2 | Total Effort | 67.5 | 67.5 | 3.375
| News | 16 | 2 | 16 | 2 | Total delivery days | 51.625 | 51.625
2 | Events timeline | 20 | 2.5 | 20 | 2.5
| Advance search | 8 | 1 | 8 | 1
| Service search with service card | 8 | 1 | 8 | 1
| Contact us | 6 | 0.75 | 6 | 0.75
| Get directions features | 10 | 1.25 | 10 | 1.25
| Locations across the UAE | 16 | 2 | 16 | 2
| Accessibility features(minimum 3) | 32 | 4 | 32 | 4
| Theming options | 32 | 4 | 32 | 4
3 | Push Notifications | 16 | 2 | 16 | 2
| Integration with khadamati and happiness meter | 34 | 4.25 | 34 | 4.25
| English & Arabic | 32 | 4 | 32 | 4
Quality Assurance
| QA & Bug Fixing | 254 | 12.3 | 254 | 12.7
4 | UAT |  | 0 |  | 0
| Deployment per instance |  | 0 |  | 0
| Total Effort |  | 44.05 |  | 49.45
Assumptions
The effort might change after a detailed system study
Consider portrait mode only
Client shall provide the API/SDK for Khadmati and happiness meter