## RateEffort
Vehicle Accident information | 11 098 2017
Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 16 | 2 | 2
Functional Specification | 0 | 0 | Sr.Developer | 1 | 0 | 0 | 0 | 9.25 | 9
Project Management | 7.4 | 0.925 | Jr Developer | 1 | 72 | 9 | 9
Graphic Design | 8 | 1 | PM | 1 | 15.4 | 1.925 | 1.925
Working Prototype | 8 | 1 | QA | 2 | 13.1 | 1.6375 | 3.275
Development |  |  | Total |  | 116.5 |  | 16.2 | 129.6
Create Users | 4 | 0.5
Create role | 4 | 0.5 | Total Delivery days | 12.6375
Authentication authorization, logging, Auditing | 0 | 0 | Total Man day Effort | 16.2 | 12.15
Vehicle handover notes | 6 | 0.75
Vehicle accident details | 6 | 0.75
Vehicle Internal condition | 6 | 0.75
Vehicle Outside Condition | 6 | 0.75
Vehicle Report Information | 6 | 0.75
Vehicle basic information | 6 | 0.75
Vehicle Lookup | 6 | 0.75
Simple columnar Report with filters | 8 | 1
Installation executable | 8 | 1
Form View | 8 | 1
Testing & Deployment
Testing | 22.2 | 2.775
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 135.6 | 16.95
Assumptions