## Obaid
| Obaid |  | 21/06/2018
Thursday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 3 | 3
| Business analysis | 16 | 2 | Sr Developer | 1.5 | 25.3333 | 38 | 33.25 | 38 | 38 | 38
| Project Management | 30 | 3.75 | Jr Developer |  |  | 0
| Design and Prototype | 24 | 3 | PM | 1 | 3.75 | 3.75
| Development |  |  | BA | 1 | 2 | 2
| Application Basic Setup | 8 | 1 | Tech writer | 1 | 2 | 2
| Admin |  |  | QA | 1.5 | 8.1667 | 12.25
1 | Set up Parent Company & Subsidiary (Suppliers) | 4 |  | Total |  |  | 61
2 | Set Up Main Item, Item & Sub Item | 4 | 0.5
3 | Sub Item Details (Description, Measurement, Unit, Min Unit Price, Max Unit Price, Avg Unit Price - Prices calculated based on supplier prices) | 12 | 1.5
4 | Item Master | 12 | 1.5 | Total Delivery days | 36.5 | 7.3
5 | Manage Suppliers | 12 | 1.5 | Total Effort | 61 | (+1 Day deployment)
6 | Manage Prices | 16 | 2
7 | Jobs (Plaster wall, Bulk Head Etc.) | 6 | 0.75
8 | Job Types | 6 | 0.75
9 | Project Types | 6 | 0.75 | Contingency: +/- 15%
10 | Project Sub Type | 6 | 0.75
11 | Manage customers | 8 | 1
12 | Labour Group | 6 | 0.75
13 | Manage Application Users (Create, Update, Delete) | 6 | 0.75
WorkSheets
14 | Create Project & Add Customer | 8 | 1
15 | Create Scenario and multiple scenarios (Single or clubbed together in a single quote) | 16 | 2
16 | Common Project Data ( Length, Width, Room Iteration, Area, Drop Height, Furring Channel Span, Main Channel Span, Profit, Wasted Material, Over head, Labour Group, No. Of Labourers, Fin Labour Count, Days, Weeks) | 12 | 1.5
17 | Select Project Type |  | 0
18 | Select Project Levels (Dynamic Templates for Project Types) X 3 | 20 | 2.5
19 | Add Items (Dynamic Templates for Levels) X 3 | 14 | 1.75
20 | Item Details ( Name, Description, Measurement, Unit, Qty Unit Price, Cost) | 8 | 1
21 | Calculated Fields (Material Cost, Material Cost + Wasted Items, Labour Cost, Total Material Cost + Labour, Total Material Cost + Labour + Overhead, CoG/MSQ, Lbr+mtrl + Cost+ovrhd+Prft, Price/msq, Rev., Profit, Profit/Day, Profit/msq | 12 | 1.5
22 | Cost based on variable profit percentages | 6 | 0.75
23 | Page customizations | 8 | 1
24 | Create & Manage Quotes (Ability to remove scenarios) | 12 | 1.5
25 | Search and Historical lookups (8-32 hrs. depending on complexity and detail) | 12 | 1.5
26 | Export to PDF and Excel | 12 | 1.5
System features
27 | Authentication & authorization | 6 | 0.75
28 | Auditing & logging | 6 | 0.75
29 | Exception handling | 6 | 0.75
30 | Reports & Printable invoices,Quotes etc. (Optional 12 -48 hrs) | 38 | 4.75
Quality Assurance
31 | QA & Bug Fixing | 90 | 11.25
32 | UAT | 8 | 1
33 | Deployment | 8 | 1
| Total Effort | 484 | 60.5
Assumptions
Does not manage Inventory
Does not generate Purchase Order or Invoices
Prices are managed per instance of the item
Reports included limited to a maximum of 3