## Estimate (hidden)
Project Name : Fisher Mobile (Android +IOS) + Desktop App
Inputs |  | Estimation Summary (Hours and Business days) |  |  | Estimated Amount
Risk and/or "unknown" (25% ; 50% ; 25% ; 10%) | 25 | Optimistic hours | 624 | 39 | 4992 | 104
Project Complexity scale Extreme(100%); high(50%) ; medium(25%) ; low(10%) | 25 | Most likely hours** | 655.2 | 40.95 | 5241.6 | 104
Average productive hours per day | 8 | Pessimistic hours* | 686.4 | 42.9 | 5491.2 | 62.4 | Holidays in 2016 | Date
Estimation parameters | Hours |  |  |  | Estimated Amount |  | New Year's Day | 2016-01-01
Requirement gathering | 0 | Expected Duration |  | Hours | 324480 |  | Republic Day | 2016-01-26
Research and analysis | 40 | Triangular distribution method |  | 40.95 | 340704 |  | Monty Thursday | 2016-03-24
Development | 360 | Beta distribution (PERT technique) |  | 40.95 | 356928 |  | Good Friday | 2016-03-25
Design | 0 | [5 empty] | Vishu | 2016-04-14
Testing | 0 | Finish Date |  |  |  |  | May Day | 2016-05-01
Training | 0 | Earliest start date | 2016-12-01 |  |  |  | Assembly Elections | 2016-05-16
Documentation | 0 | Earliest completion date | 2017-01-26 | Optimistic |  |  | Onam | 2016-09-13
Meetings | 16 | Earliest completion date | 2017-01-27 | Most likely |  |  | Onam | 2016-09-14
Migration (data or content) | 0 | Earliest completion date | 2017-01-31 | Pessimistic |  |  | Onam | 2016-09-15
Project management | 0 | [5 empty] | Gandhu Jayanthi | 2016-10-02
Reports | 0 | Latest start date | 2016-12-15 |  |  |  | Deepavali | 2016-10-29
UAT | 0 | Latest completion date | 2017-02-09 | Optimistic |  |  | Christmas | 2016-12-26
Accessibility test | 0 | Latest completion date | 2017-02-10 | Most likely
Pre deployment process | 0 | Latest completion date | 2017-02-14 | Pessimistic
Deployment | 0
Post production testing | 0 | Pessimistic case buffer (in percentage) |  | 10
Knowledge transfer/ Service transition | 0 | No of resources (This will impact the number of business days to complete and finish date calculation.) on average |  | 2
Marketing | 0
Project retrospective | 0
* Pessimistic hours= Best case hours+ Pessimistic case buffer **Most likely=(Optimistic + Pessimistic )/2 ***Excluded Saturdays, Sundays and state holidays
Total | 416
Note on E13: Prashant Thomas: Please enter your estimated start date here

## Sitefinity Upgrade
| OpenCart |  | 2016-08-26
Friday
Sl. No. | Module | Man Hours | Man Days | Resource Type | Number | Hours | Price/Hour | Total
Sitefinity Upgrade Preliminary Preparation
1 | Document Current implementation, Customizations, external module integrations | 16 | 2 | Senior Business Analyst | 1 | 64 | 20 | 1280
2 | Backup project manager, database, CMS asseblies and configurations | 16 | 2 | Project Manager | 1 | 32 | 22 | 704
3 | Configuring the application for migration | 16 | 2 | UI/UX Designer | 1 | 8 | 14 | 112
| Total Preparation Time | 48 | 6 | Senior Developer | 1 | 48 | 18 | 864
| Upgrade |  |  | Junior Developer | 1 | 104 | 15 | 1560
| Install Sitefinity 9.2 instance |  | 0.75 | QA | 1 | 72 | 14 | 1008
5 | Install New SiteFinity Version using the sitefinity project manager | 2 |  |  |  | 328 |  | 5528
6 | Install SiteFinity SDK | 2 | [5 empty] | 5500
7 | Activate Licensing | 2
| Create & Configure Sitefinity Project |  | 1.5
8 | Work with Sitefinity CMS Project Manager | 4
9 | Create a project | 4
10 | Configure and start a project | 4
| Security & Authentication |  | 1
11 | Authentication and Single Sign On (SSO) & social media integration | 4
12 | Users, roles , permisiions | 4
10 | Configure IIS |  | 2
13 | Configure the IIS to host Sitefinity CMS projects | 8
14 | Run a Sitefinity CMS instance of an ASP.NET application | 8
| Logging, Tracking & debugging |  | 2
15 | Enable debugging and tracing of applications | 4
16 | Configure the Audit trail module Administration | 4
17 | Configure ELMAH (Error Logging Modules and Handlers) on your site | 4
18 | Performance Diagnostics module | 4
| Configure system settings |  | 4.5
19 | Disable the backend UI | 4
20 | Configure SMTP settings | 4
21 | Cache settings | 4
22 | Security settings | 4
23 | Database configuration | 4
24 | URL and link settings | 4
25 | Custom error pages | 4
26 | Configure the application restart behavior during uploads | 4
27 | Create configuration classes | 4
28 | SEO updates | 8 | 1
29 | Assemblies migraion | 4 | 0.5
30 | Language support and content localization | 4 | 0.5
31 | Payment gateway Integration | 12 | 1.5
32 | Apply Security Updates and patches | 4 | 0.5
33 | Migration of images, videos and | 16 | 2
34 | Upgrade Verification | 32 | 4
35 | Migrate related data | 32 | 4
36 | Setup email campaigns (newsletter), Personalization & CMS Analytics | 32 | 4
| Total Upgrade Time | 238 | 29.75
| Upgrade time + preparation time | 286 | 35.75
| Deploy upgraded project to site |  | 3
37 | Deployment to VPS or shared hosting only (Does not include deployment to Azure cloud/webapps or AWS) | 24
| Quality Analysis & Testing |  | 3.25
38 | Functional and integration testing | 9
39 | UAT Support & Implementation | 9
| Project Management | 24 | 3
| TOTAL | 360 | 45