## Virtual Appointment App
Virtual Appointments & Prescriptions | Aug 19 2017
Friday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 32 | 4 | 4
Functional Specification | 0 | 0 | Sr.Developer | 1 | 88 | 11 | 11 | 44.5 | 44.5
Project Management | 35.6 | 4.45 | Jr Developer | 1 | 96 | 12 | 12
Solutioning | 0 | 0 | Android Developer | 1 | 172 | 21.5 | 21.5
UI/UX (Web + Mobile) | 16 | 2 | PM | 1 | 59.6 | 7.45 | 7.45
Working Prototype | 16 | 2 | QA | 2 | 57.4 | 7.175 | 14.35 | 562.4
Development |  |  | Total |  | 505 |  | 70.3
Registration (web)
Doctor Registration (degrees, references, rating, affiliated hospitals) | 16 | 2 | Total Delivery days | 32.675
Patient registration | 8 | 1 | Total Man day Effort | 70.3
Mobile App (Design + Development) |  |  | Installation & training | 1
Login, Forgot password (doctor and patient) | 8 | 1
Patient
Search Doctor by speciality and symptom (based on loc) | 16 | 2
Request appointment | 8 | 1
Patient receives appt confirmation from doc | 8 | 1
Patient makes one time payment | 8 | 1
Upload Relevant documents | 8 | 1
Consult By Chat or video | 16 | 2
Patient receives prescription (medical or leave of absence) | 8 | 1
Patient rates doctor with comments | 8 | 1
Doctor
View Appointments (req and confirmed) | 16 | 2
Doctor accepts appointment | 8 | 1
Doctor and patient notified of the appointment (SMS, Email) | 8 | 1
Access patient documents and online consultation | 16 | 2
Doctor makes prescription (medical or leave of absence) | 20 | 2.5
Doctor receives payment | 8 | 1
Respond to comments | 8 | 1
System Functions
Manage Prescription templates for docor (medical and leave prescription) | 16 | 2
Authentication, authorization, password hashing and salting | 8 | 1
Auditing and logging | 8 | 1
SMS , OTP | 8 | 1
Patient Document management (prescriptions, uploaded documents) | 16 | 2
Patient consultation history | 8 | 1
Payment Processing (patient) | 16 | 2
Credit payments for doctor | 8 | 1
Commisions for App | 8 | 1
Admin (web)
Verify Doctors | 6 | 0.75
Manage Users | 4 | 0.5
Dashboard for Management (various) | 16 | 2
Manage Health Categories | 6 | 0.75
Mobile API
search results | 4 | 0.5
request appointments | 4 | 0.5
Accept/reject appointments | 4 | 0.5
Make appointments | 4 | 0.5
Save appointments for patient and doc | 4 | 0.5
save documents | 4 | 0.5
Serve prescriptions | 4 | 0.5
rate doctor | 4 | 0.5
Testing & Deployment
Testing | 106.8 | 13.35
UAT | 8 | 1
Deployment (Android + Web) | 8 | 1
Total Effort | 570.4 | 71.3
Assumptions
Android mobile App + Responsive Web App
IOS not included
WebApp for admin & registrations
Android store registrations and developer account provided by client
VideoChat API procurement by client