## Sheet1
Project | Web Site Design and Development |  |  | Comments
Who were the other developers involved on an activity wise basis
Client | AllStarDistributing |  |  | Was there any work in Aug?
Start & End Date | June - July 2016
Team size | 3
Total Hours (D &D) | 480
Activity | Hours | Resources | Days
Layout and Design | 130 | 1 | 16.25 |  | Summary of overall effort
Wireframes, Photoshop Designs and Jpegs |  |  |  |  | Project Description | Hours | Days
Development of HTML /CMS | 350 | 3 | 14.5833 |  | All Star Distributing | 480 | 60
HTML / CSS |  |  |  |  | Draughtlines | 480 | 60
Approved Design to HTML5 & CSS |  |  |  |  | Origlio | 460 | 57.5
Responsive Design |  |  |  |  | Issues & Enhancements
Video Header Section |  |  |  |  | July Ticketed | 7 | 0.875 | 14
Create Video for header section |  |  |  |  | July Unticketed | 105 | 13.125
Convert Design to WP CMS |  |  |  |  | August Ticketed | 204 | 25.5 | 104.25
Installed Woo Commerce |  |  |  |  | August Unticketed | 630 | 78.75
Development |  |  |  |  | September Ticketed | 136 | 17 | 65.5
Added fields which was not there in woocommerce plugin to match the requirements |  |  |  |  | September Unticketed | 388 | 48.5
Uploaded 600+ products to the woocommerce system |  |  |  |  | Total Effort |  | 361.25
Cropped images to upload to the system
Created training materials to upload / maintain the site
Design changes as per requirements
Testing
Usability testing
Functionality testing
Responsive testing
Total Effort in days | 60 | Total Del Days | 30.8333
Client | Draughtlines
Start & End Date | Aug - Nov 2016
Team size | 4
Total Hours (D &D) | 360
Issues + Enhancements | 120
Activity | Hours | Resources
Layout and Design | 80 | 1 | 10
Wireframes, Photoshop Designs and Jpegs
Development of HTML /CMS | 200 | 4 | 6.25
Create the site in wordpress CMS
Managing the articles as posts
Created the categories as per the requirements
Revisions on the finalisation on the categories and its placements
Added magazines from 2014 to the system as articles
Creation of Magazines to flippable format | 80 | 1 | 10
Created magazines from 2014 to flippable format
Issues + Enhancements | 120 | 1 | 15
Total Effort in days | 60 | Total Del Days | 41.25
Client | Origlio
Start & End Date | Dec - Ongoing
Team size | 4
Total Hourse (D&D) | 80
Issues + Enhancements | 380
Activity | Hours | Resources
Layout and Design | 40 | 1 | 5
Wireframes, Photoshop Designs and Jpegs
Development of CMS | 90 | 2 | 5.625
Updated the beer sections with new counties
Added employee spotlight carousel
Added fintech section
Added New pages
Added shelf taker and sell sheets option
Video pages added to CMS
Software to create Shelftalkers | 210 | 2 | 13.125
Origlio- Ongoing Tasks |  |  | 0
Beers page needs filter option - 75 hours | 75 | 1 | 9.375
New pages to be added | 45 | 1 | 5.625
Menu needs rearrangement + Drop down added to the ment | 60 | 1 | 7.5
Beer Detail page will have Shelf talker button and Sell sheet button to upload | 40 | 1 | 5
Heady time section in the home page to be rebuilt | 15 | 1 | 1.875
Headytimes needs to have flippable version | 425 | 1 | 53.125
Creation of Shelf talkers and Sell sheets - ( 300 are remaining ) - 125 hours | 125 | 1 | 15.625
Upload of Sell sheets and Shelf talkers | 250 | 1 | 31.25
Issues + Enhancements | 120 | 1 | 15
Total Effort in days | 171.875 | Total Del Days | 153.125
Issues & Enhancements | Ticket | Hours
2017-07-01
Employee Spotlight Carousel: Adding new set of images and text | 73 | 2
Website hacked? Security issues shown in the GA pages | 74 | 1
Employee Spotlights on Origlio.com : Edit function is not working | 75 | 3
Employee Spotlights on Origlio.com:Adding new set of images and text | 76 | 1
Total Effort In Days |  | 0.875 | 7
2017-08-01 | Ticket #
Events page. (move from Origlio to Draught Lines) | 77 | 15
Tab Name Change. We changed the name of the tab "Behind the Suds" to "Pre Game" and now none of the posts are showing up. | 78 | 5
Add share buttons on articles/products. Add share buttons on articles/products. Can you please add buttons on Origlio.com to share the articles and products on social media? Based on screenshot provided | 79 | 23
Employee Spotlights on Origlio.com. Are you able to make the employee spotlight carousel on the homepage automatically rotate? | 80 | 7
Add new issue of Draught Lines to website. Can you please add the newest edition (attached) to the "current issue" tab and move the old one to past issues? | 81 | 12
Fintech Addition to the website. Setup fintech as listed in the document | 82 | 135
commas after counties. comma/spacing issue in "counties sold in" on product pages? There needs to be a space before Philadelphia and Northampton. | 83 | 7
Total Effort In Days |  | 25.5 | 204
2017-09-01 | Ticket #
Fintech Addition to the website. Setup fintech as listed in the document | 82 | 15
Rethinking Retail on Origlio Website. add a tab under "Retailer Resources" that reads "Rethinking Retail" On this tab we're hoping to include text and pictures as well as a media player for a short podcast we've produced. Is this possible to set up? | 87 | 42
google analytics on Origlio.com. Resolve question regarding some google analytics results on Origlio.com | 88 | 5
Search function on Origlio.com | 89 | 19
Website Popup. When you're not logged in to Origlio.com - there is a scroll bar that appears under the Are You 21 or Older and it causes the box to be off centered when looking at it | 90,94 | 8
Website Popup. Also, when not logged in to Origlio.com, the pop up box for Fintech shows up oddly (see left column) | 91,93 | 6
Brewery Link on Beverage Pages. There seems to be a problem with the links from individual beverage pages to the brewery page. Normally, when you click the brewery name on the page (circled in red), it takes you to a page with all of the other products from the brewery, however the pages are now coming up blank and I'm not sure how to fix it. | 92 | 16
Origlio.com. The magazines on the home page have not been made “flippable”. Is it still possible (via a link) to show flippable versions? | 95 | 10
Add share buttons on articles/products | 96 | 15
Total Effort In Days |  | 17 | 136
Non Ticketed Requests
2017-07-01
Website Changes including new page creations .As per the website meeting notes 7/26/17 |  | 25
Shelf takers PDF creation. Creating Shelf Takers by the software |  | 50
Sell Sheets Creation |  | 30
Total Effort In Days |  | 13.125 | 105
2017-08-01
Website Changes including new page creations .As per the website meeting notes 7/26/17 |  | 75
Shelf takers PDF creation. Creating Shelf Takers by the software |  | 325
Sell Sheets Creation |  | 230
Total Effort In Days |  | 78.75 | 630
2017-09-01
Website Changes including new page creations .As per the website meeting notes 7/26/17 |  | 95
Shelf takers PDF creation. Creating Shelf Takers by the software |  | 168
Sell Sheets Creation |  | 125
Total Effort In Days |  | 48.5 | 388
Consolidated Effort for 2017 (in Days) |  | 140.375