## Summary
Resource | No | man hours | Man days | Total
PM | 1 | 53.4 | 6.675 | 6.675
BA | 1 | 24 | 3 | 3
UI/UX | 1 | 40 | 5 | 5
IOS | 1 | 288 | 36 | 36
Andoid | 1 | 206 | 25.75 | 25.75
QA | 2 | 74.1 | 9.2625 | 18.525
|  | Total |  | 94.95
Delivery days | 50.2625
Total effort | 94.95

## AndroidDev
OSCAR |  | 2017-11-23
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 4 | 0.5
Registration page
Design,Development and api integration | 8 | 1
Login Page (Guest,CVA,Restaurants and Malls )
Design,Development and api integration | 12 | 1.5
Guest Dashboard
Design,Development and api integration | 8 | 1
Guest Info Screen
Design,Development and api integration | 4 | 0.5
Guest Car list page
Design,Development and api integration | 4 | 0.5
Guest add new car
Design,Development and api integration | 4 | 0.5
Guest car edit and delete
Design,Development and api integration | 6 | 0.75
Guest Quick request
Design,Development and api integration | 2 | 0.25
Generate Barcode
Design , Development and QR code Generator integration | 8 | 1
Car Selection page
Design,Development and api integration | 4 | 0.5
Push notification
integration | 16 | 2
Qr code page
Design and Development | 4 | 0.5
Retrieve car
Design,Development and api integration | 4 | 0.5
Rate us
Design,Development and api integration | 8 | 1
Feedback
Design,Development and api integration | 6 | 0.75
Contact us
Design,Development and api integration | 2 | 0.25
Logout
Design,Development and api integration | 2 | 0.25
CVA Dashboard
Design and Development | 8 | 1
CVA Check-in
Design,Development and api integration | 2 | 0.25
Barcode Reader page
Design,Development , api integration and QR code reader integration | 8 | 1
Vehicle detail page
Design,Development and api integration | 8 | 1
Parking detail page
Design,Development and api integration | 4 | 0.5
Take image option
Design and Development | 4 | 0.5
Photo gallery
Design, Development and Api integration | 8 | 1
Scan Parking QR Code page
Design,Development , api integration and QR code reader integration | 6 | 0.75
CVA check-out(Show car detail and validation)
Design,Development and api integration | 8 | 1
Fees Detail enter page
Design,Development and api integration | 4 | 0.5
CVA logout
Design,Development and api integration | 2 | 0.25
Exit App
Development |  | 0
Restaurant Dashboard
Design and Development | 4 | 0.5
Validation
Design,Development , api integration and QR code reader integration | 8 | 1
Logout
Design,Development and api integration | 2 | 0.25
Developer side testing and bug fixing | 16 | 2
total effort | 206 | 25.75
25.75
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles only.

## iOS
OSCAR | 2017-11-23
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 4 | 0.5
Registration page
Design,Development and api integration | 8 | 1
Login Page (Guest,CVA,Restaurants and Malls )
Design,Development and api integration | 16 | 2
Guest Dashboard
Design,Development and api integration | 8 | 1
Guest Info Screen
Design,Development and api integration | 4 | 0.5
Guest Car list page
Design,Development and api integration | 4 | 0.5
Guest add new car
Design,Development and api integration | 8 | 1
Guest car edit and delete
Design,Development and api integration | 8 | 1
Guest Quick request
Design,Development and api integration | 4 | 0.5
Generate Barcode
Design , Development and QR code Generator integration | 16 | 2
Car Selection page
Design,Development and api integration | 4 | 0.5
Push notification
integration | 24 | 3
Qr code page
Design and Development | 8 | 1
Retrieve car
Design,Development and api integration | 4 | 0.5
Rate us
Design,Development and api integration | 8 | 1
Feedback
Design,Development and api integration | 6 | 0.75
Contact us
Design,Development and api integration | 2 | 0.25
Logout
Design,Development and api integration | 2 | 0.25
CVA Dashboard
Design and Development | 8 | 1
CVA Check-in
Design,Development and api integration | 4 | 0.5
Barcode Reader page
Design,Development , api integration and QR code reader integration | 16 | 2
Vehicle detail page
Design,Development and api integration | 8 | 1
Parking detail page
Design,Development and api integration | 4 | 0.5
Take image option
Design and Development | 4 | 0.5
Photo gallery
Design, Development and Api integration | 8 | 1
Scan Parking QR Code page
Design,Development , api integration and QR code reader integration | 16 | 2
CVA check-out(Show car detail and validation)
Design,Development and api integration | 16 | 2
Fees Detail enter page
Design,Development and api integration | 4 | 0.5
CVA logout
Design,Development and api integration | 4 | 0.5
Exit App
Development | 2 | 0.25
Restaurant Dashboard |  | 0
Design and Development | 4 | 0.5
Validation
Design,Development , api integration and QR code reader integration | 16 | 2
Logout
Design,Development and api integration | 4 | 0.5
Developer side testing and bug fixing | 24 | 3
total effort | 288 | 36
36

## Design
OSCAR |  | 2017-11-23
Module | Hours | Man Days
Splash Screen | 1
Registration page | 2
Login Page (Guest,CVA,Restaurants and Malls ) | 2
Guest Dashboard | 3
Guest Info Screen | 2
Guest Car list page | 2
Guest add new car | 2
Guest car edit and delete | 1
Guest Quick request | 1
Generate Barcode | 1
Car Selection page | 2
Qr code page | 2
Retrieve car | 1
Rate us | 1
Feedback | 1
Contact us | 1
CVA Dashboard | 2
CVA Check-in | 1
Barcode Reader page | 1
Vehicle detail page | 2
Parking detail page | 1
Take image option | 1
Photo gallery | 2
Scan Parking QR Code page | 1
Fees Detail enter page | 2
Restaurant Dashboard | 2
total effort | 40 | 5