## POM Holdings
| POM Holdings |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business analysis | 24 | 3 | Sr Developer | 1 | 38 | 38 | 73.75 | 76 | 75.25 | 76
| Project Management | 60.2 | 7.525 | Jr Developer | 1 | 38 | 38
| Design and Prototype | 40 | 5 | PM | 1 | 7.525 | 7.525
| Development |  |  | BA | 1 | 3 | 3
| Application basic setup | 8 | 1 | QA | 2 | 11.7875 | 23.575
| Organization Brief (Web Content Management Based) |  |  | Total |  |  | 115.1
1 | Dynamic Page Updates( Insurance, Promotions, Birthdays, Health Tips) | 12 | 1.5
2 | Common Static Pages (Vision, mission, values etc) | 12 | 1.5
3 | Personal Update Pages (Anniversary, birth, death etc) | 6 | 0.75 | Total Delivery days | 57.7875
4 | Frequently Updated pages (Anouncements, News, CXO's Messages, Awards, Events) | 8 | 1 | Total Effort | 115.1 | (+1 Day deployment)
5 | Manage Employee profiles | 12 | 1.5
6 | Manage Video & Photo Gallery (upload, tag & front end display) | 12 | 1.5
7 | Online Chat Facility | 12 | 1.5
8 | Corporate document repository (Trade License, Establisment card, Lease agreements etc) | 12 | 1.5
9 | Meta data, Tagging & Categories for video, photos, documents | 12 | 1.5
Brand Asset Management
| Uplaod assets | 6 | 0.75
| Tag, Categorize assets | 12 | 1.5
| Approval workflow for assets | 24 | 3
| Access control for assets | 8 | 1
Policy Managent
| Policy management approval workflow | 24 | 3
| Create policy revisions | 4 | 0.5
| Automatic notifications for policy expiration and policy renewal or amendments | 8 | 1
| Policy access controls and entitlements | 8 | 1
| Custom metadata for policies | 6 | 0.75
| Dashboard for policies (waiting for approval pending, expired etc) | 16 | 2
| Employee acknowledgment of policies | 6 | 0.75
| Access control for policies | 12 | 1.5
| Advanced search | 16 | 2
Survey Management (Web Based)
| Categorize survey (Dept, Business Unit, Svc Type) | 8 | 1
| Survey definition | 8 | 1
| Standard rating system for surveys | 8 | 1
| Survey workflow | 24 | 3
| Survey based reports with reporting dashboard | 24 | 3
| Export functionality (PDF, XLS, DOC) | 12 | 1.5
| Create survey questions | 8 | 1
| Create Dynamic controls for survey |  | 0
| Text, Date, DropDown , Options, Radio buttons, Check boxes | 40 | 5
| Survey Scheduling | 6 | 0.75
| Generate Survey | 6 | 0.75
| Upload documents with document management features | 8 | 1
| Email surveys | 6 | 0.75
| Survey Master Data | 16 | 2
| Site code, building code, Floor code |  | 0
| Room code, equipment standard, Equipment code |  | 0
| Project code, Vendor code, status, Dept, Svc Type |  | 0
Web Content Management
| Upload content from various media | 4 | 0.5
| Approval workflow for content to be published | 24 | 3
| Versioning of content | 6 | 0.75
System Features
| Advanced document search (by name, subject, category, meta tags, date etc) | 16 | 2
| Authentication & authorization | 8 | 1
| Auditing & logging | 8 | 1
| Exception handling | 6 | 0.75
| Manage files and folders | 8 | 1
| Generate thumbnail for videos and images | 4 | 0.5
| User management (create, update, delete) | 8 | 1
| Add New user attributes | 8 | 1
| Create User roles (CxO's, Gatepass, Survey & Asset managers, admins etc) | 6 | 0.75
| Entitlements | 6 | 0.75
| manage meeting locations | 6 | 0.75
| manage Departments | 6 | 0.75
| manage Projects | 6 | 0.75
| manage Performance Goals | 6 | 0.75
| Document and asset management framework | 24 | 3
| meta tag management | 6 | 0.75
| Survey question management | 6 | 0.75
Quality Assurance
| QA & Bug Fixing | 180.6 | 22.575
| UAT | 8 | 1
| Deployment per instance | 8 | 1
| Total Effort | 922.8 | 115.35
Assumptions
Pre defined format for print and format will be designed in HTML and printed on plain paper
SMS gateway will be procured by client
Responsive web application
Does not include payment gateway integration
Chat plugin
Emirates ID
OCR engine
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Option 1
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 4 | 4
Business analysis | 16 | 2 | Sr Developer | 1 | 27 | 27 | 53 | 54
Project Management | 43 | 5.375 | Jr Developer | 1 | 27 | 27
Design and Prototype | 32 | 4 | PM | 1 | 5.375 | 5.375
Development |  |  | BA | 1 | 2 | 2
Application basic setup | 8 | 1 | QA | 2 | 8.5625 | 17.125
Organization Brief (Web Content Management Based) |  |  | Total |  |  | 82.5
Dynamic Page Updates( Insurance, Promotions, Birthdays, Health Tips) | 12 | 1.5
Common Static Pages (Vision, mission, values etc) | 12 | 1.5
Personal Update Pages (Anniversary, birth, death etc) | 6 | 0.75 | Total Delivery days | 41.5625
Frequently Updated pages (Anouncements, News, CXO's Messages, Awards, Events) | 8 | 1 | Total Effort | 82.5 | (+1 Day deployment)
Manage Employee profiles | 12 | 1.5
Manage Video & Photo Gallery (upload, tag & front end display) | 12 | 1.5
Online Chat Facility | 12 | 1.5
Corporate document repository (Trade License, Establisment card, Lease agreements etc) | 12 | 1.5 | Web Only Estimate*
Meta data, Tagging & Categories for video, photos, documents | 12 | 1.5
Brand Asset Management
Uplaod assets | 6 | 0.75
Tag, Categorize assets | 12 | 1.5
Approval workflow for assets | 24 | 3
Access control for assets | 8 | 1
Policy Managent
Policy management approval workflow | 24 | 3
Create policy revisions | 4 | 0.5
Automatic notifications for policy expiration and policy renewal or amendments | 8 | 1
Policy access controls and entitlements | 8 | 1
Custom metadata for policies | 6 | 0.75
Dashboard for policies (waiting for approval pending, expired etc) | 16 | 2
Employee acknowledgment of policies | 6 | 0.75
Access control for policies | 12 | 1.5
Advanced search | 16 | 2
Web Content Management
Upload content from various media | 4 | 0.5
Approval workflow for content to be published | 24 | 3
Versioning of content | 6 | 0.75
System Features
Advanced document search (by name, subject, category, meta tags, date etc) | 16 | 2
Authentication & authorization | 8 | 1
Auditing & logging | 8 | 1
Exception handling | 6 | 0.75
Manage files and folders | 8 | 1
Generate thumbnail for videos and images | 4 | 0.5
User management (create, update, delete) | 8 | 1
Add New user attributes | 8 | 1
Create User roles (CxO's, Gatepass, Survey & Asset managers, admins etc) | 6 | 0.75
Entitlements | 6 | 0.75
manage meeting locations | 6 | 0.75
manage Departments | 6 | 0.75
manage Projects | 6 | 0.75
manage Performance Goals | 6 | 0.75
Document and asset management framework | 32 | 4
meta tag management | 6 | 0.75
Survey question management | 0 | 0
Quality Assurance
QA & Bug Fixing | 129 | 16.125
UAT | 8 | 1
Deployment per instance | 8 | 1
Total Effort | 666 | 83.25

## Survey
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 4 | 4
Business analysis | 8 | 1 | Sr Developer | 1 | 18 | 18 | 35.75 | 36
Project Management | 19.8 | 2.475 | Jr Developer | 1 | 18 | 18
Design and Prototype | 32 | 4 | PM | 1 | 2.475 | 2.475
Development |  |  | BA | 1 | 1 | 1
Application basic setup | 8 | 1 | QA | 2 | 4.625 | 9.25
Survey Management |  |  | Total |  | 48.1 | 52.725
Categorize survey (Dept, Business Unit, Svc Type) | 8 | 1
Survey definition | 8 | 1
Standard rating system for surveys | 8 | 1 | Total Delivery days | 27.625
Survey workflow | 32 | 4 | Total Effort | 52.725 | (+1 Day deployment)
Survey based reports with reporting dashboard | 32 | 4
Export functionality (PDF, XLS, DOC) | 12 | 1.5 |  | Days
Create survey questions | 8 | 1 | IOS APP | 12
Create Dynamic controls for survey |  | 0 | Android App | 10
Text, Date, DropDown , Options, Radio buttons, Check boxes | 40 | 5 | Summary | Total effort | Delivery Timeline
Survey Scheduling | 6 | 0.75 | Web App | 53 | 28 | Days
Generate Survey | 6 | 0.75 | IOS APP | 12 | 12 | Days
Upload documents with document management features | 8 | 1 | Android App | 10 | 10 | Days
Email surveys | 6 | 0.75
Survey Master Data | 16 | 2
Site code, building code, Floor code |  | 0
Room code, equipment standard, Equipment code |  | 0
Project code, Vendor code, status, Dept, Svc Type |  | 0
API Development | 96 | 12
Quality Assurance
QA & Bug Fixing | 66 | 8.25
UAT | 8 | 1
Deployment per instance | 8 | 1
Total Effort | 435.8 | 54.475
Assumptions
Only surveys can be taken in mobile apps
Additional features of the web app will not be available on mobile devices