## POM Holdings
| POM Holdings |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
| Business analysis | 40 | 5 | Sr Developer | 2 | 50 | 100 | 207.75 | 210 | 210 | 210
| Project Management | 168 | 21 | Jr Developer | 2 | 55 | 110
| Design and Prototype | 80 | 10 | PM | 1 | 21 | 21
| Development |  |  | BA | 1 | 5 | 5
| Application basic setup | 8 | 1 | QA | 2 | 32 | 64
| Organization Brief (Web Content Management Based) |  |  | Total |  |  | 310
1 | Dynamic Page Updates( Insurance, Promotions, Birthdays, Health Tips) | 12 | 1.5
2 | Common Static Pages (Vision, mission, values etc) | 12 | 1.5
3 | Personal Update Pages (Anniversary, birth, death etc) | 6 | 0.75 | Total Delivery days | 102 |  | 5.1
4 | Frequently Updated pages (Anouncements, News, CXO's Messages, Awards, Events) | 8 | 1 | Total Effort | 310 | (+1 Day deployment) | 15.5
5 | Manage Employee profiles | 12 | 1.5 |  | 310
6 | Manage Video & Photo Gallery (upload, tag & front end display) | 12 | 1.5
7 | Online Chat Facility | 12 | 1.5
8 | Corporate document repository (Trade License, Establisment card, Lease agreements etc) | 12 | 1.5
9 | Meta data, Tagging & Categories for video, photos, documents | 12 | 1.5
Brand Asset Management
| Uplaod assets | 6 | 0.75
| Tag, Categorize assets | 12 | 1.5
| Approval workflow for assets | 24 | 3
| Access control for assets | 8 | 1
Policy Managent
| Policy management approval workflow | 24 | 3
| Create policy revisions | 4 | 0.5
| Automatic notifications for policy expiration and policy renewal or amendments | 8 | 1
| Policy access controls and entitlements | 8 | 1
| Custom metadata for policies | 6 | 0.75
| Dashboard for policies (waiting for approval pending, expired etc) | 16 | 2
| Employee acknowledgment of policies | 6 | 0.75
| Access control for policies | 12 | 1.5
| Advanced search | 16 | 2
Survey Management (Web Based)
| Categorize survey (Dept, Business Unit, Svc Type) | 8 | 1
| Survey definition | 8 | 1
| Standard rating system for surveys | 8 | 1
| Survey workflow | 24 | 3
| Survey based reports with reporting dashboard | 24 | 3
| Export functionality (PDF, XLS, DOC) | 12 | 1.5
| Create survey questions | 8 | 1
| Create Dynamic controls for survey |  | 0
| Text, Date, DropDown , Options, Radio buttons, Check boxes | 40 | 5
| Survey Scheduling | 6 | 0.75
| Generate Survey | 6 | 0.75
| Upload documents with document management features | 8 | 1
| Email surveys | 6 | 0.75
| Survey Master Data | 16 | 2
| Site code, building code, Floor code |  | 0
| Room code, equipment standard, Equipment code |  | 0
| Project code, Vendor code, status, Dept, Svc Type |  | 0
Employee Affairs Center
| Employee recruitment workflow |  | 0
| Requirement Request | 6 | 0.75
| Phone screening | 6 | 0.75
| Personal data collection | 8 | 1
| Interview results | 6 | 0.75
| Onboarding | 12 | 1.5
| Offboarding | 8 | 1
| Performance Management |  | 0
| Goal Management (create and manage goals based on employee tiers) | 6 | 0.75
| Goal Assessments | 6 | 0.75
| Performance feedbacks | 6 | 0.75
| Self service forms with workflow | 16 | 2
| Expensing | 4 | 0.5
| Passports, Emirates ID, Visa Renewal | 4 | 0.5
| Travel reembursements | 4 | 0.5
| Leave requests | 4 | 0.5
| Apply for Insurance and insurance claims | 4 | 0.5
| Attendance register | 4 | 0.5
| Claims, Feedback, complaints | 8 | 1
| Employee profile self managemnt | 6 | 0.75
| passport, Photo, personal details, vehicle registration, insurance cards etc | 12 | 1.5
Meeting Management
| Meeting Organizer |  | 0
| Subject, Agenda, preliminary attachments | 8 | 1
| Select Attendees (LDAP, Active directory, external users) | 8 | 1
| Meeting Workspace (dashboard with meeting details) | 8 | 1
| Schedule Meeting (send emails, outlook invites) | 6 | 0.75
| Calenders |  | 0
| Maintain room calenders | 8 | 1
| Inviteee calenders | 8 | 1
| Downloadable meeting details in predefined templates | 8 | 1
| Updateable meeting tags which link the meeting to other entities (Departments, projects, other meetings etc) | 8 | 1
Gate Pass System
| Integrate Emirates ID reader | 16 | 2
| External User Access | 6 | 0.75
| User Invitation email | 6 | 0.75
| Approval Link and verify identity | 6 | 0.75
| Upload Documents | 4 | 0.5
| Assign Entitlements and system access | 6 | 0.75
| Request access for forms, documents with approval workflow | 6 | 0.75
| Track requests with access logs | 4 | 0.5
| Notification of request status to requesters | 4 | 0.5
Web Content Management
| Upload content from various media | 4 | 0.5
| Approval workflow for content to be published | 24 | 3
| Versioning of content | 6 | 0.75
| Validation of content asset, dimensioning & formats | 6 | 0.75
Enterprise Business Intelligence
| Connect to variety of data sources, whether its internal or external systems | 8 | 1
| Simplify data preparation and modeling. | 6 | 0.75
| Drive ad-hoc or on demand analysis beside configured key performance indicators. Produce eye-catching reports and KPIs, | 32 | 4
| Available to view through web and across mobile devices. | 6 | 0.75
| Personalized dashboards with a unique, 360-degree view of user line of business(s). | 24 | 3
| Maintain security and access control. | 4 | 0.5
Health & Safety Management
| Support the creation and update of the audit checklist, maintain versioning and approval records. | 18 | 2.25
| Calculation of the checklist score according to weight defined. | 16 | 2
| Notify designated stakeholders of observation action reminders, deadlines with escalation matrix. | 16 | 2
| Integrate and feeds Training Management App (See 2.1.9) for certification and training requests. | 20 | 2.5
| Report and track incidents, injuries, hazardous conditions and observation with workflow for action appropriate to resolve. | 32 | 4
Contract Life Cycle management
| Classification, writing and template management. | 16 | 2
| Notify/Alert of actionable items (renewal, performance, payment, etc.) | 12 | 1.5
| Approval, Authorization and Negotiation | 18 | 2.25
| Baseline, Commitment and Communication management | 24 | 3
| Contract visibility and awareness | 8 | 1
| Contract document management | 6 | 0.75
| Contract compliance, governance including collaboration of feedback management (See 2.1.13) | 24 | 3
Training Management
| Support of e-training, in-room class, external training models. | 14 | 1.75
| Allowing employees to signup, register interest for existing and new courses, which their participation is based on approval workflow. | 18 | 2.25
| Send automated alerts notifying employees when new or updated information is available for review. | 6 | 0.75
| Automatically notify employee (new or existing) about required training and policies for them sign once added to active directory users and employee list | 8 | 1
| Set deadline for required timestamp acknowledgement, while still allowing employees to learn at their own pace. | 12 | 1.5
| Test employees with optional quizzes to ensure they have read and understood policies and processes. | 24 | 3
| Support the concept of competition and encouragement of learning by assigning points to training completed. (Gamification) | 24 | 3
| Control access to documents with configurable permissions. | 6 | 0.75
| Maintain approval workflow for training through needs analysis, materials and content, updates to assure that employees access to latest approved version. | 16 | 2
| Track employees progress on real-time dashboards and compliance report. | 8 | 1
| Alert employees about training expiring or overdue with support of escalation. | 6 | 0.75
| Produce real-time, ad-hoc reports by employees, unit and any other meta data. | 24 | 3
Project Management
| Centralize Project & Portfolio Management | 18 | 2.25
| Simplify the use of centralized resource Management | 24 | 3
| Organize project documents and resources in one location, where the stakeholders can access summaries, documents, tasks, newsfeeds and calendars. | 16 | 2
| Create workflows to standardize project progression or rejection and improve governance and control. | 44 | 5.5
| Enable security & access control features to share information and collaborate with trusted business partners on projects and everyday work. | 16 | 2
| Improve visibility with collaborative tools to seamlessly flow calendar, presence, and capacity information across your organization. | 16 | 2
| Easily manage and collaborate on work as a team without the structure of a project, but have visibility into the work for planning and reporting purposes. | 32 | 4
Document management System
| Organize and share documents inside/outside of your organization. | 12 | 1.5
| Metadata sorting, filtering and application of custom metadata to documents | 12 | 1.5
| Advance security features focusing on information rights management. | 12 | 1.5
| Rate and critique documents | 14 | 1.75
| Automate change request, review and approval processes and audit all document events, versions. | 24 | 3
| Work directly from popular document authoring tools | 40 | 5
| Find documents with simple or advanced search subject to permission. | 14 | 1.75
| Enable the modification of one document by multiple parties. | 12 | 1.5
Client Item Requisition
| Load items load it into a list, with items details includes category, photos, and other meta-data tags. | 12 | 1.5
| Display the list to predefined external user and enable the use of filtering. | 10 | 1.25
| Enable Client to browse and select an item and declare a desired action by Agent to be carried out of action preconfigured list associated with free text box. | 10 | 1.25
| Allow agent to declare status of a request from pre-configured list of status | 14 | 1.75
| Display summery of items count per category, last actions requested, last action requested and completed. | 8 | 1
System Features
| Advanced document search (by name, subject, category, meta tags, date etc) | 16 | 2
| Authentication & authorization | 8 | 1
| Auditing & logging | 8 | 1
| Exception handling | 6 | 0.75
| Manage files and folders | 8 | 1
| Generate thumbnail for videos and images | 4 | 0.5
| User management (create, update, delete) | 8 | 1
| Add New user attributes | 8 | 1
| Create User roles (CxO's, Gatepass, Survey & Asset managers, admins etc) | 6 | 0.75
| Entitlements | 6 | 0.75
| manage meeting locations | 6 | 0.75
| manage Departments | 6 | 0.75
| manage Projects | 6 | 0.75
| manage Performance Goals | 6 | 0.75
| Document and asset management framework | 24 | 3
| meta tag management | 6 | 0.75
| Secure communication | 6 | 0.75
| Survey question management | 6 | 0.75
Quality Assurance
| QA & Bug Fixing | 504 | 63
| UAT | 8 | 1
| Deployment per instance | 8 | 1
| Total Effort | 2488 | 311
Assumptions
Pre defined format for print and format will be designed in HTML and printed on plain paper
SMS gateway will be procured by client
Responsive web application
Does not include payment gateway integration
Chat plugin
Emirates ID
OCR engine
SSL
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Option 1
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 4 | 4
Business analysis | 16 | 2 | Sr Developer | 1 | 27 | 27 | 53 | 54
Project Management | 43 | 5.375 | Jr Developer | 1 | 27 | 27
Design and Prototype | 32 | 4 | PM | 1 | 5.375 | 5.375
Development |  |  | BA | 1 | 2 | 2
Application basic setup | 8 | 1 | QA | 2 | 8.5625 | 17.125
Organization Brief (Web Content Management Based) |  |  | Total |  |  | 82.5
Dynamic Page Updates( Insurance, Promotions, Birthdays, Health Tips) | 12 | 1.5
Common Static Pages (Vision, mission, values etc) | 12 | 1.5
Personal Update Pages (Anniversary, birth, death etc) | 6 | 0.75 | Total Delivery days | 41.5625
Frequently Updated pages (Anouncements, News, CXO's Messages, Awards, Events) | 8 | 1 | Total Effort | 82.5 | (+1 Day deployment)
Manage Employee profiles | 12 | 1.5
Manage Video & Photo Gallery (upload, tag & front end display) | 12 | 1.5
Online Chat Facility | 12 | 1.5
Corporate document repository (Trade License, Establisment card, Lease agreements etc) | 12 | 1.5 | Web Only Estimate*
Meta data, Tagging & Categories for video, photos, documents | 12 | 1.5
Brand Asset Management
Uplaod assets | 6 | 0.75
Tag, Categorize assets | 12 | 1.5
Approval workflow for assets | 24 | 3
Access control for assets | 8 | 1
Policy Managent
Policy management approval workflow | 24 | 3
Create policy revisions | 4 | 0.5
Automatic notifications for policy expiration and policy renewal or amendments | 8 | 1
Policy access controls and entitlements | 8 | 1
Custom metadata for policies | 6 | 0.75
Dashboard for policies (waiting for approval pending, expired etc) | 16 | 2
Employee acknowledgment of policies | 6 | 0.75
Access control for policies | 12 | 1.5
Advanced search | 16 | 2
Web Content Management
Upload content from various media | 4 | 0.5
Approval workflow for content to be published | 24 | 3
Versioning of content | 6 | 0.75
System Features
Advanced document search (by name, subject, category, meta tags, date etc) | 16 | 2
Authentication & authorization | 8 | 1
Auditing & logging | 8 | 1
Exception handling | 6 | 0.75
Manage files and folders | 8 | 1
Generate thumbnail for videos and images | 4 | 0.5
User management (create, update, delete) | 8 | 1
Add New user attributes | 8 | 1
Create User roles (CxO's, Gatepass, Survey & Asset managers, admins etc) | 6 | 0.75
Entitlements | 6 | 0.75
manage meeting locations | 6 | 0.75
manage Departments | 6 | 0.75
manage Projects | 6 | 0.75
manage Performance Goals | 6 | 0.75
Document and asset management framework | 32 | 4
meta tag management | 6 | 0.75
Survey question management | 0 | 0
Quality Assurance
QA & Bug Fixing | 129 | 16.125
UAT | 8 | 1
Deployment per instance | 8 | 1
Total Effort | 666 | 83.25

## Survey
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 4 | 4
Business analysis | 8 | 1 | Sr Developer | 1 | 18 | 18 | 35.75 | 36
Project Management | 19.8 | 2.475 | Jr Developer | 1 | 18 | 18
Design and Prototype | 32 | 4 | PM | 1 | 2.475 | 2.475
Development |  |  | BA | 1 | 1 | 1
Application basic setup | 8 | 1 | QA | 2 | 4.625 | 9.25
Survey Management |  |  | Total |  | 48.1 | 52.725
Categorize survey (Dept, Business Unit, Svc Type) | 8 | 1
Survey definition | 8 | 1
Standard rating system for surveys | 8 | 1 | Total Delivery days | 27.625
Survey workflow | 32 | 4 | Total Effort | 52.725 | (+1 Day deployment)
Survey based reports with reporting dashboard | 32 | 4
Export functionality (PDF, XLS, DOC) | 12 | 1.5 |  | Days
Create survey questions | 8 | 1 | IOS APP | 12
Create Dynamic controls for survey |  | 0 | Android App | 10
Text, Date, DropDown , Options, Radio buttons, Check boxes | 40 | 5 | Summary | Total effort | Delivery Timeline
Survey Scheduling | 6 | 0.75 | Web App | 53 | 28 | Days
Generate Survey | 6 | 0.75 | IOS APP | 12 | 12 | Days
Upload documents with document management features | 8 | 1 | Android App | 10 | 10 | Days
Email surveys | 6 | 0.75
Survey Master Data | 16 | 2
Site code, building code, Floor code |  | 0
Room code, equipment standard, Equipment code |  | 0
Project code, Vendor code, status, Dept, Svc Type |  | 0
API Development | 96 | 12
Quality Assurance
QA & Bug Fixing | 66 | 8.25
UAT | 8 | 1
Deployment per instance | 8 | 1
Total Effort | 435.8 | 54.475
Assumptions
Only surveys can be taken in mobile apps
Additional features of the web app will not be available on mobile devices