## workflow-based
| Warehouse Application |  | 21/6/2020
Sunday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 15 | 15
1 | Business analysis | 64 | 8 | Sr Developer | 1.5 | 61.3333 | 92 | 135.75 | 209.7375 | 184 | 183.5
2 | Project Management | 205.9 | 25.7375 | Jr Developer | 1.5 | 61.3333 | 92
3 | SRS,FS,User Manual | 80 | 10 | PM | 1 | 25.7375 | 25.7375
4 | Design and Prototype (Web + Mobile) | 120 | 15 | BA | 1 | 8 | 8
| Development |  |  | Tech writer | 1 | 10 | 10
5 | Application basic setup | 8 | 1 | QA | 2 | 37.4375 | 74.875
| System(Warehouse Planning & Workforce Management) |  |  | Total |  | 218.8417 | 317.6125
| Define warehouses locations based on hierarchy (Country, Site, warehouse, chamber, area, etc.) | 20 | 2.5 |  | Days | Months
| Define items along with their attributes rules and put away zones, locations etc | 40 | 5 | Effort | 317.6125 | 15.8806
| Define material categories & sub-categories & specification of attribute rules per category, sub-category or material | 40 | 5 | Delivery Time | 121.7708 | 6.0885
| Define of suppliers, client, carriers, etc. | 12 | 1.5
| Define of device groups | 12 | 1.5
| Assignment of locations, deliveries, issue requests, task request types, categories and sub-categories to mobile device groups. | 40 | 5
| Assignment of users to mobile device groups | 12 | 1.5
| Configuration of users, groups, roles and permissions | 16 | 2
| Group and assign the teams for different tasks like Client’s Request, project request and reconciliation etc. | 24 | 3
| Senior WH Assistant | 16 | 2
| WH Assistants | 16 | 2
| Warehouse Porters | 16 | 2
| Drivers and Vehicle | 16 | 2
| Forklift Operator and Equipment | 16 | 2
| Office Assistant | 16 | 2
| Assignment, recording of time and full lifecycle management of tasks. | 40 | 5
| Filling out of daily checklists of Warehouse operations. | 22 | 2.75
| Maintenance of daily checklist of Forklift. | 22 | 2.75
| Maintenance of daily checklist of Vehicle. | 22 | 2.75
| Upload of all third party contractors’ documents and job completion reports. | 16 | 2
0
| Warehouse Inbound Process |  | 0
| Recording of Inbound Requests from clients. | 22 | 2.75
| Take HD Photos of each item and also allow editing them. | 12 | 1.5
| Barcode labelling for all items. | 32 | 4
| Creation of Delivery Notes against inbound orders and check-in through the system. | 20 | 2.5
| Allow the reception of incoming items against delivery notes or inbound requests directly through any mobile, desktop or handheld device | 14 | 1.75
| Apply proper validations and barcode and receive materials against pre-defined delivery orders or purchase orders | 32 | 4
| Capture vital tracking of information | 16 | 2
| Put away of Items based on a predefined strategy. | 32 | 4
| Configuration of multiple put away strategies per Item. | 40 | 5
| Reception of items based on an Inbound Request. | 16 | 2
| Define items storage allocation rule (As per client inventory level). | 32 | 4
| Support Blind Receiving process. | 12 | 1.5
| Approval of any inbound shipment and of attached documentation. | 24 | 3
0
| Internal Warehouse Workflow |  | 0
| Edit and entering of data corrections as per physical check result. | 24 | 3
| Create, modify and track items by item unique code and include basic information: | 32 | 4
| Upload and edit HD photos (main product photo and damage photos) and photos to make 3D/360 preview. | 16 | 2
| Allow definition of dynamic attributes. | 40 | 5
| Counting of the occupied space on rack in CBM (Cubic Meters). | 12 | 1.5
| Conduct Cycle Count on the spot. | 20 | 2.5
| Perform a full physical count through hand held device for an area, zone or store using 2 or more separate teams. | 48 | 6
| Compare the results of physical counts from 2 teams and identify any discrepancies | 20 | 2.5
| Conducting full physical inventory. | 24 | 3
| Allow the in and out tracking of loaned items. | 24 | 3
| Allow the picking, reserving and shipping of items. | 40 | 5
| Allow the real-time inventory visibility. | 40 | 5
| Provide storage location visibility down to the Bin, Pallet, and carton | 48 | 6
| Utilization of Case ID, Pallet ID, and Rack ID to track all products | 40 | 5
| Printing of barcode labels of the items. | 12 | 1.5
| Relocation of items within the same warehouse or from other Warehouse. | 20 | 2.5
| Track and monitor overall data entry and operation processes status in system | 12 | 1.5
| Data reconciliation and correction. | 32 | 4
Warehouse Outbound Workflow
| Execute the picking tasks created against Outbound Requests,picking tasks represent the items to be issued, required quantities, lots and storage location. | 40 | 5
| Creation of Outbound Requests. | 14 | 1.75
| Load items based on Outbound requests. | 20 | 2.5
| Facilitate that picking items from racks for outbound requests | 14 | 1.75
| Approve any outbound shipment and attached documentation | 14 | 1.75
| Facilitate the PPE and packing material request and consumption. | 20 | 2.5
| Enable recording of complete Travel Log of vehicles. | 24 | 3
| Signature and delivery details to be uploaded into the system associated with the correct delivery and kept in the transaction records of the item. | 20 | 2.5
| Manage returns to warehouse and to clients (to identify the barcode label if it is removed at client’s location) | 16 | 2
0
| authentication based on user and password authentication. | 8 | 1
| Login password immediately after the first successful login. Moreover, the initial should never be reused. | 12 | 1.5
| Role-based Access Control (RBAC) authorization mechanism. | 16 | 2
| backup and recovery, data management, data retention policies |  | 0
Quality Assurance
| QA & Bug Fixing | 511 | 63.875
| UAT | 80 | 10
| Deployment per instance | 8 | 1
| Total Effort | 2536.9 | 317.1125
Assumptions
Every functionalities described in the document require detailed system study
The work-flows, description of the keywords in the requirement need to be studied with the help of an expert in the WMS field
The effort is a high-level one based on assumption and it needs to be estimated based on the detailed system study
Only english language is considered

## mobile
| WMS |  |  |  | 21/6/2020
Sunday
| Module | Android |  | iOS |  |  | No | Man Days | Total Effort
|  | Hours | Man Days | Hours | Man Days | Designer | 1 | 44 | 44
| Development |  |  |  |  | Jr Developer | 1 | 44 | 44 | 88.5 | 88
| Splash Screen | 8 | 1 | 8 | 1 | QA | 2 | 17.8 | 35.6
| Porter |  |  |  |  | Total |  |  | 123.6
| Receive notification on new request(once warehouse supervisor assigns team for operation) | 10 | 1.25 | 10 | 1.25
WIP: 1.1 | Pack and load to truck | 16 | 2 | 16 | 2
WIP: 1.2 | Unload and keep in Inventory | 8 | 1 | 8 | 1 | Effort | 123.6 | + 1 Day (Deployment)
WIP: 1.3 | Pack item | 8 | 1 | 8 | 1 | Delivery Time | 61.8 | + 1 Day (Deployment)
WIP: 1.4 | Locate item | 8 | 1 | 8 | 1
IWW:1.1 | Retrieve and put back to Location. | 8 | 1 | 8 | 1 | API Developer | 1 | 39.825 | 39.825
IWW:1.2 | Keep all Disposal item in designated area and load on to the truck. | 8 | 1 | 8 | 1
IWW:1.3 | Keep / transfer all items in designated Warehouse. | 8 | 1 | 8 | 1 | Total Delivery Time / Platform | 81.7125
WOP:1.2 | Safe loading in Warehouse and unloading in Client Location. | 8 | 1 | 8 | 1
| Deliver the goods and receive signature | 12 | 1.5 | 12 | 1.5
| Reaching the correct location and being accepted by the right person | 12 | 1.5 | 12 | 1.5
| Login/logout | 12 | 1.5 | 12 | 1.5
| Receive notification on new request | 8 | 1 | 8 | 1
| Dashboard | 12 | 1.5 | 12 | 1.5
Warehouse Supervisor
| Receive new Inbound client requests | 8 | 1 | 8 | 1
WIP: 1.1 | coordinate with client representative | 8 | 1 | 8 | 1
WIP: 1.1,IWW1.1,1.3,WOP1.1 | Assign operation team | 8 | 1 | 8 | 1
| Dashboard | 12 | 1.5 | 12 | 1.5
| Login/logout | 8 | 1 | 8 | 1
Warehouse assistant/Senior Warehouse Assistant
| Receive new requests(once warehouse supervisor assigns team for operation) | 12 | 1.5 | 12 | 1.5
WIP: 1.2 | Unload and assign area for inventory | 8 | 1 | 8 | 1
WIP: 1.2 | check and receive | 12 | 1.5 | 12 | 1.5
WIP: 1.3 | Inventory each item (quantity, weight, dimensions, Condition and brand name (if any)) | 12 | 1.5 | 12 | 1.5
WIP: 1.3 | Photograph and photoedit | 12 | 1.5 | 12 | 1.5
WIP: 1.3 | Barcode label Print & Upload to system | 12 | 1.5 | 12 | 1.5
WIP: 1.4 | Recheck Inventory | 12 | 1.5 | 12 | 1.5
WIP: 1.4 | Locate item on system assigned location | 12 | 1.5 | 12 | 1.5
IWW:1.1 | Checks physically items quantity. Package Details.Item Condition and designated Location comparing with inventory data sheet. | 12 | 1.5 | 12 | 1.5
IWW:1.2 | Retrieve all Disposable items from Location and keep in designated area. | 8 | 1 | 8 | 1
IWW:1.3 | Retrieve all items from Location and Transfer to assigned location. | 8 | 1 | 8 | 1
WOP:1.1 | Picking items from the Rack | 8 | 1 | 8 | 1
WOP:1.1 | Keep items ready in the dispatching area. | 8 | 1 | 8 | 1
WOP:1.2 | Safe loading.Checks items Loaded in good manner. | 8 | 1 | 8 | 1
| Login/login | 8 | 1 | 8 | 1
| Dashboard | 12 | 1.5 | 12 | 1.5
Forklift Operator
| Receive new requests(once warehouse supervisor assigns team for operation) | 12 | 1.5 | 12 | 1.5
WIP: 1.2 | Unload and keep in Inventory | 12 | 1.5 | 12 | 1.5
WIP: 1.4 | Locate item | 8 | 1 | 8 | 1
IWW:1.1 | Retrieve and put back to Location. | 8 | 1 | 8 | 1
IWW:1.2 | Keep all Disposal item in designated area and load on to the truck. | 8 | 1 | 8 | 1
IWW:1.3 | Keep / transfer all items in designated Warehouse. | 12 | 1.5 | 12 | 1.5
WOP:1.2 | Safe loading | 8 | 1 | 8 | 1
| Login/login | 8 | 1 | 8 | 1
| Dashboard | 12 | 1.5 | 12 | 1.5
Driver
| Receive new requests(once warehouse supervisor assigns team for operation) | 8 | 1 | 8 | 1
WIP: 1.1 | Ship to Warehouse | 8 | 1 | 8 | 1
IWW:1.3 | Keep / transfer all items in designated Warehouse. | 8 | 1 | 8 | 1
WOP:1.2 | Ships to Client Location | 8 | 1 | 8 | 1
| Login/login | 8 | 1 | 8 | 1
| Dashboard | 12 | 1.5 | 12 | 1.5
Inventory database Administrator
| Receive new request | 12 | 1.5 | 12 | 1.5
WIP: 1.5 | Verify drafted inventory | 8 | 1 | 8 | 1
WIP: 1.5 | Confirm inventory standards and standard quality of photos | 8 | 1 | 8 | 1
WIP: 1.5 | Assign category and post on system | 8 | 1 | 8 | 1
IWW:1.1 | Updates Item details in the system if any changes. | 12 | 1.5 | 12 | 1.5
IWW:1.2 | Segregating item with Client comment. | 8 | 1 | 8 | 1
IWW:1.2 | Prepare IDF (Item Disposal Form) | 12 | 1.5 | 12 | 1.5
IWW:1.2 | submit IDF to the client representative | 8 | 1 | 8 | 1
IWW:1.3 | Retrieves the item and location details from the system. | 8 | 1 | 8 | 1
IWW:1.3 | Transfers and updates items to assigned warehouse | 8 | 1 | 8 | 1
WOP:1.1 | Retrieves the item and location details from the system. | 8 | 1 | 8 | 1
WOP1.3 | Updates Outbound inventory in the system | 6 | 0.75 | 6 | 0.75
WOP1.3 | Approves & verifies all inbound Inventory. | 8 | 1 | 8 | 1
| Login/login | 6 | 0.75 | 6 | 0.75
| Dashboard | 8 | 1 | 8 | 1
Database Supervisor
| Receive Outbound client Requests | 12 | 1.5 | 12 | 1.5
WIP: 1.5 | Approves and verifies Inbound inventory | 8 | 1 | 8 | 1
IWW:1.1 | Generates inventory data sheets rack-wise. | 8 | 1 | 8 | 1
IWW:1.2 | Segregating item with Client comment. | 8 | 1 | 8 | 1
IWW:1.2 | Preparing IDF (Item Disposal Form) | 8 | 1 | 8 | 1
IWW:1.2 | submit IDF to the client representative | 6 | 0.75 | 6 | 0.75
IWW:1.3 | Assigning Warehouse as per Client. | 8 | 1 | 8 | 1
WOP:1.1 | Coordinates with client representative. | 8 | 1 | 8 | 1
| Login/login | 8 | 1 | 8 | 1
| Dashboard | 12 | 1.5 | 12 | 1.5
Mobile API Development
| API |  |  |  |  | 39.825
Quality Assurance
| QA & Bug Fixing | 204.8 | 25.6 | 204.8 | 25.6
| UAT | 80 | 10 | 80 | 10
| Deployment per instance | 8 | 1 | 8 | 1
| Total Effort | 1000.8 | 125.1 | 1000.8 | 125.1
Assumptions 1.The estimation is put for both tablet and phone. 2.The estimation is only for portrait mode of the app. 3.The estimated time may vary with difference in functionality and design.