## Arbitration_USE
| Mawarid Payment Module |  | 01 Sep 2016
Thursday
Sl. No. | Module | Man Hours | Man Days
| Initiation | 32 | 4 | Resource Type | Number | Hours | Price/Hour | Total
| Requirement gathering & System Study | 16 | 2 | Senior Technical Architect | 1 | 8 |  | 0
| SRS Document | 16 | 2 | Senior Business Analyst | 1 | 8 |  | 0
| Sign Off( 1 Working Day) |  |  | Project Manager | 1 | 40 |  | 0
1 | Low Level Design (Milestone 1) | 40 | 5 | UI/UX Designer | 1 | 16 |  | 0
| UI Design | 16 | 2 | Senior Developer | 1 | 40 |  | 0
| Design Sign Off (1 Working Day) |  |  | Midlevel Developers | 1 | 140 |  | 0
| FS Document | 16 | 2 | Tester | 1 | 64 |  | 0
| FS Document Sign Off (2 Working Days) |  |  | Total |  | 316 |  | 0
| Database Design | 8 | 1
2 | Development & Testing (Milestone 2) | 180 | 22.5
Creating Developemt Environment
| Login, Forgot Password, Reset Password | 8 | 1
| Change Password | 4 | 0.5
3 | User Module
| Welcome screen | 8 | 1
| POS Integration in the application | 24 | 3
| Payment Request Module | 16 | 2
| Log Request & Response | 8 | 1
| Web Service Integrations (Login, Payment Request, Response) | 32 | 4
| Report (2 Tabular Reports) | 16 | 2
6 | Testing and Fixes
| Internal Testing (Cycle 1) & Fixing | 64 | 8
| UAT Support & Implementation | 24 | 3
| Project Management | 40 | 5
| TOTAL | 316 | 39.5