## Android&iOS
| Image bank Mobile App |  |  |  | 2018-10-26
Friday
[7 empty] | Resource | # | Hours | Days
|  | Android |  | iOS |  |  | IOS | 1 | 120 | 15 | 8
# | Module | Hours | Man Days | Hours | Man Days | SUM | Android | 1 | 120 | 15 | 9.9375
| Project Management | 6.3 | 0.7875 | 6.3 | 0.7875 | 1.575 | Testing (QA) | 1 | 44.25 | 5.5312
| Documentation | 12 | 1.5 | 12 | 1.5 | 3 | UI/UX | 1 | 17 | 2.125
| UI/UX | 16 | 2 | 1 | 0.125 | 2.125 | PM | 1 | 12.6 | 1.575 | [7 empty] | Total Delivery Days
[6 empty] | 0 | Documentation | 1 | 24 | 3 |  |  |  | Portrait |  | Landscape |  | Portrait |  | Landscape
| Ui Design/Page Design |  |  |  |  | 0 | Web Services | 1 | 40 | 5 |  |  |  | Mob | Tab | Mob | Tab | Mob | Tab | Mob | Tab
[6 empty] | 0 |  |  | Total | 47.2313 |  | Android | 21.1156 | 3 | 1.5 | 2.5 | 2 | 24.1156 | 22.6156 | 23.6156 | 23.1156
| Mobile portrait | 47 | 5.875 | 1 | 0.125 | 6 | [5 empty] | IOS | 20.85 | 3 | 1.5 | 2.5 | 2 | 23.85 | 22.35 | 23.35 | 22.85
| Mobile landscape | 35 | 4.375 | 1 | 0.125 | 4.5 | Delivery Days | 22.6562 | [9 empty] | Total Man Days
| Tab portrait | 20 | 2.5 | 1 | 0.125 | 2.625 | [5 empty] | Dev + QA | 47.2313
| Tab landscape | 28.5 | 3.5625 | 1 | 0.125 | 3.6875 | Mobile Portrait (IOS + Android) | 6 |  |  |  | Android | [5 empty] | 50.2313 | 48.7313 | 49.7313 | 49.2313
[6 empty] | 0 | Mobile Landscape (IOS + Android) | 5 |  |  |  | IOS | [5 empty] | 50.2313 | 48.7313 | 49.7313 | 49.2313
| Development |  |  |  |  | 0 | Tab Portrait (IOS + Android) | 3
1 | Basic Setup | 8 | 1 | 8 | 1 | 2 | Tab Landscape (IOS + Android) | 4
2 | Splash | 2 | 0.25 | 2 | 0.25 | 0.5
3 | [5 empty] | 0 | Android Estimate | 21.1156
4 | Login page | 2 | 0.25 | 2 | 0.25 | 0.5 | IOS Estimate | 20.85
5 | Intenal users Dashboard | 5 | 0.625 | 5 | 0.625 | 1.25
6 | External users Dashboard | 3 | 0.375 | 3 | 0.375 | 0.75
7 | Upload Designs with fields to add metadata | 4 | 0.5 | 4 | 0.5 | 1
8 | Search by keyword | 6 | 0.75 | 6 | 0.75 | 1.5
9 | Advanced search (country, gender, newest, oldest, brand, category, internal or external customer) | 3 | 0.375 | 3 | 0.375 | 0.75
10 | Search results (downloadable, shareable) | 8 | 1 | 8 | 1 | 2
11 | Shared data view page(view or download) | 4 | 0.5 | 4 | 0.5 | 1
12 | image detail page(Space where the customer can leave comments, tags, links, references etc) | 6 | 0.75 | 6 | 0.75 | 1.5
13 | Privacy & Terms of access | 1 | 0.125 | 1 | 0.125 | 0.25
14 | About | 1 | 0.125 | 1 | 0.125 | 0.25
15 | My uploads(Designer) | 3 | 0.375 | 3 | 0.375 | 0.75
16 | My public folders | 2 | 0.25 | 2 | 0.25 | 0.5
17 | My private folders | 2 | 0.25 | 2 | 0.25 | 0.5
18 | Shared with me | 2 | 0.25 | 2 | 0.25 | 0.5
19 | Shared by me | 1 | 0.125 | 1 | 0.125 | 0.25
| Api Integration |  |  |  |  | 0
0
| Api integration (Mobile developer) | 16.5 | 2.0625 | 1 | 0.125 | 2.1875
0
| Testing |  |  |  |  | 0
| Testing Developer | 16 | 2 | 16 | 2 | 4
| QA | 23.85 | 2.9812 | 20.4 | 2.55 | 5.5312
| Total effort |  | 35.5188 |  | 15.4625 | 50.9813
| API services | 40 | 5
Assumptions
Consider only online mode
This estimation may vary based on additional functionalities and is currently based on description from Mail.
In android it will work with kitkat and above and iOS 9.0+.
We have considered all functionalities mentioned in the mail but we need clarification regarding which user(Designer/internal/External) have those features.

## Cost Estimate
| Image bank Mobile App |  |  |  | 2018-10-26
Friday
[7 empty] | Resource | # | Hours | Days
|  | Android |  | iOS |  |  | IOS | 1 | 120 | 15 | 8
# | Module | Hours | Man Days | Hours | Man Days | SUM | Android | 1 | 120 | 15 | 9.9375
| Project Management | 6.3 | 0.7875 | 6.3 | 0.7875 | 1.575 | Testing (QA) | 1 | 44.25 | 5.5312
| Documentation | 12 | 1.5 | 12 | 1.5 | 3 | UI/UX | 1 | 17 | 2.125
| UI/UX | 16 | 2 | 1 | 0.125 | 2.125 | PM | 1 | 12.6 | 1.575 | [7 empty] | Total Delivery Days
[6 empty] | 0 | Documentation | 1 | 24 | 3 |  |  |  | Portrait |  | Landscape |  | Portrait |  | Landscape
| Ui Design/Page Design |  |  |  |  | 0 | Web Services | 1 | 40 | 5 |  |  |  | Mob | Tab | Mob | Tab | Mob | Tab | Mob | Tab
[6 empty] | 0 |  |  | Total | 47.2313 |  | Android | 21.1156 | 3 | 1.5 | 2.5 | 2 | 24.1156 | 22.6156 | 23.6156 | 23.1156
| Mobile portrait | 47 | 5.875 | 1 | 0.125 | 6 | [5 empty] | IOS | 20.85 | 3 | 1.5 | 2.5 | 2 | 23.85 | 22.35 | 23.35 | 22.85
| Mobile landscape | 35 | 4.375 | 1 | 0.125 | 4.5 | Delivery Days | 22.6562 | [9 empty] | Total Man Days
| Tab portrait | 20 | 2.5 | 1 | 0.125 | 2.625 | [5 empty] | Dev + QA | 47.2313
| Tab landscape | 28.5 | 3.5625 | 1 | 0.125 | 3.6875 | Mobile Portrait (IOS + Android) | 6 |  |  |  | Android | [5 empty] | 50.2313 | 48.7313 | 49.7313 | 49.2313
[6 empty] | 0 | Mobile Landscape (IOS + Android) | 5 |  |  |  | IOS | [5 empty] | 50.2313 | 48.7313 | 49.7313 | 49.2313
| Development |  |  |  |  | 0 | Tab Portrait (IOS + Android) | 3
1 | Basic Setup | 8 | 1 | 8 | 1 | 2 | Tab Landscape (IOS + Android) | 4 | [9 empty] | Total Hours
2 | Splash | 2 | 0.25 | 2 | 0.25 | 0.5 | [5 empty] | Dev + QA
3 | [5 empty] | 0 | Android Estimate | 21.1156 |  |  |  | Android | [5 empty] | 401.85 | 389.85 | 397.85 | 393.85
4 | Login page | 2 | 0.25 | 2 | 0.25 | 0.5 | IOS Estimate | 20.85 |  |  |  | IOS | [5 empty] | 401.85 | 389.85 | 397.85 | 393.85
5 | Intenal users Dashboard | 5 | 0.625 | 5 | 0.625 | 1.25 | [11 empty] | Contingency Hours(8%)
6 | External users Dashboard | 3 | 0.375 | 3 | 0.375 | 0.75 | [5 empty] | Dev + QA
7 | Upload Designs with fields to add metadata | 4 | 0.5 | 4 | 0.5 | 1 | [5 empty] | Android | [5 empty] | 433.998 | 421.038 | 429.678 | 425.358
8 | Search by keyword | 6 | 0.75 | 6 | 0.75 | 1.5 | [5 empty] | IOS | [5 empty] | 433.998 | 421.038 | 429.678 | 425.358
9 | Advanced search (country, gender, newest, oldest, brand, category, internal or external customer) | 3 | 0.375 | 3 | 0.375 | 0.75
10 | Search results (downloadable, shareable) | 8 | 1 | 8 | 1 | 2
11 | Shared data view page(view or download) | 4 | 0.5 | 4 | 0.5 | 1 | [5 empty] | Dev + QA | Cost / Hr
12 | image detail page(Space where the customer can leave comments, tags, links, references etc) | 6 | 0.75 | 6 | 0.75 | 1.5 | [5 empty] | Android |  | 15 | 15 | 15 | 15 | 423148.05 | 410512.05 | 418936.05 | 414724.05
13 | Privacy & Terms of access | 1 | 0.125 | 1 | 0.125 | 0.25 | [5 empty] | IOS |  | 18 | 18 | 18 | 18 | 507777.66 | 492614.46 | 502723.26 | 497668.86
14 | About | 1 | 0.125 | 1 | 0.125 | 0.25 | [11 empty] | (including CF)
15 | My uploads(Designer) | 3 | 0.375 | 3 | 0.375 | 0.75 | [5 empty] | Android | [5 empty] | 486620.2575 | 472088.8575 | 481776.4575 | 476932.6575
16 | My public folders | 2 | 0.25 | 2 | 0.25 | 0.5 | [5 empty] | IOS | [5 empty] | 583944.309 | 566506.629 | 578131.749 | 572319.189
17 | My private folders | 2 | 0.25 | 2 | 0.25 | 0.5
18 | Shared with me | 2 | 0.25 | 2 | 0.25 | 0.5
19 | Shared by me | 1 | 0.125 | 1 | 0.125 | 0.25
| Api Integration |  |  |  |  | 0
0
| Api integration (Mobile developer) | 16.5 | 2.0625 | 1 | 0.125 | 2.1875
0
| Testing |  |  |  |  | 0
| Testing Developer | 16 | 2 | 16 | 2 | 4
| QA | 23.85 | 2.9812 | 20.4 | 2.55 | 5.5312
| Total effort |  | 35.5188 |  | 15.4625 | 50.9813
| API services | 40 | 5
Assumptions
Consider only online mode
This estimation may vary based on additional functionalities and is currently based on description from Mail.
In android it will work with kitkat and above and iOS 9.0+.
We have considered all functionalities mentioned in the mail but we need clarification regarding which user(Designer/internal/External) have those features.

## Sheet1
Total Cost Inclusive of Consultation Fee
| Portrait |  | Landscape
| Mob | Tab | Mob | Tab
Android | 486620.2575 | 472088.8575 | 481776.4575 | 476932.6575
IOS | 583944.309 | 566506.629 | 578131.749 | 572319.189
Total Delivery Days
| Portrait |  | Landscape
| Mob | Tab | Mob | Tab
Android | 24.1156 | 22.6156 | 23.6156 | 23.1156
IOS | 23.85 | 22.35 | 23.35 | 22.85