## Tax Academy Estimate
| Tax Academy - PWC |  | 16/4/2020
Thursady
| Module | Hours | Man Days
Initiation
1 | Business analysis | 24 | 3
2 | Project Management | 52.6 | 6.575
3 | SRS,FS,User Manual | 24 | 3
4 | Design and Prototype with PWC Brand Compliance (Laptop, PC, Tablets) |  | 10
Responsive for mobile phones (Phase 2)
Development
5 | Application basic setup | 8 | 1
Registration & Sign in
| Register new user | 8 | 1
| Login with social media (only LinkedIn considered) | 6 | 0.75
| LDAP integration & AD (Phase 2) |  | 0
| Login integration with PWC (optional) |  | 0
| Key cloak integration (Optional: Phase 2) |  | 0
| Multi Factor Autentication (email, Phone:SMS - OTP) | 12 | 1.5
| Verify email, forgot password, forgot User name, remember password | 8 | 1
| Authentication / Authorization / Access control | 12 | 1.5
| Login & Log out | 4 | 0.5
Static Pages & General Site Features
| About Us | 4 | 0.5
| Contact Us, Call Us, Request a call back | 18 | 2.25
| Social Media | 4 | 0.5
| Terms of Use, Privacy Policy, Refund Policy, Course Reschedule policy, Corporate Learning | 12 | 1.5
| Help & Support (simple) | 12 | 1.5
| Blog: simple (Phase 1) | 12 | 1.5
| Live Chat (Phase 2) |  | 0
| Advanced blog (Phase 2) |  | 0
| Advanced Help & Support : Phase 2) |  | 0
Home Page Elements
| Search Courses (simple: DB Based) | 16 | 2
| Banner Image, logo, PWC Branding |  | 0
| Learning Paths ( Bundled courses to gain expertise in a specific area) (Phase 2 optional) | 8 | 1
| Trending courses | 4 | 0.5
| Popular courses | 4 | 0.5
| Explore all courses (via Button) | 16 | 2
| PWC Tax Academy reviews | 6 | 0.75
| Partners | 2 | 0.25
| Features of Tax Academy | 2 | 0.25
Course related Pages (General before logging)
| Course list page (after search or after pressing the "Show Courses" button): Multi card layout | 16 | 2
| Card layout Information : Course name, short description, Actual price, course creater, credentials, Discount Price if any) | 6 | 0.75
| Advanced search for Course list page by categories, most popular etc | 16 | 2
| Course Details Page (Course image, short description, long description, ratings, views, key topics, course curriculum : Eligibility, prerequisies, Course contents, Syllabus, certification details) | 16 | 2
Admin
| Login/logout | 6 | 0.75
| manage Users | 14 | 1.75
| Create roles (Authors, content creators)) | 12 | 1.5
| Uploiad course | 12 | 1.5
| Access Analytics ( Basic) | 16 | 2
| Advanced Analytics (Phase 2) |  | 0
| Manage learning paths | 12 | 1.5
| Manage course ( course details + artifact directories + topic rating) | 12 | 1.5
| tag courses, learning paths and artifacts | 6 | 0.75
| Track user activity | 6 | 0.75
| Integration with content provider | 32 | 4
User Dashboard (After logging)
| Profile icon with drop down (Update profile, invoices, Exams, certificates, help & support) | 4 | 0.5
| Courses Section with progress | 6 | 0.75
| Courses for bundeled courses section | 6 | 0.75
| Advanced search, sorting and filtering | 6 | 0.75
| Course details | 6 | 0.75
| select course for purchase | 8 | 1
| add to cart | 4 | 0.5
| make payment | 12 | 1.5
| Update Dashboard | 4 | 0.5
System Integration
| SMS integration | 12 | 1.5
| Payment gateway integration | 12 | 1.5
| Course content integration | 40 | 5
| Document store integration (Phase 2) |  | 0
| Keaycloak (identity management : Phase 2) |  | 0
| REDIS Integration (Phase 2) |  | 0
| ELK stack integration (Phase 2) |  | 0
| HDInsight integration (Phase 3) |  | 0
| Notifications (SMS, Email) | 12 | 1.5
| Scorm Integraion (Phase 2) |  | 0
| Google Analytics integration (Pdhase 3) |  | 0
Security Features
| Protection against injection (SQL, CRLF, LDAP) | 6 | 0.75
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
| Auditing and logging | 6 | 0.75
| Exception Handling and error handling | 6 | 0.75
Quality Assurance
| QA & Bug Fixing | 186.9 | 23.3625
| UAT | 40 | 5
| Deployment per instance | 16 | 2
| Total Effort |  | 119.6875
Assumptions
The effort may change after a detailed system study

## TAX Academy-Prashant
| Tax Academy - PWC |  | 16/4/2020
Thursady
| Module | Hours | Man Days | Resource | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
1 | Business analysis | 24 | 3 | Sr Developer | 1.5 | 22.6667 | 34 | 66.75 | 73.575 | 66.75 | 67
2 | Project Management | 52.6 | 6.575 | Jr Developer | 1.5 | 22 | 33
3 | SRS,FS,User Manual | 24 | 3 | PM | 1 | 6.575 | 6.575
4 | Design and Prototype with PWC Brand Compliance (laptop, PC, Tablets) | 80 | 10 | BA | 1 | 3 | 3
| Responsive for mobile phones (Phase 2) |  |  | Tech writer | 1 | 3 | 3
| Development |  |  | QA | 2 | 14.1812 | 28.3625
5 | Application basic setup | 8 | 1 | Total | 9 | 81.4229 | 117.9375
| Registration & Sign in |  |  | - | - | - | -
| Register new user | 8 | 1 | Effort | 117.9375 | + 2 Day (Deployment) |  |  |  | 14.7422
| Login with social media (only LinkedIn considered) | 6 | 0.75 | Delivery Time | 46.1812 | + 2 Day (Deployment) |  |  |  | 2.3091
| LDAP integration & AD (Phase 2) |  | 0
| Login integration with PWC (optional) |  | 0
| Key cloak integration (Optional: Phase 2) |  | 0
| Multi Factor Autentication (email, Phone:SMS - OTP) | 12 | 1.5
| Verify email, forgot password, forgot User name, remember password | 8 | 1
| Authentication / Authorization / Access control | 12 | 1.5
| Login & Log out | 4 | 0.5
Static Pages & General Site Features
| About Us | 4 | 0.5
| Contact Us, Call Us, Request a call back | 18 | 2.25
| Social Media | 4 | 0.5
| Terms of Use, Privacy Policy, Refund Policy, Course Reschedule policy, Corporate Learning | 12 | 1.5
| Help & Support (simple) | 12 | 1.5
| Blog: simple (Phase 1) | 12 | 1.5
| Live Chat (Phase 2) |  | 0
| Advanced blog (Phase 2) |  | 0
| Advanced Help & Support : Phase 2) |  | 0
Home Page Elements
| Search Courses (simple: DB Based) | 16 | 2
| Banner Image, logo, PWC Branding |  | 0
| Learning Paths ( Bundled courses to gain expertise in a specific area) (Phase 2 optional) | 8 | 1
| Trending courses | 4 | 0.5
| Popular courses | 4 | 0.5
| Explore all courses (via Button) | 16 | 2
| PWC Tax Academy reviews | 6 | 0.75
| Partners | 2 | 0.25
| Features of Tax Academy | 2 | 0.25
Course related Pages (General before logging)
| Course list page (after search or after pressing the "Show Courses" button): Multi card layout | 16 | 2
| Card layout Information : Course name, short description, Actual price, course creater, credentials, Discount Price if any) | 6 | 0.75
| Advanced search for Course list page by categories, most popular etc | 16 | 2
| Course Details Page (Course image, short description, long description, ratings, views, key topics, course curriculum : Eligibility, prerequisies, Course contents, Syllabus, certification details) | 16 | 2
Admin
| Login/logout | 6 | 0.75
| manage Users | 14 | 1.75
| Create roles (Authors, content creators)) | 12 | 1.5
| Uploiad course | 12 | 1.5
| Access Analytics ( Basic) | 16 | 2
| Advanced Analytics (Phase 2) |  | 0
| Manage learning paths | 12 | 1.5
| Manage course ( course details + artifact directories + topic rating) | 12 | 1.5
| tag courses, learning paths and artifacts | 6 | 0.75
| Track user activity | 6 | 0.75
| Integration with content provider | 32 | 4
User Dashboard (After logging)
| Profile icon with drop down (Update profile, invoices, Exams, certificates, help & support) | 4 | 0.5
| Courses Section with progress | 6 | 0.75
| Courses for bundeled courses section | 6 | 0.75
| Advanced search, sorting and filtering | 6 | 0.75
| Course details | 6 | 0.75
| select course for purchase | 8 | 1
| add to cart | 4 | 0.5
| make payment | 12 | 1.5
| Update Dashboard | 4 | 0.5
System Integration
| SMS integration | 12 | 1.5
| Payment gateway integration | 12 | 1.5
| Course content integration | 40 | 5
| Document store integration (Phase 2) |  | 0
| Keaycloak (identity management : Phase 2) |  | 0
| REDIS Integration (Phase 2) |  | 0
| ELK stack integration (Phase 2) |  | 0
| HDInsight integration (Phase 3) |  | 0
| Notifications (SMS, Email) | 12 | 1.5
| Scorm Integraion (Phase 2) |  | 0
| Google Analytics integration (Pdhase 3) |  | 0
Security Features
| Protection against injection (SQL, CRLF, LDAP) | 6 | 0.75
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
| Auditing and logging | 6 | 0.75
| Exception Handling and error handling | 6 | 0.75
Quality Assurance
| QA & Bug Fixing | 186.9 | 23.3625
| UAT | 40 | 5
| Deployment per instance | 16 | 2
| Total Effort |  | 119.6875
Assumptions
The effort may change after a detailed system study