## Summary
Track | Resources | Hours | Days | Total Days | Contingency Hours | Contingency (15%) | Contingency (12%) | With Contingency (20%) | Mobile | Days |  | WEB | Days | Rate/hr | Total Amt (20%) | Total Amt(15%) | Total Amount (12%)
UI/UX | 1 | 80 | 10 | 10 | 96 | 11.5 | 11.2 | 12 | UI/UX IOS | 5 |  |  |  | 780 | 74880 | 71760 | 69888
Web API | 1 | 180 | 22.5 | 22.5 | 216 | 25.875 | 25.2 | 27 | IOS APP DEV | 65.3125 |  | Web API Dev | 22.5 | 780 | 168480 | 161460 | 157248
IOS App | 1.5 | 348.3333 | 43.5417 | 65.3125 | 627 | 75.1094 | 73.15 | 78.375 | QA IOS | 29.3906 |  | QA Web API | 6.75 | 1170 | 733590 | 703023.75 | 684684
Android App | 1.5 | 348.3333 | 43.5417 | 65.3125 | 627 | 75.1094 | 73.15 | 78.375 | IOS PM | 4.2062 |  | Web API PM | 2.25 | 910 | 570570 | 546796.25 | 532532
QA Web API | 2 | 27 | 3.375 | 6.75 | 64.8 | 7.7625 | 7.56 | 8.1 | IOS BA | 1.5 |  | WEB API BA | 1 | 650 | 42120 | 40365 | 39312
QA IOS | 2 | 117.5625 | 14.6953 | 29.3906 | 282.15 | 33.7992 | 32.9175 | 35.2687 | Total | 105.4094 |  | Total | 32.5 | 650 | 183397.5 | 175755.9375 | 171171
QA Android | 2 | 117.5625 | 14.6953 | 29.3906 | 282.15 | 33.7992 | 32.9175 | 35.2687 | [5 empty] | 650 | 183397.5 | 175755.9375 | 171171
PM | 1 | 98 | 12.25 | 12.25 | 117.6 | 14.0875 | 13.72 | 14.7 | Grand Total | 243.3187 |  |  |  | 1300 | 152880 | 146510 | 142688
BA | 1 | 24 | 3 | 3 | 28.8 | 3.45 | 3.36 | 3.6 | [5 empty] | 975 | 28080 | 26910 | 26208
Total Hours |  |  |  | 1951.25 | 2341.5 | 2243.9375 | 2185.4 | [7 empty] | 2137395 | 2048336.875 | 1994902
Total Man Days |  |  |  | 243.9062 |  |  |  | 292.6875 |  | Hours | Days
Total Man Month |  |  |  | 12.1953 |  |  |  |  | WebAPI Total | 260 | 32.5
[9 empty] | IOS APP | 843.275 | 105.4094 |  |  |  |  | Final Quote
Delivery Days | 68.237 | 81.8844 | [6 empty] | Android App | 843.275 | 105.4094 |  |  | Android Alone | 1220407.5 | 1403468.625
Delivery Months | 3.4118 | 4.0942 | [7 empty] | 1946.55 | 243.3188 |  |  | IOS Alone | 1383427.5 | 1590941.625
[14 empty] | Together | 2048336.875 | 2355587.4062

## Web Api
Modules | Man Hour | Days
PM | 18 | 2.25
Login (with two factor authentication) | 8 | 1
Forgot Password | 4 | 0.5
Reset Password | 2 | 0.25
Change Password | 2 | 0.25
Assessment Year | 2 | 0.25
Plan Selection | 12 | 1.5
XML Upload | 6 | 0.75
Tax Filing |  | 0
Personal Details | 20 | 2.5
Income Sources | 40 | 5
Deductions | 32 | 4
Taxes Paid | 12 | 1.5
Summary & Review | 8 | 1
Payment | 12 | 1.5
Dashboard | 20 | 2.5
Testing | 54 | 6.75 | 12
Total | 252 | 31.5
0
Development | 180 | 22.5
QA | 54 | 6.75
PM | 18 | 2.25
BA | 8 | 1
Total | 260 | 32.5

## Mobile App - Android & iOS
Taxbreeze Mobile Estimate
Modules | Hours | Days | Hours | Days |  | Resources |  | Days | Total
| Android |  | iOS |  |  | PM | 1 | 3.5312 | 3.5312
Ui Design | [5 empty] | Designer | 1.5 | 10 | 15
UI/UX (15 page layout only) | 80 | 10 |  |  |  | Developer | 1.5 | 30.0417 | 45.0625
Page Design | 162 | 20.25 | 162 | 20.25 |  | QA | 1 | 15.8906 | 15.8906
[7 empty] | Total |  | 79.4844
Development |  |  |  |  | UI/UX |  | 10
Basic Setup | 8 | 1 | 8 | 1 | Andorid | Delivery Time | 55.9323
Splash Screen | 1 | 0.125 | 1 | 0.125 |  | Total Effort | 79.4844
Login Page | 2 | 0.25 | 2 | 0.25
SignUp page | 4 | 0.5 | 4 | 0.5 | IOS
Eligibility page | 1.5 | 0.1875 | 1.5 | 0.1875 |  | Resources | # | Days | Total
Dash board |  | 0 |  | 0 |  | PM | 1 | 8.4125 | 8.4125
Tax summary | 2 | 0.25 | 2 | 0.25 |  | UI/UX | 1 | 10 | 10
challan | 4 | 0.5 | 4 | 0.5 |  | IOS Developer | 1 | 65.3125 | 65.3125
Show uploaded docments | 4 | 0.5 | 4 | 0.5 |  | Android Developer | 1 | 65.3125 | 65.3125
filter | 1 | 0.125 | 1 | 0.125 |  | QA IOS | 1 | 29.3906 | 29.3906 | 235.125
Show ITR related docs | 4 | 0.5 | 4 | 0.5 |  | QA Android | 1 | 29.3906 | 29.3906
Approve | 2 | 0.25 | 2 | 0.25 |  | BA | 1 | 3 | 3
Notification | 2 | 0.25 | 2 | 0.25 |  | Total |  |  | 210.8187
Yearly Summary | 2 | 0.25 | 2 | 0.25
Start Tax return |  | 0 |  | 0
Finantial year selection | 1 | 0.125 | 1 | 0.125
Package Selection | 8 | 1 | 8 | 1 |  | Total IOS Days | 105.4094
Selection Prefill with XML data /Prefill with PAN data | 12 | 1.5 | 12 | 1.5 |  | Total Android | 105.4094
Personal details
Personal information | 6 |  | 6
Address | 4 | 0.5 | 4 | 0.5
Residential Details (Questions based) | 8 | 1 | 8 | 1
Bank details |  | 0 |  | 0
Primary Bank Account | 2 | 0.25 | 2 | 0.25
All other bank Accounts | 6 | 0.75 | 6 | 0.75
Asset and Liability |  | 0 |  | 0
immovabile asset | 8 | 1 | 8 | 1
movable Asset | 6 | 0.75 | 6 | 0.75
Foreign Assets | 6 | 0.75 | 6 | 0.75
Salary |  | 0 |  | 0
Upload | 8 | 1 | 8 | 1
income from salary | 4 | 0.5 | 4 | 0.5
other income
Upload | 2 | 0.25 | 2 | 0.25
interest income | 1 | 0.125 | 1 | 0.125
other income | 1 | 0.125 | 1 | 0.125
Exempt income | 2 | 0.25 | 2 | 0.25
Agriculture income | 2 | 0.25 | 2 | 0.25
Dependent income | 4 | 0.5 | 4 | 0.5
PF withdrawal income | 2 | 0.25 | 2 | 0.25
House property
Upload | 1 | 0.125 | 1 | 0.125
Property Address | 4 | 0.5 | 4 | 0.5
interest paid | 6 | 0.75 | 6 | 0.75
property ownership | 12 | 1.5 | 12 | 1.5
income from rental property | 6 | 0.75 | 6 | 0.75
unrealized Rent | 4 | 0.5 | 4 | 0.5
Capital Gain | 4 | 0.5 | 4 | 0.5
Section 80 |  | 0 |  | 0
upload | 1 | 0.125 | 1 | 0.125
section 80c | 4 | 0.5 | 4 | 0.5
section 80D | 2 | 0.25 | 2 | 0.25
section 80TTA | 1 | 0.125 | 1 | 0.125
section 80G | 6 | 0.75 | 6 | 0.75
more deductions
section 80CCG | 1 | 0.125 | 1 | 0.125
section 80E | 1 | 0.125 | 1 | 0.125
section 80CCC | 1 | 0.125 | 1 | 0.125
section 80CCD(1),(1B)&(2) | 2 | 0.25 | 2 | 0.25
Section 80GG | 1 | 0.125 | 1 | 0.125
Section 80DDB | 1 | 0.125 | 1 | 0.125
Section 80EE | 1 | 0.125 | 1 | 0.125
Section 80QQB | 2 | 0.25 | 2 | 0.25
Section 80RRB | 3 | 0.375 | 3 | 0.375
Section 80GGA | 4 | 0.5 | 4 | 0.5
Section 80GGC | 5 | 0.625 | 5 | 0.625
Section 80DD | 2 | 0.25 | 2 | 0.25
Section 80U | 1 | 0.125 | 1 | 0.125
Taxes paid |  | 0 |  | 0
upload 26AS | 2 | 0.25 | 2 | 0.25
challan Details | 4 | 0.5 | 4 | 0.5
Summary and Review | 6 | 0.75 | 6 | 0.75
PDF Report | 8 | 1 | 8 | 1
Payment | 12 | 1.5 | 12 | 1.5
Help center |  | 0 |  | 0
Chat bot | 32 | 4 | 32 | 4
Whats new | 4 | 0.5 | 4 | 0.5
Contact Us |  | 0 |  | 0
Submit request | 8 | 1 | 8 | 1
Terms and Condition | 4 | 0.5 | 4 | 0.5
Legal privacy | 2 | 0.25 | 2 | 0.25
Support for Tab & iPad | 20 | 2.5 | 20 | 2.5
Api Integration |  | 0
Api integration | 34 | 4.25 | 34 | 4.25
Testing
Developer side testing | 24 | 3 | 24 | 3
Total effort |  | 65.3125 |  | 65.3125