## PWC
| PWC_Web_Capturing form details |  | 2018-02-20
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 12 | 12
1 | Business analysis | 0 | 0 | Sr Developer | 1 | 25 | 25 | 0 | 50
2 | Project Management | 0 | 0 | Jr Developer | 1 | 25 | 25
3 | Project Documentation (SRS, Scope, WBS etc.) | 0 | 0 | PM | 1 | 0 | 0
4 | Prototype Updates | 32 | 12 | BA | 1 | 1 | 1
| Functional Spec | 8 | 1 | Tech writer | 1 | 4 | 4
| Development |  |  | QA | 2 | 0.25 | 0.5
5 | Login |  |  | Total |  |  | 67.5
6 | Login
7 | Social Media Login | [6 empty] | <--- This would be the minimum time required
3 | Create an account (registration) |  |  | Total Delivery days | 37.25
4 | Forgot passowrd |  |  | Total Effort | 67.5 | (+1 Day deployment)
5 | Logout
7 | Basic Details
8 | Prefill from PAN #
9 | Prefill from XML
10 | Basic Tax Profile (options)
11 | Personal Details
12 | Personal information
13 | Address
14 | Bank Details (Primary & Secondary Bank Accounts)
15 | Assets and Liabilities
16 | Immovable Assets (+)
17 | Movable Assets (+)
18 | Assosiation of Persons (+)
19 | Foreign Assets (+)
20 | Income Sources
21 | Salary (form 16, head salaries, TDS, Doc Upload) (+)
22 | Other Income
23 | Doc Upload
24 | Interest income
25 | Other Income
26 | Exempt
27 | Agriculture
28 | Dependent (+)
29 | PF Withdrawal
30 | House & Property
31 | House Address (+)
32 | Interest Paid on Housing Loan (Doc Upload)
33 | Property Ownership (+)
34 | Rental Property
35 | Property Address (+)
36 | Income from rental property (+)
37 | Interest paid on rental property (+) , Upload Doc
38 | Unrealized rent (+)
39 | Rental Property Ownership (+)
40 | Capital Gains (upload multiple documents)
41 | Deductions
42 | Section 80
43 | Other deductions
44 | Taxes Paid
45 | 26 AS
46 | Chellan Details (+)
47 | Submit to PWC
48 | Update information before submit
49 | Preselect Plan , Make Payment
50 | Dashboard
51 | Status Update
52 | Tax summary
53 | ITR, Tax Computation (document downloads)
54 | Upgrade Plan
55 | Submit new documentation
56 | Download Tax documents (using previous year)
57 | Search
58 | System Features
59 | Authentication, Authorization, Entitlements
60 | Logging, Auditing, Exceptions
61 | Document management (Tagging + meta data + Archiving )
62 | SMS & Email
63 | API Services
State Management
Database Services
Business layer
Reload application state (from where the user left off)
Routing based on basic tax profile
Quality Assurance
| QA & Bug Fixing | 0 | 0
| UAT | 4 | 0.5
| Deployment | 4 | 0.5
| Total Effort | 48 | 14
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions