## PWC
| PWC_Web_Capturing form details |  | 2018-02-20
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
1 | Business analysis | 0 | 0 | Sr Developer | 1 | 25 | 25 | 50.25 | 50
2 | Project Management | 33.6 | 4.2 | Jr Developer | 1 | 25 | 25
3 | Project Documentation (SRS, Scope, WBS etc.) | 0 | 0 | PM | 1 | 4.2 | 4.2
4 | Prototype Updates | 40 | 5 | BA | 1 | 1 | 1
5 | Functional Spec | 8 | 1 | Tech writer | 1 | 0 | 0
| Development |  |  | QA | 2 | 8.65 | 17.3
6 | database design and development | 6 | 0.75 | Total |  |  | 77.5
7 | Website | 40 | 5
8 | Login |  | 0 |  |  |  |  | <--- This would be the minimum time required
9 | Login | 4 | 0.5 | Total Delivery days | 33.65
10 | Social Media Login | 8 | 1
11 | Create an account (registration) | 8 | 1 | Total Effort | 77.5 | (+1 Day deployment)
12 | Eligibility | 4 | 0.5
13 | Forgot password | 8 | 1
14 | Logout | 4 | 0.5
15 | Basic Details
16 | Prefill from XML | 8 | 1
17 | Prefill from PAN # | 8 | 1
18 | Basic Tax Profile (options) | 4 | 0.5
19 | Personal Details
20 | Personal information | 8 | 1
21 | Address | 8 | 1
22 | Bank Details (Primary & Secondary Bank Accounts) | 8 | 1
23 | Assets and Liabilities
24 | Immovable Assets | 8 | 1
25 | Movable Assets | 4 | 0.5
26 | Assosiation of Persons | 8 | 1
27 | Foreign Assets | 4 | 0.5
28 | Income Sources
29 | Salary (form 16, head salaries, TDS, Doc Upload) | 8 | 1
30 | Other Income
31 | Doc Upload | 4 | 0.5
32 | Interest income | 4 | 0.5
33 | Other Income | 4 | 0.5
34 | Exempt | 4 | 0.5
35 | Agriculture | 4 | 0.5
36 | Dependent | 8 | 1
37 | PF Withdrawal | 4 | 0.5
38 | House & Property
39 | House Address | 3 | 0.375
40 | Interest Paid on Housing Loan (Doc Upload) | 3 | 0.375
41 | Property Ownership | 2 | 0.25
42 | Rental Property
43 | Property Address | 3 | 0.375
44 | Income from rental property | 4 | 0.5
45 | Interest paid on rental property , Upload Doc | 3 | 0.375
46 | Unrealized rent | 2 | 0.25
47 | Rental Property Ownership | 4 | 0.5
48 | Capital Gains (upload multiple documents) | 4 | 0.5
49 | Deductions
50 | Section 80 | 8 | 1
51 | Other deductions | 8 | 1
52 | Taxes Paid
53 | 26 AS | 4 | 0.5
54 | Chellan Details | 4 | 0.5
55 | Submit to PWC
56 | Update information before submit | 4 | 0.5
57 | Preselect Plan | 4 | 0.5
58 | Make Payment | 24 | 3
59 | Dashboard
60 | Status Update | 2 | 0.25
61 | Tax summary | 2 | 0.25
62 | Upgrade Plan | 16 | 2
63 | Submit new documentation | 8 | 1
64 | Download Tax documents | 4 | 0.5
65 | Search | 8 | 0.5
66 | System Features
67 | Authentication, Authorization, Entitlements | 4 | 0.5
68 | Logging, Auditing, Exceptions | 8 | 1
69 | Document management (Tagging + meta data + Archiving ) | 24 | 3
70 | SMS & Email | 8 | 1
71 | API Services | 24 | 3
72 | State Management (Reload application state from where the user left off) | 8 | 1
73 | Database Services | 8 | 1
74 | Business Layer | 8 | 1
Quality Assurance
75 | QA & Bug Fixing | 134.4 | 16.8
76 | UAT | 4 | 0.5
77 | Deployment | 4 | 0.5
| Total Effort | 630 | 78.25
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions
SMS Gateway to be shared by the client