## Survey Application
| PWC_Web_Capturing form details |  | 2018-02-20
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 12 | 12
1 | Business analysis | 8 | 1 | Sr Developer | 1 | 25 | 25 | 50 | 50
2 | Project Management | 40 | 5 | Jr Developer | 1 | 25 | 25
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 | PM | 1 | 5 | 5
4 | Complete running prototype | 96 | 12 | BA | 1 | 5 | 5
| Functional Spec | 8 | 1 | Tech writer | 1 | 4 | 4
| Development |  |  | QA | 2 | 11.25 | 22.5
| Admin |  |  | Total |  |  | 98.5
1 | User Management | 8 | 1
2 | Price Management | 8 | 1 |  |  |  |  | <--- This would be the minimum time required
3 | Plan Management | 12 | 1.5 | Total Delivery days | 48.25
4 | Refer friend | 4 | 0.5 | Total Effort | 98.5 | (+1 Day deployment)
5 | Promo Code | 12 | 1.5
6 | Services | 8 | 1
| Pricing | 12 | 1.5
1 | Help Centre | 16 | 2
2 | Contact | 4 | 0.5
3 | Manage Questions | 40 | 5
4 | Home
| Registration | 8 | 1
| Login | 4 | 0.5
| Dashboard | 16 | 2
| Basic Information | 12 | 1.5
| Personal Information | 20 | 2.5
| Address Details | 12 | 1.5
| Salary & Form 16 | 24 | 3
| Additional Tax Benefits | 20 | 2.5
| Other Income | 8 | 1
| House Property | 8 | 1
1 | Bank Details | 12 | 1.5
2 | Upload Documents | 24 | 3
3 | confirmation | 4 | 0.5
4 | Payment gateway integration | 24 | 3
| APIs for transferring the details to external software | 32 | 4
1 | System features
2 | Auditing & logging | 4 | 0.5
3 | Exception handling | 4 | 0.5
| User Manual | 32 | 4
| Document Archival | 8 | 1
Quality Assurance
| QA & Bug Fixing | 176 | 22
| UAT | 4 | 0.5
| Deployment | 4 | 0.5
| Total Effort | 760 | 95
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions