## Survey Application
| PWC_Web_Capturing form details |  | 2018-02-20 | Original Effort | 98
|  |  | Tuesday | delivery | 48
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
1 | Business analysis | 8 | 1 | Sr Developer | 1 | 17 | 17 | 34.5 | 34
2 | Project Management | 27.6 | 3.45 | Jr Developer | 1 | 17 | 17
3 | Project Documentation (SRS, Scope, WBS etc.) | 8 | 1 | PM | 1 | 3.45 | 3.45
4 | Complete running prototype | 40 | 5 | BA | 1 | 3 | 3
| Functional Spec | 8 | 1 | Tech writer | 1 | 4 | 4
| Development |  |  | QA | 2 | 5.325 | 10.65
| Admin |  |  | Total |  |  | 60.1
1 | User Management | 8 | 1
2 | Price Management | 0 | 0 |  | 27.325 |  |  | <--- This would be the minimum time required
3 | Plan Management | 12 | 1.5
4 | Refer friend | 4 | 0.5
5 | Promo Code | 8 | 1
6 | Services | 8 | 1
| Pricing | 0 | 0
1 | Help Centre | 16 | 2
2 | Contact | 4 | 0.5
3 | Manage Questions | 32 | 4
4 | Home
| Registration | 8 | 1
| Login | 4 | 0.5
| Dashboard | 16 | 2
| Basic Information | 6 | 0.75
| Personal Information | 6 | 0.75
| Address Details | 6 | 0.75
| Salary & Form 16 | 8 | 1
| Additional Tax Benefits | 12 | 1.5
| Other Income | 12 | 1.5
| House Property | 12 | 1.5
1 | Bank Details | 6 | 0.75
2 | Upload Documents | 12 | 1.5
3 | confirmation | 4 | 0.5
4 | Payment gateway integration | 12 | 1.5
| APIs for transferring the details to external software | 16 | 2
1 | System features
2 | Auditing & logging | 6 | 0.75
3 | Exception handling | 6 | 0.75
| User Manual | 24 | 3
| Document Archival | 8 | 1
Quality Assurance
| QA & Bug Fixing | 81.2 | 10.15
| UAT | 4 | 0.5
| Deployment | 4 | 0.5
| Total Effort | 456.8 | 57.1
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions