## Sheet1
PWC Phase 2 |  | 15/05/2018
Tuesday
Initiation | Hours | Days
Business Analysis | 16 | 2 | Resource | No | Man Days | Total Effort
Project Management | 107.6 | 13.45 | Designer | 1 | 3 | 3
UI/UX | 24 | 3 | Sr Developer | 1 | 45 | 45 | 134.5 | 135
Documentation | 8 | 1 | Jr Developer | 2 | 45 | 90
Development |  |  | PM | 1 | 13.45 | 13.45
Admin |  |  | BA | 1 | 2 | 2
User Management with roles & entitlements | 16 | 2 | Tech writer | 1 | 1 | 1
End user Listing: Year wise user management screen | 8 | 1 | QA | 2 | 20.175 | 40.35
Unlock User | 6 | 0.75 | Total |  |  | 194.8
Manage Corporate Clients | 16 | 2 | Total Delivery days | 68.175
Notifications | 6 | 0.75 | Total Effort | 194.8 | (+1 Day deployment)
Plan Management | 16 | 2
Price Management: Pricing configuration | 16 | 2 | Approx | 1215552
Help Centre Content (https://www.hrblock.com/support/) Management : CMS includes Services updates | 40 | 5
Ip Management w.r.t corporate clients | 16 | 2
Video Management: Change videos displayed on web page | 12 | 1.5
Dashboard Updates | 8 | 1
Resubmission of Returns | 16 | 2
Trigger from Admin console
Resubmit Documents (end User)
Notification on end user Dashboard
Repush Failed tax filings (failed due to time out or some other technical glitches)
Revise Returns | 16 | 2
Revise Data
Maintain history of updated Data
Data Gathering based on Plan Selection | 24 | 3
Based on plan selection, select wizard
Plan Upgrade | 28 | 3.5
Change the selected plan
Plan Upgrade Reccomendation
Master Data Management | 28 | 3.5
IFSC Code, Bank Name, Investment Category
Account type, Pin Code, Employer Type, Tax Rate, City, State
Qualifying Percentage, Deduction Age, Financial Year, Tax Filing Status
Plan Types, Promo Codes, Service Types
Notification Management : Notification on new changes via Email | 28 | 3.5
After e-filing, Query response email, Email link to feedback form
Reminder email for review, Email after review (Tax processing)
Missing Info Email, Reminder for missing info, Disclaimer for non-response
Advanced Logging & Auditing for Security | 24 | 3
User Events
System Events
Admin Events
Multifactor Authentication | 24 | 3
OTP (Phone + Email )
Captcha
Japanese Language integration | 416 | 52
Create Resource File (Global And Local Res. files)
Create Multi language Routes and Route handling mechanism (includes SEO)
Activate Culture & Upgrade content, labels and form values
Total # of pages to modify 78 (@4hrs/page) | 312 | 39 | 312
QA + UAT | 322.8 | 40.35
Total | 1554.4 | 194.3

## Sheet2
Removed Features
Refer friend via email (Store Refferals to create email database) with referral bonus (gamification)
Promo Code management(dashboard, Coupon codes, Dates Valid, Distribution list, Discounts, Analytics)
Push Notification Channels( Email, SMS, Web Push, Onsite Personalization: Exit intent)
Context Sensitive Help Within tax Workflow (Hover over text for individual line items and eidtable text that can be managed via CMS)
Social Media Integration (link to FB, Lin, instagram , twitter, pinterest, google)
Promo code distribution
Referral links
Document Archival
Simple + Advanced search (Tax Documents + Site Search)
Save data on back button (Tax Workflow)
Prefill with PAN
Prior Year XML
Foreign income and assets validation : Premium plan
Other Batch Jobs (retry failed returns, Status updates pending failed returns)
End user reports (5 reports max)
Feedback form (Survey)
Values in the form should be saved on navigating to other tabs even without clicking save
Manage Customer Queries ( multi step drop down questions to narrow down common questions that requires human intervention)
Manage Email Templates (clarity required, not sure if this is relevant)
Loyalty Program for returning users (need clarity)
Email Marketing