## Phase 2
[5 empty] | Resource | No | Man Days | Total Effort
[5 empty] | Designer | 1 | 2 | 2
| PWC Phase 2 |  | 15/05/2018 |  | Sr Developer | 1 | 35 | 35 | 73.5 | 70
|  |  | Tuesday |  | Jr Developer | 1.5 | 23.3333 | 35
[5 empty] | PM | 1 | 7.35 | 7.35
| Module | Hours | Man Days |  | BA | 1 | 5 | 5
| Initiation |  |  |  | Tech writer | 1 | 4 | 4
1 | Business analysis | 16 | 2 |  | QA | 2 | 14.95 | 29.9
2 | Project Management | 58.8 | 7.35 |  | Total |  |  | 118.25
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 |  | Total Delivery days | 40.2833
4 | UI/UX | 16 | 2 |  | Total Effort | 118.25 | (+1 Day deployment)
5 | Documentation | 0 | 0
| Development |  |  | Comments
Admin
1 | User Management | 16 | 2
2 | Price & Plan Management With Plan Inclusions | 24 | 3 | Limitation in space based on the layout |  |  |  | test
3 | Refer friend via email (Store Refferals to create email database) | 4 | 0.5
4 | Promo Code management(dashboard, Coupon codes, Dates Valid, Distribution list, Discounts, Analytics) | 32 | 4
5 | Manage Services (updates the services page) | 12 | 1.5 | Limitation based on layout, Customization may not be possible as it is template based
6 | Push Notification Channels( Email, SMS, Mobile Push, Web Push, Onsite Personalization: Exit intent, pop ups, Timers, Reccomendations) | 48 | 6
7 | Help Centre | 12 | 1.5 | https://www.hrblock.com/support/ ; https://in.godaddy.com/help
8 | Context Sensitive Help Within tax Workflow | 48 | 6 | Need to discuss
9 | Manage Questions |  | 0 | ????
10 | Social Media Integration (contact Us) | 6 | 0.75 | ???
11 | Manage Customer Queries |  | 0 | Email
12 | Manage Email Templates | 32 | 4
13 | Loyalty Program ??? |  | 0 | For returning users???
14 | Repush Failed Orders | 12 | 1.5
15 | Plan Upgrade Reccomendations | 10 | 1.25
16 | Status Updates to Dashboards (Notifications) | 12 | 1.5 | Create status
17 | email Marketing(???) |  | 0 | ?
18 | Reports and Analytics |  | 0
19 | End User related Reports |  | 0 | Define report fields
20 | B2B Entity based reports |  | 0 | Define report fields
21 | Taxbreeze product (PWC) Reports |  | 0 | Define report fields
22 | Master Data Management |  | 0
23 | IFSC Code, Bank Name | 8 | 1
24 | Gender | 4 | 0.5
25 | Account type | 4 | 0.5
26 | Pin Code | 4 | 0.5
27 | Emplyer Type | 4 | 0.5
28 | Tax Rate | 4 | 0.5
29 | City, State | 8 | 1
30 | Investment category | 4 | 0.5
31 | Qualifying Percentage | 4 | 0.5
32 | deduction Age | 4 | 0.5
33 | Financial Year | 4 | 0.5
| Tax Filing Status | 4 | 0.5
Website
34 | Consume Promo codes | 8 | 1
35 | Referrals | 4 | 0.5
36 | Document Archiving | 8 | 1
37 | Simple + Advanced search (Tax Documents + Site Search) |  | 0 | may not include searching text within documents
38 | Save data on back button (Tax Workflow) | 40 | 5
39 | Prefill with PAN |  | 0 | Integration with tax site ?
40 | Change Tax Filing plan Before Submit | 20 | 2.5 | Simple use case
41 | Form -16 Upload |  | 0 | Read form ?
42 | Advanced Logging & Auditing (User Events) | 48 | 6
43 | Foreign income and assets validation : Premium plan |  | 0 | ?
44 | Multifactor Authentication | 20 | 2.5
45 | Revisit |  | 0
46 | Security Updates | 32 | 4
47 |  |  | 0
48 |  |  | 0
49 | Plan Upgrade (Intelligent reccomendations + Ability to manually upgrade plan) |  | 0 | ?
50 | Other Batch Jobs |  | 0 | ?
51 | B2B Integration |  | 0 | ?
52 | End user reports |  | 0 | ?
53 | Feedback form (Survey) | 32 | 4
54 | Split Aadhar And Enrollment ID | 4 | 0.5
55 |  |  | 0
56 | Indicator for user to identify already filled tabs | 24 | 3
57 | Values in the form should be saved on navigating to other tabs even without clicking save | 16 | 2
58 | Additional Terms& Condition during Payment(KYC Related) | 8 | 1
59 |  |  | 0
60 | Emails |  | 0
61 | After e-filing |  | 0
62 | Email link to feedback form |  | 0
63 | Query response email |  | 0
64 | Ready for review [Payable] |  | 0
65 | Ready for review [Non Payable] |  | 0
66 | reminder email for review |  | 0
67 | Email after review (Tax processing) |  | 0
68 | Confirmation email after payment |  | 0
69 | Email after approval |  | 0
70 | Missing Info Email |  | 0
71 | reminder for missing info |  | 0
72 | Disclaimer for non-response |  | 0
Quality Assurance
| QA & Bug Fixing | 235.2 | 29.4
load Testing
| UAT | 4 | 0.5
| Deployment | 4 | 0.5
| Total Effort | 946 | 118.25
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions

## Multilanguage
| Hours | Days
Transliterating to one language
Transliterating to an additional language
Create resource files
make sure its SEO Friendly
Set up Multilanguage routes (Route Localization)
Create Resource file with keys and add contents that would be provided by the client.
Modify 75 Pages to support multi-language
Effort 50 days (Including Resource file 5.5 Days)
Timeline 25 days
Note:- Only captions of the site will be updated. (The input from the user will be captured in English. The drop down values also would be in English.) The languages will be left to right.

## Mobile
Taxbreeze Mobile Estimate
Modules | Hours | Days | Hours | Days |  | Resources |  | Days | Total
| Android |  | iOS |  |  | PM | 1 | 2.6313 | 2.6313
Ui Design | [5 empty] | Designer | 1.5 | 13.1667 | 19.75
UI/UX (15 page layout only) | 10 |  |  |  |  | Developer | 1.5 | 21.7083 | 32.5625
Page Design | 158 | 19.75 | 158 | 19.75 |  | QA | 1 | 11.8406 | 11.8406
[7 empty] | Total |  | 66.7844
Development |  |  |  |  | UI/UX |  | 10
Basic Setup | 8 | 1 | 8 | 1 | Andorid | Delivery Time | 46.7156
Splash Screen | 1 | 0.125 | 1 | 0.125 |  | Total Effort | 66.7844
Login Page | 2 | 0.25 | 2 | 0.25
SignUp page | 4 | 0.5 | 4 | 0.5 | IOS
Eligibility page | 1.5 | 0.1875 | 1.5 | 0.1875
Dash board |  | 0 |  | 0
Tax summey | 2 | 0.25 | 2 | 0.25
challan | 4 | 0.5 | 4 | 0.5
upload docments from phone | 4 | 0.5 | 4 | 0.5
filter | 1 | 0.125 | 1 | 0.125
Start Tax return |  | 0 |  | 0
Finantial year selection | 1 | 0.125 | 1 | 0.125
Package Selection | 8 | 1 | 8 | 1
Selection Prefill with XML data /Prefill with PAN data | 3 | 0.375 | 3 | 0.375
Personal details
Personal information | 6 |  | 6
Address | 4 | 0.5 | 4 | 0.5
Bank details |  | 0 |  | 0
Primary Bank Account | 2 | 0.25 | 2 | 0.25
All other bank Accounts | 4 | 0.5 | 4 | 0.5
Asset and Liability |  | 0 |  | 0
immovabile assert | 6 | 0.75 | 6 | 0.75
movabile Asset | 3 | 0.375 | 3 | 0.375
Association of persons | 6 | 0.75 | 6 | 0.75
Foreign Assets | 3 | 0.375 | 3 | 0.375
Salary |  | 0 |  | 0
Upload | 4 | 0.5 | 4 | 0.5
income from salery | 2 | 0.25 | 2 | 0.25
TDS for salery | 2 | 0.25 | 2 | 0.25
other income
Upload | 1 | 0.125 | 1 | 0.125
interest income | 1 | 0.125 | 1 | 0.125
other income | 1 | 0.125 | 1 | 0.125
Exempt income | 2 | 0.25 | 2 | 0.25
Agriculture income | 2 | 0.25 | 2 | 0.25
Dependent income | 2 | 0.25 | 2 | 0.25
PF withdrawal income | 2 | 0.25 | 2 | 0.25
House property
HOuse Address | 1 | 0.125 | 1 | 0.125
interest paid | 6 | 0.75 | 6 | 0.75
property ownership | 6 | 0.75 | 6 | 0.75
Rentel property |  | 0 |  | 0
Prperty address | 6 | 0.75 | 6 | 0.75
income from renal property | 6 | 0.75 | 6 | 0.75
interest paid | 4 | 0.5 | 4 | 0.5
property ownership | 4 | 0.5 | 4 | 0.5
unrealized Rent | 4 | 0.5 | 4 | 0.5
Capital Gain | 4 | 0.5 | 4 | 0.5
Section 80 |  | 0 |  | 0
upload | 2 | 0.25 | 2 | 0.25
section 80c | 2 | 0.25 | 2 | 0.25
section 80D | 2 | 0.25 | 2 | 0.25
section 80TTA | 1 | 0.125 | 1 | 0.125
section 80G | 6 | 0.75 | 6 | 0.75
more deductions
section 80CCG | 1 | 0.125 | 1 | 0.125
section 80E | 1 | 0.125 | 1 | 0.125
section 80CCC | 1 | 0.125 | 1 | 0.125
section 80CCD(1),(1B)&(2) | 2 | 0.25 | 2 | 0.25
Section 80GG | 1 | 0.125 | 1 | 0.125
Section 80DDB | 1 | 0.125 | 1 | 0.125
Section 80EE | 1 | 0.125 | 1 | 0.125
Section 80QQB | 2 | 0.25 | 2 | 0.25
Section 80RRB | 3 | 0.375 | 3 | 0.375
Section 80GGA | 4 | 0.5 | 4 | 0.5
Section 80GGC | 5 | 0.625 | 5 | 0.625
Taxes paid |  | 0 |  | 0
upload 26AS | 4 | 0.5 | 4 | 0.5
challan Details | 4 | 0.5 | 4 | 0.5
Summary and Review | 6 | 0.75 | 6 | 0.75
Services | need clarity
Help center |  | 0 |  | 0
Chat bot | 16 | 2 | 16 | 2
Whats new | 8 | 1 | 8 | 1
Contact Us |  | 0 |  | 0
Submit request | 4 | 0.5 | 4 | 0.5
Terms and Condition | 4 | 0.5 | 4 | 0.5
Legal privacy | 2 | 0.25 | 2 | 0.25
Api Integration |  | 0
API services for Mobile App | 176 | 22
Api integration | 34 | 4.25 | 34 | 4.25
Testing
Developer side testing | 16 | 2 | 16 | 2
Total effort |  | 74.3125 |  | 52.3125

## Sheet1
Admin Functions
User Management | Admin Dashboard(What/) | langauage Translation
Plan & Price Management (with limitations)
Request additional information from client
Refer friend by email
Promo Code management (Issue and consume)
Help Centre (context sensitive help)
Manage Questions
Refer friend
Reports
Usersise Reports
B2B reports
Taxbreeze product (PWC) Reports
Social Media Integration
CMS (Update Website content) with limitations : only content updates
Upgrade plan
Status Updates (From backend)
Document Archival
Advanced Search (Tax documentrs + Site search)
Security
Multifactor Authentication
Advanced password security(MD5, Salting, One-way algorithms, SCRYPT and PBKDF2)
Query parameterization (SQL Injection)
Contextual output encoding XSS defense (JS injection, output encoding/escaping)
Loyalty Programs
Prefill with PAN
Email &SMS
save data while clicking "Back" button: Navigation
Change tax filing plan before payment
form-16 upload (Basic)
repush failed orders
other Batch Jobs
Advanced logging and auditing
Prior Year XML
Foreign income and assets validation : Premium plan