## Android & iOS
Taxbreeze
Modules | Hours | Days | Hours | Days |  |  |  | Days | Total
| Android |  | iOS |  |  | PM | 1 | 2.6313 | 2.6313
Ui Design | [5 empty] | Designer | 1.5 | 13.1667 | 19.75
UI/UX (15 page layout only) |  | 10 |  |  |  | Developer | 1.5 | 21.7083 | 32.5625
Page Design | 158 | 19.75 | 158 | 19.75 |  | QA | 1 | 7.8937 | 7.8937
[7 empty] | Total |  | 62.8375
Development |  |  |  |  | UI/UX |  | 10
Basic Setup | 8 | 1 | 8 | 1 | Andorid | Delivery Time | 42.7687
Splash Screen | 1 | 0.125 | 1 | 0.125 |  | Total Effort | 62.8375
Login Page | 2 | 0.25 | 2 | 0.25
SignUp page | 4 | 0.5 | 4 | 0.5 | IOS
Eligibility page | 1.5 | 0.1875 | 1.5 | 0.1875
Dash board |  | 0 |  | 0
Tax summey | 2 | 0.25 | 2 | 0.25
challan | 4 | 0.5 | 4 | 0.5
upload docments from phone | 4 | 0.5 | 4 | 0.5
filter | 1 | 0.125 | 1 | 0.125
Start Tax return |  | 0 |  | 0
Finantial year selection | 1 | 0.125 | 1 | 0.125
Package Selection | 8 | 1 | 8 | 1
Selection Prefill with XML data /Prefill with PAN data | 3 | 0.375 | 3 | 0.375
Personal details
Personal information | 6 |  | 6
Address | 4 | 0.5 | 4 | 0.5
Bank details |  | 0 |  | 0
Primary Bank Account | 2 | 0.25 | 2 | 0.25
All other bank Accounts | 4 | 0.5 | 4 | 0.5
Asset and Liability |  | 0 |  | 0
immovabile assert | 6 | 0.75 | 6 | 0.75
movabile Asset | 3 | 0.375 | 3 | 0.375
Association of persons | 6 | 0.75 | 6 | 0.75
Foreign Assets | 3 | 0.375 | 3 | 0.375
Salary |  | 0 |  | 0
Upload | 4 | 0.5 | 4 | 0.5
income from salery | 2 | 0.25 | 2 | 0.25
TDS for salery | 2 | 0.25 | 2 | 0.25
other income
Upload | 1 | 0.125 | 1 | 0.125
interest income | 1 | 0.125 | 1 | 0.125
other income | 1 | 0.125 | 1 | 0.125
Exempt income | 2 | 0.25 | 2 | 0.25
Agriculture income | 2 | 0.25 | 2 | 0.25
Dependent income | 2 | 0.25 | 2 | 0.25
PF withdrawal income | 2 | 0.25 | 2 | 0.25
House property
HOuse Address | 1 | 0.125 | 1 | 0.125
interest paid | 6 | 0.75 | 6 | 0.75
property ownership | 6 | 0.75 | 6 | 0.75
Rentel property |  | 0 |  | 0
Prperty address | 6 | 0.75 | 6 | 0.75
income from renal property | 6 | 0.75 | 6 | 0.75
interest paid | 4 | 0.5 | 4 | 0.5
property ownership | 4 | 0.5 | 4 | 0.5
unrealized Rent | 4 | 0.5 | 4 | 0.5
Capital Gain | 4 | 0.5 | 4 | 0.5
Section 80 |  | 0 |  | 0
upload | 2 | 0.25 | 2 | 0.25
section 80c | 2 | 0.25 | 2 | 0.25
section 80D | 2 | 0.25 | 2 | 0.25
section 80TTA | 1 | 0.125 | 1 | 0.125
section 80G | 6 | 0.75 | 6 | 0.75
more deductions
section 80CCG | 1 | 0.125 | 1 | 0.125
section 80E | 1 | 0.125 | 1 | 0.125
section 80CCC | 1 | 0.125 | 1 | 0.125
section 80CCD(1),(1B)&(2) | 2 | 0.25 | 2 | 0.25
Section 80GG | 1 | 0.125 | 1 | 0.125
Section 80DDB | 1 | 0.125 | 1 | 0.125
Section 80EE | 1 | 0.125 | 1 | 0.125
Section 80QQB | 2 | 0.25 | 2 | 0.25
Section 80RRB | 3 | 0.375 | 3 | 0.375
Section 80GGA | 4 | 0.5 | 4 | 0.5
Section 80GGC | 5 | 0.625 | 5 | 0.625
Taxes paid |  | 0 |  | 0
upload 26AS | 4 | 0.5 | 4 | 0.5
challan Details | 4 | 0.5 | 4 | 0.5
Summary and Review | 6 | 0.75 | 6 | 0.75
Services | need clarity
Help center |  | 0 |  | 0
Chat bot | 16 | 2 | 16 | 2
Whats new | 8 | 1 | 8 | 1
Contact Us |  | 0 |  | 0
Submit request | 4 | 0.5 | 4 | 0.5
Terms and Condition | 4 | 0.5 | 4 | 0.5
Legal privacy | 2 | 0.25 | 2 | 0.25
Api Integration
Api integration | 34 | 4.25 | 34 | 4.25
Testing
Developer side testing | 16 | 2 | 16 | 2
Total effort |  | 62.3125 |  | 52.3125