## Web Admin
| PWC Phase 2 |  | 15/05/2018
Tuesday
| Initiation | Hours | Days | Admin
| Business Analysis | 32 | 4 | Resource | No | Man Days | Total Effort
| Project Management | 27.8 | 3.475 | Designer | 1 | 4 | 4
| UI/UX | 32 | 4 | Sr Developer | 1 | 15 | 15 | 34.75 | 35
| Documentation | 8 | 1 | Jr Developer | 1 | 20 | 20
| Development |  |  | PM | 1 | 3.475 | 3.475
| Admin |  |  | BA | 1 | 4 | 4
| User Management with roles & entitlements | 16 | 2 | Tech writer | 1 | 1 | 1
| Billing, Invoicing, Transaction Summary (End user transactions) | 24 | 3 | QA | 2 | 5.2125 | 10.425
| End user Listing: Year wise user management screen | 8 | 1 | Total |  |  | 57.9
| Unlock User | 6 | 0.75 | Delivery days | 29.2125
| Manage Corporate Clients | 0 | 0 | Total Effort | 57.9 | (+1 Day deployment)
| Notifications | 0 | 0
| Plan Management | 16 | 2
| Price Management: Pricing configuration | 16 | 2 | Admin | 361296
| Help Centre Content (https://www.hrblock.com/support/) Management : CMS includes Services updates | 0 | 0
| Ip Management w.r.t corporate clients | 8 | 1 | Japanese Language
| Video Management: Change videos displayed on web page | 12 | 1.5 | Resource | No | Man Days | Effort
| Dashboard Updates | 8 | 1 | Jr. Developer | 1 | 39 | 39
| Resubmission of Returns | 24 | 3
| Trigger from Admin console |  |  | Delivery Days | 39
| Resubmit Documents (end User) |  |  |  | 243360
| Notification on end user Dashboard |  |  |  | 604656
Repush Failed tax filings (failed due to time out or some other technical glitches)
| Revise Returns | 24 | 3
Revise Data
Maintain history of updated Data
| Data Gathering based on Plan Selection | 32 | 4
Based on plan selection, select wizard
| Plan Upgrade | 32 | 4
Change the selected plan
Plan Upgrade Reccomendation
| Master Data Management | 16 | 2
IFSC Code, Bank Name, Investment Category
Account type, Pin Code, Employer Type, Tax Rate, City, State
Qualifying Percentage, Deduction Age, Financial Year, Tax Filing Status
Plan Types, Promo Codes, Service Types
| Notification Management : Notification on new changes via Email | 20 | 2.5
After e-filing, Query response email, Email link to feedback form
Reminder email for review, Email after review (Tax processing)
Missing Info Email, Reminder for missing info, Disclaimer for non-response
| Advanced Logging & Auditing for Security | 16 | 2
User Events
System Events
Admin Events
Error logs
| Multifactor Authentication | 0 | 0
OTP (Phone + Email )
Captcha
| QA + UAT | 83.4 | 10.425
| Deployment | 12 | 1.5
| Total | 473.2 | 59.15 | 312
| Japanese Language integration | 312 | 39
Create Resource File (Global And Local Res. files)
Create Multi language Routes and Route handling mechanism (includes SEO)
Activate Culture & Upgrade content, labels and form values
Total # of pages to modify 78 (@4hrs/page)
Admin
1 | User Management | 8 | 1
2 | Price Management | 0 | 0
3 | Plan Management | 12 | 1.5
4 | Refer friend | 4 | 0.5
5 | Promo Code | 8 | 1
6 | Services | 8 | 1
| Pricing | 0 | 0
1 | Help Centre | 16 | 2
2 | Contact | 4 | 0.5
3 | Manage Questions | 32 | 4

## Japanese
Japanese Language integration | 312 | 39
Create Resource File (Global And Local Res. files)
Create Multi language Routes and Route handling mechanism (includes SEO)
Activate Culture & Upgrade content, labels and form values
Total # of pages to modify 78 (@4hrs/page)

## API
Modules | Man Hour | Days
PM | 18 | 2.25
Login (with two factor authentication) | 8 | 1
Forgot Password | 4 | 0.5
Reset Password | 2 | 0.25
Change Password | 2 | 0.25
Assessment Year | 2 | 0.25
Plan Selection | 12 | 1.5
XML Upload | 6 | 0.75
Tax Filing |  | 0
Personal Details | 20 | 2.5
Income Sources | 40 | 5
Deductions | 32 | 4
Taxes Paid | 12 | 1.5
Summary & Review | 8 | 1
Payment | 12 | 1.5
Dashboard | 20 | 2.5
Testing | 54 | 6.75
Total | 252 | 31.5
0
Development | 180 | 22.5
QA | 54 | 6.75
PM | 18 | 2.25
BA | 8 | 1
Total | 260 | 32.5

## Mobile App
Taxbreeze Mobile Estimate
Modules | Hours | Days | Hours | Days |  | Resources |  | Days | Total
| Android |  | iOS |  |  | PM | 1 | 3.5312 | 3.5312
Ui Design | [5 empty] | Designer | 1.5 | 10 | 15
UI/UX (15 page layout only) | 80 | 10 |  |  |  | Developer | 1.5 | 30.0417 | 45.0625
Page Design | 162 | 20.25 | 162 | 20.25 |  | QA | 1 | 15.8906 | 15.8906
[7 empty] | Total |  | 79.4844
Development |  |  |  |  | UI/UX |  | 10
Basic Setup | 3.5 | 0.4375 | 8 | 1 | Andorid | Delivery Time | 55.9323
Splash Screen | 1 | 0.125 | 1 | 0.125 |  | Total Effort | 79.4844
Login Page | 2 | 0.25 | 2 | 0.25
SignUp page | 1 | 0.125 | 4 | 0.5 | IOS
Eligibility page | 1.5 | 0.1875 | 1.5 | 0.1875 |  | Resources | # | Days | Total
Dash board |  | 0 |  | 0 |  | PM | 1 | 8.4125 | 8.4125
Tax summary | 2 | 0.25 | 2 | 0.25 |  | UI/UX | 1 | 10 | 10
challan | 3.5 | 0.4375 | 4 | 0.5 |  | IOS Developer | 1 | 65.3125 | 65.3125
Show uploaded docments | 3.5 | 0.4375 | 4 | 0.5 |  | Android Developer | 1 | 57 | 57
filter | 1 | 0.125 | 1 | 0.125 |  | QA IOS | 1 | 29.3906 | 29.3906 | 235.125
Show ITR related docs | 3.5 | 0.4375 | 4 | 0.5 |  | QA Android | 1 | 25.65 | 25.65
Approve | 2 | 0.25 | 2 | 0.25 |  | BA | 1 | 3 | 3
Notification | 2 | 0.25 | 2 | 0.25 |  | Total |  |  | 198.7656
Yearly Summary | 2 | 0.25 | 2 | 0.25
Start Tax return |  | 0 |  | 0
Finantial year selection | 1 | 0.125 | 1 | 0.125
Package Selection | 6.5 | 0.8125 | 8 | 1 |  | Total IOS Days | 105.4094
Selection Prefill with XML data /Prefill with PAN data | 5 | 0.625 | 12 | 1.5 |  | Total Android | 105.4094
Personal details
Personal information | 5 |  | 6
Address | 4 | 0.5 | 4 | 0.5
Residential Details (Questions based) | 6.5 | 0.8125 | 8 | 1
Bank details |  | 0 |  | 0
Primary Bank Account | 2 | 0.25 | 2 | 0.25
All other bank Accounts | 5.5 | 0.6875 | 6 | 0.75
Asset and Liability |  | 0 |  | 0
immovabile asset | 5.5 | 0.6875 | 8 | 1
movable Asset | 5.5 | 0.6875 | 6 | 0.75
Foreign Assets | 5.5 | 0.6875 | 6 | 0.75
Salary |  | 0 |  | 0
Upload | 5.5 | 0.6875 | 8 | 1
income from salary | 3 | 0.375 | 4 | 0.5
other income
Upload | 1 | 0.125 | 2 | 0.25
interest income | 1 | 0.125 | 1 | 0.125
other income | 1 | 0.125 | 1 | 0.125
Exempt income | 2 | 0.25 | 2 | 0.25
Agriculture income | 2 | 0.25 | 2 | 0.25
Dependent income | 4 | 0.5 | 4 | 0.5
PF withdrawal income | 2 | 0.25 | 2 | 0.25
House property
Upload | 1 | 0.125 | 1 | 0.125
Property Address | 4 | 0.5 | 4 | 0.5
interest paid | 6 | 0.75 | 6 | 0.75
property ownership | 8 | 1 | 12 | 1.5
income from rental property | 5 | 0.625 | 6 | 0.75
unrealized Rent | 4 | 0.5 | 4 | 0.5
Capital Gain | 4 | 0.5 | 4 | 0.5
Section 80 |  | 0 |  | 0
upload | 1 | 0.125 | 1 | 0.125
section 80c | 4 | 0.5 | 4 | 0.5
section 80D | 2 | 0.25 | 2 | 0.25
section 80TTA | 1 | 0.125 | 1 | 0.125
section 80G | 5 | 0.625 | 6 | 0.75
more deductions
section 80CCG | 1 | 0.125 | 1 | 0.125
section 80E | 1 | 0.125 | 1 | 0.125
section 80CCC | 1 | 0.125 | 1 | 0.125
section 80CCD(1),(1B)&(2) | 2 | 0.25 | 2 | 0.25
Section 80GG | 1 | 0.125 | 1 | 0.125
Section 80DDB | 1 | 0.125 | 1 | 0.125
Section 80EE | 1 | 0.125 | 1 | 0.125
Section 80QQB | 2 | 0.25 | 2 | 0.25
Section 80RRB | 3 | 0.375 | 3 | 0.375
Section 80GGA | 4 | 0.5 | 4 | 0.5
Section 80GGC | 4 | 0.5 | 5 | 0.625
Section 80DD | 2 | 0.25 | 2 | 0.25
Section 80U | 1 | 0.125 | 1 | 0.125
Taxes paid |  | 0 |  | 0
upload 26AS | 2 | 0.25 | 2 | 0.25
challan Details | 4 | 0.5 | 4 | 0.5
Summary and Review | 6 | 0.75 | 6 | 0.75
PDF Report | 6 | 0.75 | 8 | 1
Payment | 6 | 0.75 | 12 | 1.5
Help center |  | 0 |  | 0
Chat bot | 30 | 3.75 | 32 | 4
Whats new | 4 | 0.5 | 4 | 0.5
Contact Us |  | 0 |  | 0
Submit request | 6 | 0.75 | 8 | 1
Terms and Condition | 1 | 0.125 | 4 | 0.5
Legal privacy | 1 | 0.125 | 2 | 0.25
Support for Tab & iPad | 20 | 2.5 | 20 | 2.5
Api Integration |  | 0
Api integration | 34 | 4.25 | 34 | 4.25
Testing
Developer side testing | 8 | 1 | 24 | 3
Total effort |  | 57 |  | 65.3125