## Summary
Note on S15: Shibu-Verbat: Without Commission, Contingeny 15%
Note on T15: Shibu-Verbat: With Commision of 6%

## Web Api
Modules | Man Hour | Days
PM | 18 | 2.25
Login (with two factor authentication) | 8 | 1
Forgot Password | 4 | 0.5
Reset Password | 2 | 0.25
Change Password | 2 | 0.25
Assessment Year | 2 | 0.25
Plan Selection | 12 | 1.5
XML Upload | 6 | 0.75
Tax Filing |  | 0
Personal Details | 20 | 2.5
Income Sources | 40 | 5
Deductions | 32 | 4
Taxes Paid | 12 | 1.5
Summary & Review | 8 | 1
Payment | 12 | 1.5
Dashboard | 20 | 2.5
Testing | 54 | 6.75 | 12
Total | 252 | 31.5
0
Development | 180 | 22.5
QA | 54 | 6.75
PM | 18 | 2.25
BA | 8 | 1
Total | 260 | 32.5

## Mobile App - Android & iOS
Taxbreeze Mobile Estimate
Modules | Hours | Days | Hours | Days |  | Resources |  | Days | Total
| Android |  | iOS |  |  | PM | 1 | 3.5312 | 3.5312
Ui Design | [5 empty] | Designer | 1.5 | 10 | 15
UI/UX (15 page layout only) | 80 | 10 |  |  |  | Developer | 1.5 | 30.0417 | 45.0625
Page Design | 162 | 20.25 | 162 | 20.25 |  | QA | 1 | 15.8906 | 15.8906
[7 empty] | Total |  | 79.4844
Development |  |  |  |  | UI/UX |  | 10
Basic Setup | 3.5 | 0.4375 | 8 | 1 | Andorid | Delivery Time | 55.9323
Splash Screen | 1 | 0.125 | 1 | 0.125 |  | Total Effort | 79.4844
Login Page | 2 | 0.25 | 2 | 0.25
SignUp page | 1 | 0.125 | 4 | 0.5 | IOS
Eligibility page | 1.5 | 0.1875 | 1.5 | 0.1875 |  | Resources | # | Days | Total
Dash board |  | 0 |  | 0 |  | PM | 1 | 8.4125 | 8.4125
Tax summary | 2 | 0.25 | 2 | 0.25 |  | UI/UX | 1 | 10 | 10
challan | 3.5 | 0.4375 | 4 | 0.5 |  | IOS Developer | 1 | 65.3125 | 65.3125
Show uploaded docments | 3.5 | 0.4375 | 4 | 0.5 |  | Android Developer | 1 | 57 | 57
filter | 1 | 0.125 | 1 | 0.125 |  | QA IOS | 1 | 29.3906 | 29.3906 | 235.125
Show ITR related docs | 3.5 | 0.4375 | 4 | 0.5 |  | QA Android | 1 | 25.65 | 25.65
Approve | 2 | 0.25 | 2 | 0.25 |  | BA | 1 | 3 | 3
Notification | 2 | 0.25 | 2 | 0.25 |  | Total |  |  | 198.7656
Yearly Summary | 2 | 0.25 | 2 | 0.25
Start Tax return |  | 0 |  | 0
Finantial year selection | 1 | 0.125 | 1 | 0.125
Package Selection | 6.5 | 0.8125 | 8 | 1 |  | Total IOS Days | 105.4094
Selection Prefill with XML data /Prefill with PAN data | 5 | 0.625 | 12 | 1.5 |  | Total Android | 105.4094
Personal details
Personal information | 5 |  | 6
Address | 4 | 0.5 | 4 | 0.5
Residential Details (Questions based) | 6.5 | 0.8125 | 8 | 1
Bank details |  | 0 |  | 0
Primary Bank Account | 2 | 0.25 | 2 | 0.25
All other bank Accounts | 5.5 | 0.6875 | 6 | 0.75
Asset and Liability |  | 0 |  | 0
immovabile asset | 5.5 | 0.6875 | 8 | 1
movable Asset | 5.5 | 0.6875 | 6 | 0.75
Foreign Assets | 5.5 | 0.6875 | 6 | 0.75
Salary |  | 0 |  | 0
Upload | 5.5 | 0.6875 | 8 | 1
income from salary | 3 | 0.375 | 4 | 0.5
other income
Upload | 1 | 0.125 | 2 | 0.25
interest income | 1 | 0.125 | 1 | 0.125
other income | 1 | 0.125 | 1 | 0.125
Exempt income | 2 | 0.25 | 2 | 0.25
Agriculture income | 2 | 0.25 | 2 | 0.25
Dependent income | 4 | 0.5 | 4 | 0.5
PF withdrawal income | 2 | 0.25 | 2 | 0.25
House property
Upload | 1 | 0.125 | 1 | 0.125
Property Address | 4 | 0.5 | 4 | 0.5
interest paid | 6 | 0.75 | 6 | 0.75
property ownership | 8 | 1 | 12 | 1.5
income from rental property | 5 | 0.625 | 6 | 0.75
unrealized Rent | 4 | 0.5 | 4 | 0.5
Capital Gain | 4 | 0.5 | 4 | 0.5
Section 80 |  | 0 |  | 0
upload | 1 | 0.125 | 1 | 0.125
section 80c | 4 | 0.5 | 4 | 0.5
section 80D | 2 | 0.25 | 2 | 0.25
section 80TTA | 1 | 0.125 | 1 | 0.125
section 80G | 5 | 0.625 | 6 | 0.75
more deductions
section 80CCG | 1 | 0.125 | 1 | 0.125
section 80E | 1 | 0.125 | 1 | 0.125
section 80CCC | 1 | 0.125 | 1 | 0.125
section 80CCD(1),(1B)&(2) | 2 | 0.25 | 2 | 0.25
Section 80GG | 1 | 0.125 | 1 | 0.125
Section 80DDB | 1 | 0.125 | 1 | 0.125
Section 80EE | 1 | 0.125 | 1 | 0.125
Section 80QQB | 2 | 0.25 | 2 | 0.25
Section 80RRB | 3 | 0.375 | 3 | 0.375
Section 80GGA | 4 | 0.5 | 4 | 0.5
Section 80GGC | 4 | 0.5 | 5 | 0.625
Section 80DD | 2 | 0.25 | 2 | 0.25
Section 80U | 1 | 0.125 | 1 | 0.125
Taxes paid |  | 0 |  | 0
upload 26AS | 2 | 0.25 | 2 | 0.25
challan Details | 4 | 0.5 | 4 | 0.5
Summary and Review | 6 | 0.75 | 6 | 0.75
PDF Report | 6 | 0.75 | 8 | 1
Payment | 6 | 0.75 | 12 | 1.5
Help center |  | 0 |  | 0
Chat bot | 30 | 3.75 | 32 | 4
Whats new | 4 | 0.5 | 4 | 0.5
Contact Us |  | 0 |  | 0
Submit request | 6 | 0.75 | 8 | 1
Terms and Condition | 1 | 0.125 | 4 | 0.5
Legal privacy | 1 | 0.125 | 2 | 0.25
Support for Tab & iPad | 20 | 2.5 | 20 | 2.5
Api Integration |  | 0
Api integration | 34 | 4.25 | 34 | 4.25
Testing
Developer side testing | 8 | 1 | 24 | 3
Total effort |  | 57 |  | 65.3125

## Call
QA Need time |  |  | UI DESIGN for ioS and Android shud have different designs
iOS testing in different devices |  |  | Coding need to be done seperately for Android & iOS
iPad mini | 11.4.1
iPhone 5s, 6
Android | XML
Samasung tab | Lollypop
Pixel Phone | Oreo
Alcatel | Nugget
Moto G | MarshMellow
Total Man Days | 292
QA | 70 | 25% of the total
Dev (ios/Andriod) | 156 | 54% of the total - | 12 DEVICES & 6 OS versions
UI-UX | 10 | 3.5%
Web API+API QA | 35 | 11%