## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Software Development | 71 days | October 15, 2018 8:00 AM | January 15, 2019 5:00 PM |  | 0
1 | Yes | Auto Scheduled | Scope | 1.5 days | October 15, 2018 8:00 AM | October 16, 2018 12:00 PM |  | 1
2 | Yes | Auto Scheduled | Determine project scope | 4 hrs | October 15, 2018 8:00 AM | October 15, 2018 12:00 PM |  | 2
3 | Yes | Auto Scheduled | Secure core resources | 1 day | October 15, 2018 1:00 PM | October 16, 2018 12:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Scope complete | 0 days | October 16, 2018 12:00 PM | October 16, 2018 12:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Analysis/Software Requirements | 9 days | October 18, 2018 8:00 AM | October 29, 2018 5:00 PM |  | 1
6 | Yes | Auto Scheduled | Draft SRS | 3 days | October 18, 2018 8:00 AM | October 20, 2018 5:00 PM | 4 | 2
7 | Yes | Auto Scheduled | Review SRS (PWC + Verbat Meet up) | 3 days | October 22, 2018 8:00 AM | October 24, 2018 5:00 PM | 6 | 2
8 | Yes | Auto Scheduled | Incorporate feedback on SRS | 2 days | October 25, 2018 8:00 AM | October 26, 2018 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Update delivery Schedule | 1 day | October 29, 2018 8:00 AM | October 29, 2018 5:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Obtain approvals to proceed | 8 hrs | October 29, 2018 8:00 AM | October 29, 2018 5:00 PM | 8 | 2
11 | Yes | Auto Scheduled | Analysis complete | 0 days | October 29, 2018 5:00 PM | October 29, 2018 5:00 PM | 10 | 2
12 | Yes | Auto Scheduled | Design | 7 days | October 30, 2018 8:00 AM | November 6, 2018 5:00 PM |  | 1
13 | Yes | Auto Scheduled | Develop prototype | 5 days | October 30, 2018 8:00 AM | November 3, 2018 5:00 PM | 11 | 2
14 | Yes | Auto Scheduled | Final approve of SRS and Review prototype | 1 day | October 30, 2018 8:00 AM | October 30, 2018 5:00 PM | 11 | 2
15 | Yes | Auto Scheduled | Incorporate feedback on prototype | 2 days | November 5, 2018 8:00 AM | November 6, 2018 5:00 PM | 13 | 2
16 | Yes | Auto Scheduled | Database Design | 2 days | October 31, 2018 8:00 AM | November 1, 2018 5:00 PM | 14 | 2
17 | Yes | Auto Scheduled | Obtain approval to proceed | 4 hrs | November 2, 2018 8:00 AM | November 2, 2018 12:00 PM | 16 | 2
18 | Yes | Auto Scheduled | Design complete | 0 days | November 2, 2018 12:00 PM | November 2, 2018 12:00 PM | 17 | 2
19 | Yes | Auto Scheduled | Development | 66 days | October 15, 2018 8:00 AM | January 8, 2019 5:00 PM |  | 1
20 | Yes | Auto Scheduled | Web Admin | 30.5 days | November 2, 2018 1:00 PM | December 12, 2018 5:00 PM | 18 | 2
21 | Yes | Auto Scheduled | Confirm Database Design | 8 hrs | November 2, 2018 1:00 PM | November 3, 2018 12:00 PM |  | 3
22 | Yes | Auto Scheduled | Master Data Management | 3 days | November 3, 2018 1:00 PM | November 7, 2018 12:00 PM | 21 | 3
23 | Yes | Auto Scheduled | User management with roles & entitlements | 2 days | November 3, 2018 1:00 PM | November 6, 2018 12:00 PM | 21 | 3
24 | Yes | Auto Scheduled | Manage Corp Clients | 1 day | November 6, 2018 1:00 PM | November 7, 2018 12:00 PM | 23 | 3
25 | Yes | Auto Scheduled | Price Management : Price configuration | 2 days | November 7, 2018 1:00 PM | November 9, 2018 12:00 PM | 22 | 3
26 | Yes | Auto Scheduled | Plan Management | 3 days | November 7, 2018 1:00 PM | November 12, 2018 12:00 PM | 24 | 3
27 | Yes | Auto Scheduled | IP Management for corporate clients | 2 days | November 9, 2018 1:00 PM | November 13, 2018 12:00 PM | 25 | 3
28 | Yes | Auto Scheduled | Help Center | 2 days | November 12, 2018 1:00 PM | November 14, 2018 12:00 PM | 26 | 3
29 | Yes | Auto Scheduled | Notification Management | 3 days | November 13, 2018 1:00 PM | November 16, 2018 12:00 PM | 27 | 3
30 | Yes | Auto Scheduled | Video Management | 2 days | November 14, 2018 1:00 PM | November 16, 2018 12:00 PM | 28 | 3
31 | Yes | Auto Scheduled | Plan Upgrade (change selected plan) | 4 days | November 16, 2018 1:00 PM | November 21, 2018 12:00 PM | 29 | 3
32 | Yes | Auto Scheduled | Data gathering based on plan selection (Upgrade Wizard) | 4 days | November 16, 2018 1:00 PM | November 21, 2018 12:00 PM | 30 | 3
33 | Yes | Auto Scheduled | Resubmit returns | 3 days | November 21, 2018 1:00 PM | November 26, 2018 12:00 PM | 31 | 3
34 | Yes | Auto Scheduled | Revise returns | 3 days | November 21, 2018 1:00 PM | November 26, 2018 12:00 PM | 32 | 3
35 | Yes | Auto Scheduled | Billing, Invoicing, End userTx summary | 3 days | November 26, 2018 1:00 PM | November 29, 2018 12:00 PM | 34 | 3
36 | Yes | Auto Scheduled | End user Listing: Year wise user management screen | 2 days | November 26, 2018 1:00 PM | November 28, 2018 12:00 PM | 33 | 3
37 | Yes | Auto Scheduled | Unlock User | 1 day | November 28, 2018 1:00 PM | November 29, 2018 12:00 PM | 36 | 3
38 | Yes | Auto Scheduled | Dashboard Updates | 3 days | November 30, 2018 8:00 AM | December 4, 2018 5:00 PM | 35 | 3
39 | Yes | Auto Scheduled | Logging, Auditing, event logs, Security, Brush up | 3 days | November 30, 2018 8:00 AM | December 4, 2018 5:00 PM | 37 | 3
40 | Yes | Auto Scheduled | API Integration, Japanese, Misc | 6 days | December 5, 2018 8:00 AM | December 12, 2018 5:00 PM | 37 | 3
41 | Yes | Auto Scheduled | Development complete | 0 days | December 12, 2018 5:00 PM | December 12, 2018 5:00 PM | 40 | 3
42 | Yes | Auto Scheduled | Web API | 25 days | October 22, 2018 8:00 AM | November 21, 2018 5:00 PM |  | 2
43 | Yes | Auto Scheduled | Login Management | 2 days | October 22, 2018 8:00 AM | October 23, 2018 5:00 PM |  | 3
44 | Yes | Auto Scheduled | Assessment year | 1 day | October 24, 2018 8:00 AM | October 24, 2018 5:00 PM | 43 | 3
45 | Yes | Auto Scheduled | Plan selection | 2 days | October 25, 2018 8:00 AM | October 26, 2018 5:00 PM | 44 | 3
46 | Yes | Auto Scheduled | XML Uploads | 2 days | October 29, 2018 8:00 AM | October 30, 2018 5:00 PM | 45 | 3
47 | Yes | Auto Scheduled | Tax filing | 15 days | October 31, 2018 8:00 AM | November 17, 2018 5:00 PM | 46 | 3
48 | Yes | Auto Scheduled | Dashboard Updates | 3 days | November 19, 2018 8:00 AM | November 21, 2018 5:00 PM | 47 | 3
49 | Yes | Auto Scheduled | Development complete | 0 days | November 21, 2018 5:00 PM | November 21, 2018 5:00 PM | 48 | 3
50 | Yes | Auto Scheduled | Japanese Langauge integration | 35 days | November 21, 2018 5:00 PM | January 8, 2019 5:00 PM |  | 2
51 | Yes | Auto Scheduled | Create Resource File | 0 days | November 21, 2018 5:00 PM | November 21, 2018 5:00 PM | 49 | 3
52 | Yes | Auto Scheduled | Create Multi language Routes and Route handling mechanism (includes SEO) | 0 days | November 21, 2018 5:00 PM | November 21, 2018 5:00 PM | 51 | 3
53 | Yes | Auto Scheduled | Activate Culture & Upgrade content, labels and form values | 0 days | November 21, 2018 5:00 PM | November 21, 2018 5:00 PM | 52 | 3
54 | Yes | Auto Scheduled | Total # of pages to modify 78 | 35 days | November 22, 2018 8:00 AM | January 8, 2019 5:00 PM | 53 | 3
55 | Yes | Auto Scheduled | Development complete | 0 days | January 8, 2019 5:00 PM | January 8, 2019 5:00 PM | 54 | 3
56 | Yes | Auto Scheduled | Mobile App | 59 days | October 15, 2018 8:00 AM | December 28, 2018 5:00 PM |  | 2
57 | Yes | Auto Scheduled | SRS | 6 days | October 15, 2018 8:00 AM | October 20, 2018 5:00 PM |  | 3
58 | Yes | Auto Scheduled | Confirm SRS (PWC + Verbat Meet up) | 4 days | October 22, 2018 8:00 AM | October 25, 2018 5:00 PM | 57 | 3
59 | Yes | Auto Scheduled | Wire Frames | 2 days | October 26, 2018 8:00 AM | October 29, 2018 5:00 PM | 58 | 3
60 | Yes | Auto Scheduled | PWC review of wireframes | 5 days | October 30, 2018 8:00 AM | November 3, 2018 5:00 PM | 59 | 3
61 | Yes | Auto Scheduled | Prototype and Designing | 12 days | November 7, 2018 8:00 AM | November 21, 2018 5:00 PM | 60 | 3
62 | Yes | Auto Scheduled | Splash Screen, Login etc. | 2 days | October 30, 2018 8:00 AM | October 31, 2018 5:00 PM | 59 | 3
63 | Yes | Auto Scheduled | Dashboard(Tax Summary, Chellan, Filter, Uploaded docs, ITR related docs, Approve, Notifications, Yearly Summary) | 2 days | November 1, 2018 8:00 AM | November 2, 2018 5:00 PM | 62 | 3
64 | Yes | Auto Scheduled | Start Tax Return (Year / Package selection, Prefill XML / PAN) | 2 days | November 3, 2018 8:00 AM | November 5, 2018 5:00 PM | 63 | 3
65 | Yes | Auto Scheduled | Personal details | 2 days | November 6, 2018 8:00 AM | November 7, 2018 5:00 PM | 64 | 3
66 | Yes | Auto Scheduled | Bank Details | 2 days | November 8, 2018 8:00 AM | November 9, 2018 5:00 PM | 65 | 3
67 | Yes | Auto Scheduled | Assets & Liabelities | 3 days | November 12, 2018 8:00 AM | November 14, 2018 5:00 PM | 66 | 3
68 | Yes | Auto Scheduled | Salary | 2 days | November 15, 2018 8:00 AM | November 16, 2018 5:00 PM | 67 | 3
69 | Yes | Auto Scheduled | Other Income | 4 days | November 17, 2018 8:00 AM | November 21, 2018 5:00 PM | 68 | 3
70 | Yes | Auto Scheduled | House property | 4 days | November 22, 2018 8:00 AM | November 27, 2018 5:00 PM | 69 | 3
71 | Yes | Auto Scheduled | Section 80 | 3 days | November 28, 2018 8:00 AM | November 30, 2018 5:00 PM | 70 | 3
72 | Yes | Auto Scheduled | More Deductions (80E, 80CCC etc.) | 4 days | December 3, 2018 8:00 AM | December 6, 2018 5:00 PM | 71 | 3
73 | Yes | Auto Scheduled | Taxes paid (Upload 26AS, Challan Details, Summary & review, PDF report, Payment) | 4 days | December 7, 2018 8:00 AM | December 12, 2018 5:00 PM | 72 | 3
74 | Yes | Auto Scheduled | Help center (Chat bot, Whats new) | 4 days | December 13, 2018 8:00 AM | December 18, 2018 5:00 PM | 73 | 3
75 | Yes | Auto Scheduled | Static Pages (FAQ, T&C, Privacy, legal, support, Contact) | 4 days | December 19, 2018 8:00 AM | December 22, 2018 5:00 PM | 74 | 3
76 | Yes | Auto Scheduled | API integration | 5 days | December 24, 2018 8:00 AM | December 28, 2018 5:00 PM | 75 | 3
77 | Yes | Auto Scheduled | Testing | 56 days | November 1, 2018 8:00 AM | January 14, 2019 5:00 PM |  | 1
78 | Yes | Auto Scheduled | Web Dev | 8 days | November 1, 2018 8:00 AM | November 9, 2018 5:00 PM |  | 2
79 | Yes | Auto Scheduled | Test scenarios | 4 days | November 1, 2018 8:00 AM | November 5, 2018 5:00 PM | 14 | 3
80 | Yes | Auto Scheduled | Test Cases | 4 days | November 6, 2018 8:00 AM | November 9, 2018 5:00 PM | 79 | 3
81 | Yes | Auto Scheduled | Mobile Dev | 8 days | November 15, 2018 8:00 AM | November 23, 2018 5:00 PM |  | 2
82 | Yes | Auto Scheduled | Test Scenarios | 4 days | November 15, 2018 8:00 AM | November 19, 2018 5:00 PM |  | 3
83 | Yes | Auto Scheduled | Test Cases | 4 days | November 20, 2018 8:00 AM | November 23, 2018 5:00 PM | 82 | 3
84 | Yes | Auto Scheduled | Functional Testing | 39 days | November 19, 2018 8:00 AM | January 9, 2019 5:00 PM |  | 2
85 | Yes | Auto Scheduled | Web App | 36 days | November 19, 2018 8:00 AM | January 4, 2019 5:00 PM |  | 3
86 | Yes | Auto Scheduled | Module testing | 20 days | November 19, 2018 8:00 AM | December 14, 2018 5:00 PM | 80 | 4
87 | Yes | Auto Scheduled | Test component modules to product specifications | 3 days | December 18, 2018 8:00 AM | December 20, 2018 5:00 PM | 86 | 4
88 | Yes | Auto Scheduled | Identify anomalies to product specifications | 6 days | December 21, 2018 8:00 AM | December 27, 2018 5:00 PM | 87 | 4
89 | Yes | Auto Scheduled | Modify code | 12 days | December 14, 2018 8:00 AM | December 28, 2018 5:00 PM | 41 | 4
90 | Yes | Auto Scheduled | Re-test modified code | 3 days | January 2, 2019 8:00 AM | January 4, 2019 5:00 PM | 88 | 4
91 | Yes | Auto Scheduled | Functional testing complete | 0 days | January 4, 2019 5:00 PM | January 4, 2019 5:00 PM | 90 | 4
92 | Yes | Auto Scheduled | Mobile App | 29 days | December 3, 2018 8:00 AM | January 9, 2019 5:00 PM |  | 3
93 | Yes | Auto Scheduled | Module Testing | 20 days | December 3, 2018 8:00 AM | December 27, 2018 5:00 PM | 80 | 4
94 | Yes | Auto Scheduled | Test component modules to product specifications | 2 days | December 28, 2018 8:00 AM | December 31, 2018 5:00 PM | 93 | 4
95 | Yes | Auto Scheduled | Identify anomalies to product specifications | 1 day | January 1, 2019 8:00 AM | January 1, 2019 5:00 PM | 94 | 4
96 | Yes | Auto Scheduled | Modify code | 5 days | January 2, 2019 8:00 AM | January 8, 2019 5:00 PM | 95 | 4
97 | Yes | Auto Scheduled | Re-test modified code | 1 day | January 9, 2019 8:00 AM | January 9, 2019 5:00 PM | 96 | 4
98 | Yes | Auto Scheduled | Functional testing complete | 0 days | January 9, 2019 5:00 PM | January 9, 2019 5:00 PM | 97 | 4
99 | Yes | Auto Scheduled | Integration Testing | 6 days | January 7, 2019 8:00 AM | January 14, 2019 5:00 PM |  | 2
100 | Yes | Auto Scheduled | Test module integration | 2 days | January 7, 2019 8:00 AM | January 8, 2019 5:00 PM | 91 | 3
101 | Yes | Auto Scheduled | Identify anomalies to specifications | 1 day | January 9, 2019 8:00 AM | January 9, 2019 5:00 PM | 100 | 3
102 | Yes | Auto Scheduled | Modify code | 2 days | January 10, 2019 8:00 AM | January 11, 2019 5:00 PM | 101 | 3
103 | Yes | Auto Scheduled | Re-test modified code | 1 day | January 14, 2019 8:00 AM | January 14, 2019 5:00 PM | 102 | 3
104 | Yes | Auto Scheduled | Integration testing complete | 0 days | January 14, 2019 5:00 PM | January 14, 2019 5:00 PM | 103 | 3
105 | Yes | Auto Scheduled | Deployment | 1 day | January 14, 2019 5:00 PM | January 15, 2019 5:00 PM |  | 1
106 | Yes | Auto Scheduled | Determine final deployment strategy | 0 days | January 14, 2019 5:00 PM | January 14, 2019 5:00 PM | 104 | 2
107 | Yes | Auto Scheduled | Deploy software | 1 day | January 15, 2019 8:00 AM | January 15, 2019 5:00 PM | 106 | 2
108 | Yes | Auto Scheduled | Deployment complete | 0 days | January 15, 2019 5:00 PM | January 15, 2019 5:00 PM | 107 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Analyst 1 | A | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Developer 1 | D | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Technical Communicators | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0
9 | PWC | P | Work |  |  |  |  | 100% | $0.00/h | 0
10 | UI/UX 1 | U | Work |  |  |  |  | 100% | $0.00/h | 0
11 | Developer 2 | D | Work |  |  |  |  | 100% | $0.00/h | 0
12 | Development Team | D | Work |  |  |  |  | 100% | $0.00/h | 0
13 | Developer 3 | D | Work |  |  |  |  | 100% | $0.00/h | 0
14 | Analyst 2 | A | Work |  |  |  |  | 100% | $0.00/h | 0
15 | UI/UX 2 | U | Work |  |  |  |  | 100% | $0.00/h | 0
16 | UI | U | Work |  |  |  |  | 100% | $0.00/h | 0
17 | Android / IOS Dev 1 | A | Work |  |  |  |  | 100% | $0.00/h | 0
18 | Android / iOS Dev 2 | A | Work |  |  |  |  | 100% | $0.00/h | 0
19 | Android Dev | A | Work |  |  |  |  | 100% | $0.00/h | 0
20 | IOS Dev | I | Work |  |  |  |  | 100% | $0.00/h | 0
21 | QA 1 | Q | Work |  |  |  |  | 100% | $0.00/h | 0
22 | Lead QA | L | Work |  |  |  |  | 100% | $0.00/h | 0
23 | QA 2 | Q | Work |  |  |  |  | 100% | $0.00/h | 0
24 | QA 3 | Q | Work |  |  |  |  | 100% | $0.00/h | 0
25 | QA 4 | Q | Work |  |  |  |  | 100% | $0.00/h | 0
26 | Developer 4 | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Determine project scope | Management | 0 | 4h | 100%
Secure core resources | Project Manager | 0 | 8h | 100%
Draft SRS | Analyst 1 | 0 | 24h | 100%
Review SRS (PWC + Verbat Meet up) | PWC | 0 | 24h | 100%
Review SRS (PWC + Verbat Meet up) | Management | 0 | 24h | 100%
Review SRS (PWC + Verbat Meet up) | Project Manager | 0 | 24h | 100%
Incorporate feedback on SRS | Analyst 1 | 0 | 16h | 100%
Update delivery Schedule | Project Manager | 0 | 8h | 100%
Obtain approvals to proceed | Management | 0 | 8h | 100%
Obtain approvals to proceed | PWC | 0 | 8h | 100%
Develop prototype | UI/UX 1 | 0 | 40h | 100%
Final approve of SRS and Review prototype | PWC | 0 | 8h | 100%
Incorporate feedback on prototype | UI/UX 1 | 0 | 16h | 100%
Database Design | Development Team | 0 | 16h | 100%
Obtain approval to proceed | Management | 0 | 4h | 100%
Obtain approval to proceed | Project Manager | 0 | 4h | 100%
Design complete | Project Manager | 0 | 0h | 100%
Confirm Database Design | Development Team | 0 | 8h | 100%
Master Data Management | Developer 2 | 0 | 24h | 100%
User management with roles & entitlements | Developer 1 | 0 | 16h | 100%
Manage Corp Clients | Developer 1 | 0 | 8h | 100%
Price Management : Price configuration | Developer 2 | 0 | 16h | 100%
Plan Management | Developer 1 | 0 | 24h | 100%
IP Management for corporate clients | Developer 2 | 0 | 16h | 100%
Help Center | Developer 1 | 0 | 16h | 100%
Notification Management | Developer 2 | 0 | 24h | 100%
Video Management | Developer 1 | 0 | 16h | 100%
Plan Upgrade (change selected plan) | Developer 2 | 0 | 32h | 100%
Data gathering based on plan selection (Upgrade Wizard) | Developer 1 | 0 | 32h | 100%
Resubmit returns | Developer 2 | 0 | 24h | 100%
Revise returns | Developer 1 | 0 | 24h | 100%
Billing, Invoicing, End userTx summary | Developer 1 | 0 | 24h | 100%
End user Listing: Year wise user management screen | Developer 2 | 0 | 16h | 100%
Unlock User | Developer 2 | 0 | 8h | 100%
Dashboard Updates | Developer 1 | 0 | 24h | 100%
Logging, Auditing, event logs, Security, Brush up | Developer 2 | 0 | 24h | 100%
API Integration, Japanese, Misc | Developer 1 | 0 | 48h | 100%
API Integration, Japanese, Misc | Developer 2 | 0 | 48h | 100%
Login Management | Developer 3 | 0 | 16h | 100%
Assessment year | Developer 3 | 0 | 8h | 100%
Plan selection | Developer 3 | 0 | 16h | 100%
XML Uploads | Developer 3 | 0 | 16h | 100%
Tax filing | Developer 3 | 0 | 120h | 100%
Dashboard Updates | Developer 3 | 0 | 24h | 100%
Total # of pages to modify 78 | Developer 3 | 0 | 280h | 100%
SRS | Analyst 2 | 0 | 48h | 100%
Confirm SRS (PWC + Verbat Meet up) | Management | 0 | 32h | 100%
Confirm SRS (PWC + Verbat Meet up) | PWC | 0 | 32h | 100%
Wire Frames | UI | 0 | 16h | 100%
PWC review of wireframes | PWC | 0 | 40h | 100%
Prototype and Designing | UI/UX 1 | 0 | 96h | 100%
Splash Screen, Login etc. | Android Dev | 0 | 16h | 100%
Splash Screen, Login etc. | IOS Dev | 0 | 16h | 100%
Dashboard(Tax Summary, Chellan, Filter, Uploaded docs, ITR related docs, Approve, Notifications, Yearly Summary) | Android Dev | 0 | 16h | 100%
Dashboard(Tax Summary, Chellan, Filter, Uploaded docs, ITR related docs, Approve, Notifications, Yearly Summary) | IOS Dev | 0 | 16h | 100%
Start Tax Return (Year / Package selection, Prefill XML / PAN) | Android Dev | 0 | 16h | 100%
Start Tax Return (Year / Package selection, Prefill XML / PAN) | IOS Dev | 0 | 16h | 100%
Personal details | Android Dev | 0 | 16h | 100%
Personal details | IOS Dev | 0 | 16h | 100%
Bank Details | Android Dev | 0 | 16h | 100%
Bank Details | IOS Dev | 0 | 16h | 100%
Assets & Liabelities | Android Dev | 0 | 24h | 100%
Assets & Liabelities | IOS Dev | 0 | 24h | 100%
Salary | Android Dev | 0 | 16h | 100%
Salary | IOS Dev | 0 | 16h | 100%
Other Income | Android Dev | 0 | 32h | 100%
Other Income | IOS Dev | 0 | 32h | 100%
House property | Android Dev | 0 | 32h | 100%
House property | IOS Dev | 0 | 32h | 100%
Section 80 | Android Dev | 0 | 24h | 100%
Section 80 | IOS Dev | 0 | 24h | 100%
More Deductions (80E, 80CCC etc.) | Android Dev | 0 | 32h | 100%
More Deductions (80E, 80CCC etc.) | IOS Dev | 0 | 32h | 100%
Taxes paid (Upload 26AS, Challan Details, Summary & review, PDF report, Payment) | Android Dev | 0 | 32h | 100%
Taxes paid (Upload 26AS, Challan Details, Summary & review, PDF report, Payment) | IOS Dev | 0 | 32h | 100%
Help center (Chat bot, Whats new) | Android Dev | 0 | 32h | 100%
Help center (Chat bot, Whats new) | IOS Dev | 0 | 32h | 100%
Static Pages (FAQ, T&C, Privacy, legal, support, Contact) | Android Dev | 0 | 32h | 100%
Static Pages (FAQ, T&C, Privacy, legal, support, Contact) | IOS Dev | 0 | 32h | 100%
API integration | Android Dev | 0 | 40h | 100%
Test scenarios | Lead QA | 0 | 32h | 100%
Test Cases | Lead QA | 0 | 32h | 100%
Test Scenarios | Lead QA | 0 | 32h | 100%
Test Cases | Lead QA | 0 | 32h | 100%
Module testing | QA 1 | 0 | 160h | 100%
Test component modules to product specifications | QA 1 | 0 | 24h | 100%
Identify anomalies to product specifications | QA 1 | 0 | 48h | 100%
Modify code | Developer 1 | 0 | 96h | 100%
Modify code | Developer 2 | 0 | 96h | 100%
Re-test modified code | QA 1 | 0 | 24h | 100%
Module Testing | QA 3 | 0 | 160h | 100%
Module Testing | QA 4 | 0 | 160h | 100%
Module Testing | QA 2 | 0 | 160h | 100%
Test component modules to product specifications | QA 3 | 0 | 16h | 100%
Test component modules to product specifications | QA 4 | 0 | 16h | 100%
Test component modules to product specifications | QA 2 | 0 | 16h | 100%
Identify anomalies to product specifications | QA 3 | 0 | 8h | 100%
Identify anomalies to product specifications | QA 4 | 0 | 8h | 100%
Identify anomalies to product specifications | QA 2 | 0 | 8h | 100%
Modify code | Android Dev | 0 | 40h | 100%
Modify code | IOS Dev | 0 | 40h | 100%
Re-test modified code | QA 3 | 0 | 8h | 100%
Re-test modified code | QA 4 | 0 | 8h | 100%
Re-test modified code | QA 2 | 0 | 8h | 100%
Test module integration | Testers | 0 | 16h | 100%
Identify anomalies to specifications | Testers | 0 | 8h | 100%
Modify code | Development Team | 0 | 16h | 100%
Re-test modified code | Testers | 0 | 8h | 100%
Determine final deployment strategy | Deployment Team | 0 | 0h | 100%
Deploy software | Deployment Team | 0 | 8h | 100%