## Project Plan
| Name | Start | Finish | Duration
1 | PWC Web Application | 4/5/18 | 5/17/18 | 30.125 days
2 | Initiation | 4/5/18 | 4/11/18 | 5 days
3 | Business analysis | 4/5/18 | 4/5/18 | 0 days
4 | Project Management | 4/5/18 | 4/11/18 | 5 days
5 | Project Documentation (SRS- Scope- WBS etc.) | 4/5/18 | 4/5/18 | 0 days
6 | Prototype Updates | 4/5/18 | 4/11/18 | 5 days
7 | Functional Spec | 4/5/18 | 4/5/18 | 1 day
8 | Development | 4/5/18 | 5/7/18 | 22.875 days
9 | Website | 4/5/18 | 4/11/18 | 5 days
10 | Database Design | 4/5/18 | 4/5/18 | 0.375 days
11 | Authentication- Authorization | 4/5/18 | 4/5/18 | 0.5 days
12 | Logging- Auditing- Exceptions | 4/5/18 | 4/6/18 | 0.5 days
13 | State Management (Reload application state from where the user left off) | 4/6/18 | 4/6/18 | 0.25 days
14 | Database Services | 4/6/18 | 4/6/18 | 0.25 days
15 | Business Layer | 4/6/18 | 4/9/18 | 0.25 days
16 | Login/Registration | 4/9/18 | 4/16/18 | 5 days
17 | Login | 4/9/18 | 4/9/18 | 0.5 days
18 | Social Media Login | 4/9/18 | 4/10/18 | 1 day
19 | Create an account (registration) | 4/10/18 | 4/11/18 | 1 day
20 | Eligibility | 4/11/18 | 4/12/18 | 0.5 days
21 | Forgot password | 4/12/18 | 4/13/18 | 1 day
22 | Change password | 4/13/18 | 4/13/18 | 0.5 days
23 | Logout | 4/13/18 | 4/16/18 | 0.5 days
24 | Basic Details | 4/5/18 | 4/9/18 | 2.5 days
25 | Basic Tax Profile (options) | 4/5/18 | 4/5/18 | 0.5 days
26 | Prefill from PAN # | 4/5/18 | 4/6/18 | 1 day
27 | Prefill from XML | 4/6/18 | 4/9/18 | 1 day
28 | Personal Details | 4/9/18 | 5/7/18 | 20 days
29 | Personal information | 4/9/18 | 4/10/18 | 1 day
30 | Address | 4/10/18 | 4/11/18 | 1 day
31 | Bank Details (Primary & Secondary Bank Accounts) | 4/11/18 | 4/12/18 | 1 day
32 | Assets and Liabilities | 4/16/18 | 4/19/18 | 3 days
33 | Immovable Assets | 4/16/18 | 4/17/18 | 1 day
34 | Movable Assets | 4/17/18 | 4/17/18 | 0.5 days
35 | Assosiation of Persons | 4/17/18 | 4/18/18 | 1 day
36 | Foreign Assets | 4/18/18 | 4/19/18 | 0.5 days
37 | Income Sources | 4/12/18 | 4/24/18 | 7.75 days
38 | Salary (form 16, head salaries, TDS, Doc Upload) | 4/12/18 | 4/13/18 | 1 day
39 | Other Income | 4/13/18 | 4/20/18 | 4.25 days
40 | Doc Upload | 4/13/18 | 4/16/18 | 0.5 days
41 | Interest income | 4/16/18 | 4/16/18 | 0.5 days
42 | Other Income | 4/16/18 | 4/17/18 | 0.5 days
43 | Exempt | 4/17/18 | 4/17/18 | 0.5 days
44 | Agriculture | 4/17/18 | 4/18/18 | 0.5 days
45 | Dependent | 4/18/18 | 4/19/18 | 1 day
46 | PF Withdrawal | 4/19/18 | 4/20/18 | 0.75 days
47 | House & Property | 4/19/18 | 4/20/18 | 1 day
48 | House Address | 4/19/18 | 4/19/18 | 0.375 days
49 | Interest Paid on Housing Loan (Doc Upload) | 4/19/18 | 4/19/18 | 0.375 days
50 | Property Ownership | 4/19/18 | 4/20/18 | 0.25 days
51 | Rental Property | 4/20/18 | 4/24/18 | 2 days
52 | Property Address | 4/20/18 | 4/20/18 | 0.375 days
53 | Income from rental property | 4/20/18 | 4/20/18 | 0.5 days
54 | Interest paid on rental property Upload Doc | 4/23/18 | 4/23/18 | 0.375 days
55 | Unrealized rent | 4/23/18 | 4/23/18 | 0.25 days
56 | Rental Property Ownership | 4/23/18 | 4/24/18 | 0.5 days
57 | Capital Gains | 4/24/18 | 4/24/18 | 0.5 days
58 | Capital Gains (upload multiple documents) | 4/24/18 | 4/24/18 | 0.5 days
59 | Deductions | 4/24/18 | 4/25/18 | 1 day
60 | Section 80 | 4/24/18 | 4/25/18 | 0.5 days
61 | Other deductions | 4/25/18 | 4/25/18 | 0.5 days
62 | Taxes Paid | 4/25/18 | 4/26/18 | 0.5 days
63 | 26 AS | 4/25/18 | 4/25/18 | 0.25 days
64 | Chellan Details | 4/25/18 | 4/26/18 | 0.25 days
65 | Submit to PWC | 4/26/18 | 4/30/18 | 2 days
66 | Update information before submit | 4/26/18 | 4/26/18 | 0.25 days
67 | Preselect Plan | 4/26/18 | 4/26/18 | 0.25 days
68 | Make Payment | 4/26/18 | 4/30/18 | 1.5 days
69 | Dashboard | 4/30/18 | 5/7/18 | 5.75 days
70 | Status Update | 4/30/18 | 4/30/18 | 0.125 days
71 | Tax summary | 4/30/18 | 4/30/18 | 0.125 days
72 | Upgrade Plan | 4/30/18 | 5/1/18 | 1 day
73 | Submit new documentation | 5/1/18 | 5/1/18 | 0.5 days
74 | Download Tax documents | 5/1/18 | 5/2/18 | 0.25 days
75 | Search | 5/2/18 | 5/2/18 | 0.25 days
76 | System Features | 5/2/18 | 5/7/18 | 3.5 days
77 | Document management (Tagging + meta data + Archiving ) | 5/2/18 | 5/3/18 | 1.5 days
78 | SMS & Email | 5/3/18 | 5/4/18 | 0.5 days
79 | API Services | 5/4/18 | 5/7/18 | 1.5 days
80 | Quality Assurance | 4/12/18 | 5/17/18 | 25.125 days
81 | QA-Website | 4/12/18 | 4/13/18 | 2 days
82 | QA-TaxPayer | 5/2/18 | 5/10/18 | 6.5 days
83 | BugFix | 5/2/18 | 5/11/18 | 7 days
84 | QA-Regression | 5/11/18 | 5/15/18 | 2 days
85 | UAT | 5/15/18 | 5/16/18 | 1 day
86 | Deployment | 5/16/18 | 5/17/18 | 1 day