## PWC
| PWC Venue Management App |  | 2018-11-12
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer |  | #REF! | #REF!
| Business Analysis | 40 | 5 | Sr Developer |  |  | 0 | 10 | 0 | 10 | 0
| Project Management | 8 | 1 | Jr Developer |  |  | 0
| Documentation (SRS, FS, Weekly Reports) | 32 | 4 | BA |  | 1 | 0
| Development |  | 0 | TechWriter |  | 5 | 0
| UI design | 40 | 5 | QA |  |  | 0
| Prototyping | 40 | 5 | Total |  | 0 | 0
| Responsive Web Application |  | 0
1 | Master Data Management (Templated and configurable) |  | 0
2 | Floor Plan & Floor Sites |  | 0
3 | IT Facilities |  | 0
4 | Security Facilities |  | 0
5 | House keeping |  | 0
6 | FNB |  | 0
7 | Three tiered approval workflow framework. |  | 0
Floor Plan & Floor Sites
| Data Collection templates for each service |  |  | Total Delivery days | #REF!
User authorization and entitlements linked to approval workflow
8 | Event Booking |  | 0
9 | Lead Generation (Website and emails*1) |  | 0
10 | Capture event facility requirments |  | 0 | Total Effort | 0 | (+1 Day deployment)
11 | Floor area, IT requirments, Security requirments House keeping FNB. Multiple forms that are dynamically generated based on the options being selected |  | 0
Capture client details, event details, Offer period, misc data
12 | Generate documents that capture the requirments listed. Confirmation letter etc |  | 0
13 | Generate MOU to receive approval from the client |  | 0
14 | Workflow for approval process |  | 0
15 | Customer approved MOU |  | 0
Check in and attendee tracking
Email campaigns
Manage invoices
Collect Payments
Online registration and ticketing
16 | Customer web view |  | 0
17 | Customer Login
18 | Floor plans and site details (View and update plan With service specific forms) |  | 0
19 | IT Facilities (View and update plan With service specific forms) |  | 0
20 | Security Facilities (View and update plan With service specific forms) |  | 0
21 | House keeping (View and update plan With service specific forms) |  | 0
22 | FNB (View and update plan With service specific forms) |  | 0
Consumption Sheets
Financial Impact Assesment
Change management
Workflow for change and approvals
Summary and feedback
23 | Integrations |  | 0
24 | Tally integration |  | 0
25 | Mail integration |  | 0
26 | SMS integration |  | 0
27 | Operations |  | 0
28 | Reminders for start operations |  | 0
29 | Assign SPOC for services |  | 0
30 | SPOC creates tasks and activity schedules |  | 0
31 | Assign responsibilities |  | 0
32 | Calendar integrations |  | 0
33 | Sign off on project plans from the client |  | 0
34 | Data collection wizard for each service (5 services identified) |  | 0
Generate data sheets with list of requirments
Vendor management
Create Vendor service categories
Create Vendor selection criteria
Create Bid Document (RFI, RFP, RFQ)
Risk Assessment & Evaluate offers
Contract negotiation
Onboarding
Monitoring performace and mitigating risks
Managing Vendor relationship
Store management
Receipt of incoming materials
Supervision of unloading of materials and tallying of materials
Checking for damages or shortages and preparation of the report
Filling of ‘goods inward’, ‘day book’, or ‘daily collection’ register
Completion of vendors consignment note (challan)
Making arrangement for inspection and getting the inspection completed
Preparation of ‘goods receipt note’ (GRN)
Preparation of ‘goods rejection memo’ (in case of rejection of materials)
Sending of materials to the respective stores
Sending of the relevant documents to the respective departments
Ensuring all storage and material handling facilities are in proper working order
Ensuring good housekeeping and cleanliness in the storage space
Checking, counting and tallying of materials before issue
Making prompt entries in ‘Bin card’ or stock card
Ensuring correct documentation of material receipts and material issues
Ensuring safe and proper handling of materials so as not to damage them
Ensuring proper record keeping and correct accounting of materials
Ensuring regular stock verification
Ensuring that rules and regulations relating to physical custody and preservation of materials are followed
Ensuring safety of materials and personnel
Facility Management
Shift management and Roster generation
Leaves processing & workflow management
Track time-in and time-out of every personnel
Overtime calculation and reporting
Integration with multiple access control systems
Export data to Payroll systems
Web enabled facility reservation
Inviting Internal & External attendees for meetings
Car Park reservation and Visitor Management integration
Scheduling of refreshments orders to catering
Billing & Usage Analysis
Switch On/off HVAC and Lighting automatically
Manage space inventory
Visually plan and allocate space
Department / project wise occupancy analysis, charge backs
Reports
Create your own KPIs, reports and dashboards
Drill Down provision to view detailed reports
Pivot grids for more detailed analysis
Link custom reports, KPIs to menu system
System Features
Set up complex workflow rules and logics as per needs
Routing of workflows based on user actions
Auto reminders on pending approvals
Customizable email messages
Detailed audit log / history
Legacy documents
Scan legacy document
Create digital assets that can be searched and tagged
Associate the assets with existing projects, clients etc
| Quality Assurance |  | 0
| QA & Bug Fixing |  | 0
| UAT |  | 0
| Deployment per instance |  | 20
Total Effort
Assumptions
* Optional Item
1 Lead generation through email will use RPA to read emails or attachments and create a lead within the application
Estimate does not include BOM for hardware

## Mobile
Login and registration
Event info
contact information
details of other participants
rate events
customized Quizzes