## PWC
PWC Venue Management App |  | 2018-11-12
Tuesday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 10 | 10
Business Analysis | 40 | 5 | Sr Developer | 2 | 75 | 150 | 90.875 | 310 | 309.25 | 310
Project Management | 247.4 | 30.925 | Jr Developer | 2 | 80 | 160
Documentation (SRS, FS, Weekly Reports) | 32 | 4 | BA | 1 | 5 | 5
Development |  | 0 | TechWriter | 1 | 4 | 4
UI design | 40 | 5 | PM | 1 | 30.925 | 30.925
Prototyping | 40 | 5 | QA | 2 | 52.3687 | 104.7375
Responsive Web Application |  | 0 | Total |  |  | 464.6625
Master Data Management (Templated and configurable) | 0 | 0
Floor Plan & Floor Sites | 32 | 4
IT Facilities | 32 | 4
Security Facilities | 32 | 4
House keeping | 32 | 4
FNB | 32 | 4
Three tiered approval workflow framework. | 32 | 4
Floor Plan & Floor Sites | 32 | 4
Data Collection templates for each service | 32 | 4 |  | Days | months
User authorization and entitlements linked to approval workflow | 32 | 4 | Total Delivery days | 142.3688 | 7.1184
Event Booking |  | 0
Lead Generation (Website and emails*1) | 16 | 2
Capture event facility requirments | 16 | 2
Floor area, IT requirments, Security requirments House keeping FNB. Multiple forms that are dynamically generated based on the options being selected | 20 | 2.5 | Total Effort | 464.6625 | (+1 Day deployment)
Capture client details, event details, Offer period, misc data | 20 | 2.5
Generate documents that capture the requirments listed. Confirmation letter etc | 20 | 2.5
Generate MOU to receive approval from the client | 20 | 2.5
Workflow for approval process | 20 | 2.5
Customer approved MOU | 24 | 3
Check in and attendee tracking | 8 | 1
Email campaigns | 20 | 2.5
Manage invoices | 20 | 2.5
Collect Payments | 20 | 2.5
Online registration | 45 | 5.625
Customer web view |  | 0
Customer Login | 10 | 1.25
Floor plans and site details (View and update plan With service specific forms) | 16 | 2
IT Facilities (View and update plan With service specific forms) | 16 | 2
Security Facilities (View and update plan With service specific forms) | 16 | 2
House keeping (View and update plan With service specific forms) | 16 | 2
FNB (View and update plan With service specific forms) | 16 | 2
Consumption Sheets | 8 | 1
Financial Impact Assesment | 8 | 1
Change management | 16 | 2
Workflow for change and approvals | 8 | 1
Summary and feedback | 16 | 2
Integrations |  | 0
Tally integration | 40 | 5
Mail integration |  | 0
SMS integration | 24 | 3
Operations |  | 0
Reminders for start operations | 8 | 1
Assign SPOC for services | 10 | 1.25
SPOC creates tasks and activity schedules | 24 | 3
Assign responsibilities | 8 | 1
Calendar integrations (google calender, Client will be responsible for API access) | 24 | 3
Sign off on project plans from the client | 16 | 2
Data collection wizard for each service (5 services identified) | 35 | 4.375
Generate data sheets with list of requirments | 21 | 2.625
Vendor management
Create Vendor service categories | 10 | 1.25
Create Vendor selection criteria | 12 | 1.5
Create Bid Document (RFI, RFP, RFQ) | 24 | 3
Risk Assessment & Evaluate offers | 24 | 3
Contract negotiation | 10 | 1.25
Onboarding | 35 | 4.375
Monitoring performace and mitigating risks | 24 | 3
Managing Vendor relationship | 24 | 3
Store management |  | 0
Receipt of incoming materials | 24 | 3
Supervision of unloading of materials and tallying of materials | 16 | 2
Checking for damages or shortages and preparation of the report | 16 | 2
Filling of ‘goods inward’, ‘day book’, or ‘daily collection’ register | 32 | 4
Completion of vendors consignment note (challan) | 16 | 2
Making arrangement for inspection and getting the inspection completed | 16 | 2
Preparation of ‘goods receipt note’ (GRN) | 16 | 2
Preparation of ‘goods rejection memo’ (in case of rejection of materials) | 16 | 2
Sending of materials to the respective stores | 16 | 2
Sending of the relevant documents to the respective departments | 16 | 2
Ensuring all storage and material handling facilities are in proper working order | 16 | 2
Ensuring good housekeeping and cleanliness in the storage space | 16 | 2
Checking, counting and tallying of materials before issue | 30 | 3.75
Making prompt entries in ‘Bin card’ or stock card | 35 | 4.375
Ensuring correct documentation of material receipts and material issues | 12 | 1.5
Ensuring safe and proper handling of materials so as not to damage them | 12 | 1.5
Ensuring proper record keeping and correct accounting of materials | 12 | 1.5
Ensuring regular stock verification | 32 | 4
Ensuring that rules and regulations relating to physical custody and preservation of materials are followed | 12 | 1.5
Ensuring safety of materials and personnel | 12 | 1.5
Facility Management |  | 0
Shift management and Roster generation | 24 | 3
Leaves processing & workflow management | 110 | 13.75
Track time-in and time-out of every personnel | 70 | 8.75
Overtime calculation and reporting | 42 | 5.25
Export data to Payroll systems | 40 | 5
Web enabled facility reservation | 45 | 5.625
Inviting Internal & External attendees for meetings | 24 | 3
Car Park reservation and Visitor Management integration | 25 | 3.125
Scheduling of refreshments orders to catering | 24 | 3
Billing & Usage Analysis | 32 | 4
Manage space inventory | 25 | 3.125
Visually plan and allocate space | 12 | 1.5 | ?
Department / project wise occupancy analysis, charge backs | 20 | 2.5
Reports |  | 0
Create your own KPIs, reports and dashboards | 35 | 4.375
Drill Down provision to view detailed reports | 24 | 3
Pivot grids for more detailed analysis | 55 | 6.875
Link custom reports, KPIs to menu system | 60 | 7.5
System Features |  | 0
Set up complex workflow rules and logics as per needs | 110 | 13.75
Routing of workflows based on user actions | 80 | 10
Auto reminders on pending approvals | 32 | 4
Customizable email messages | 24 | 3
Detailed audit log / history | 32 | 4
Legacy documents |  | 0
Scan legacy document (integration only) |  | 0
Create digital assets that can be searched and tagged |  | 0
Associate the assets with existing projects, clients etc |  | 0
Quality Assurance |  | 0
QA & Bug Fixing | 837.9 | 104.7375
UAT
Deployment per instance |  | 0
Total Effort |  | 453.9125
Assumptions
* Optional Item
1 Lead generation through email will use RPA to read emails or attachments and create a lead within the application
Estimate does not include BOM for hardware

## Mobile
Login and registration
Event info
contact information
details of other participants
rate events
customized Quizzes