## PWC
PWC Venue Management App |  | 2018-11-12
Tuesday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 10 | 10
Business Analysis | 32 | 4 | Sr Developer | 2 | 55 | 110 | 103 | 222 | 222.25 | 222
Project Management | 183.4 | 22.925 | Jr Developer | 2 | 56 | 112
Documentation (SRS, FS, Weekly Reports) | 32 | 4 | BA | 1 | 4 | 4
Development |  | 0 | TechWriter | 1 | 4 | 4
UI design | 40 | 5 | PM | 1 | 22.925 | 22.925
Prototyping | 40 | 5 | QA | 2 | 31.5375 | 63.075
Responsive Web Application |  | 0 | Total |  |  | 326
Master Data Management (Templated and configurable, Quatifiable MOU’s) | 0 | 0
Service Master | 8 | 1
Service Master details (Maps services to service details) | 8 | 1
Venue Master | 8 | 1
Client Master | 8 | 1
Venue – service master (Maps the venue to services offered at venue) | 8 | 1
Floor Plans & quantitative floor plan descriptions (upload site plans and capture space availability via forms) | 8 | 1
IT Facility service master | 8 | 1
Security master | 8 | 1 |  | Days | months
House keeping service master | 8 | 1 | Total Delivery days | 97.5375 | 4.8769 | 2034240
Vendor service categories | 8 | 1
Vendor master | 8 | 1
Vendor-service master | 8 | 1
Manage Empaneled vendors | 8 | 1 | Total Effort | 326 | (+1 Day deployment)
FNB service master | 8 | 1
Service approval master | 8 | 1
Data Collection templates for each service | 24 | 3
User authorization and entitlements linked to approval workflow | 24 | 3
MOU Approval Process (Generic module inherited by all services)
Generic 3 Tiered approval process for MOU (Develop framework) | 24 | 3
Manage MOU (Add clauses and assosiated costs; Imports information from service masters) | 24 | 3
Create workflow triggers (includes order approval and legal approval) | 24 | 3
Generate documentation based on MOU parameters | 24 | 3
MOU Customer approval | 24 | 3
Project Management (Generic module inherited by all Services) |  | 0
Create task list and Schedules | 16 | 2
Assign resources | 6 | 0.75
Export Project schedule for presentation purpose (PDF or Excel) | 16 | 2
Schedule reminders via email | 8 | 1
Project Kick off meetings (MOM, Attendees, additional references) | 16 | 2
Project approval workflow with triggers (3 tiered) | 16 | 2
project signoffs (customer signoffs) | 16 | 2
Project updates (scheduled vs Actuals). Mark executions | 16 | 2
Track project progress (via reports) | 16 | 2
Calendar integration | 16 | 2
Event Booking |  | 0
Integrate and customize approvals and overall project plan for the event | 8 | 1
Capture event requirments (Based on advertised services created from master data) | 16 | 2
Floor area, IT requirments, Security requirments House keeping FNB. Multiple forms that are dynamically generated based on information contained in master data | 20 | 2.5
Capture client details, event details, Offer period, misc data | 8 | 1
Generate documents that capture the requirments listed. Confirmation letter etc | 20 | 2.5
Generate MOU to receive approval from the client | 32 | 4
Capture attendee list | 8 | 1
Customer approved MOU | 24 | 3
Check in and attendee tracking | 8 | 1
Email campaigns (integrate with external marketing tools) / Verify guest attendance | 20 | 2.5
Import legacy information on already booked events | 16 | 2
Import legacy information of completed events | 22 | 2.75
Generate reports related to event (services ordered, Event schedule with important dates, client details, SPOC details, Space requiremenst, changes requested etc) | 20 | 2.5
Customer web view |  | 0
Customer Login & registration | 12 | 1.5
Initial online registration for events (assuming the MOU has already been signed off) | 8
Customers may also fill out a templated spreadsheet with requirements (made available to them via web or email) and email it. RPA can be utilized to process such emails and the information can be enetered into the application without human assistance | 24
Available services that can be configured based on the MOU | 24
Floor plans and site details (View and update plan With service specific forms) | 16 | 2
IT Facilities (View and update plan With service specific forms) | 16 | 2
Security Facilities (View and update plan With service specific forms) | 16 | 2
House keeping (View and update plan With service specific forms) | 16 | 2
FNB (View and update plan With service specific forms) | 16 | 2
Financial Impact Assesment (Since customers configure the service based on already accepted MOU, the price change can be calculated on the fly) | 12 | 1.5
Change management (When customer requests services that were not part of the MOU) | 16 | 2
Workflow for change and approvals based on triggers | 8 | 1
Summary of feedback (Various reports ranging from schedules, costs, changes requested etc) | 16 | 2
Integrations |  | 0
Tally integration (generate formatted documents that can be uploaded to Tally) | 32 | 4
Integration for Lead Generation via website and emails | 12 | 1.5
DMS Integration using open source tools (eg. Alfresco) | 24 | 3
Marketing tool integration (Extrenal marketing service plugins) | 24 | 3
SMS & email integration | 24 | 3
PM and Workflow integrations( already mentioned)
Operations |  | 0
Initiate operations (reminder emails to concerned parties) | 8 | 1
Assign SPOC for services | 8 | 1
Capture MOM for various activities | 8 | 1
Assimilate Project plans to create the master project plan | 16 | 2
Link SPOC with Client Representatives | 8 | 1
SPOC performance | 12 | 1.5 |  |  | B
Operational reports (Equipment:IT arrival reports, Human resource requirment reports, FnB Requirement, Menu requirements etc) | 24 | 3
Consumption Sheets | 24 | 3
Vendor management
Create Vendor selection criteria | 12 | 1.5
vendor onboarding | 24 | 3
Create Bid Document (RFI, RFP, RFQ) | 24 | 3
Receive offers | 24 | 3
Evaluate offers | 10 | 1.25
Approve Offer | 8 | 1
Store quotes received | 8 | 1
Reports (vendor supply list : material and resources) | 16 | 2
Link Vendor supply to store management | 24 | 3
Link vendor supply schedules with project plans | 8 | 1
Reports on quotes floated / quotes received per event. Criteria for selection etc | 12 | 1.5
Store management |  | 0 | ?
Integrate with vendor management for material management | 8 | 1
Daily collection/return report | 12 | 1.5
Security Inspection Results | 12 | 1.5
Receipt and tally of incoming materials | 12 | 1.5
Record damages and shortages (Quality Control) | 12 | 1.5
Material inspection report | 12 | 1.5
Generate and print goods receipt note | 12 | 1.5
Preparation of ‘goods rejection memo’ (in case of rejection of materials) | 12 | 1.5
Material issue or material transfer receipts (intra department) | 16 | 2
Verify material return (intra departments), tallying | 12 | 1.5
Material return / stock verification (outgoing) | 12 | 1.5
Facility Management |  | 0
Link facility with venue and client | 8 | 1
Car Park reservation and Visitor Management integration | 8 | 1
Manage space inventory | 8 | 1
Reports (Space available, utilization by client, date, event etc) | 16 | 2
Security Management
Security requirment for the event (Type, No., dates, events etc.) | 8 | 1
link security requirement with rented space, venues etc | 8 | 1
Link security with vendor provider (Multiple vendors) | 8 | 1
information on security personell being recruited | 8 | 1
Related Reports | 16 | 2
FNB + Housekeeping |  | 0
FNB requirment per venue / event / client (service timings, menu/cuisine selections, vendors):Multiple | 8 | 1
House keeping requirments +linked vendors + # availability + Schedules etc | 8 | 1
Cuisine details (veg/nonveg/vegan etc) | 8 | 1
Menu details for each cuisine | 8 | 1
link to vendor / vendor timings / schedules / servers / no of guests etc | 8 | 1
Corelate with expected attendance from event booking module | 8 | 1
Corelated reports on FNB Vendors, venues, schedules, menus in any combinations | 16 | 2
IT Facility Management |  | 0
Determine IT requirements per venue based on master data (Routers, computers, laptops, flatscreens power outlets, bandwidth etc) | 8 | 1
Link IT vendor with venue / event / client | 8 | 1
link vendors and store | 8 | 1
Reports for security requirments corelated to clients / venues / events / dates etc | 16 | 2
System Features |  | 0
Set up complex workflow rules and logics as per needs | 24 | 3
Procurement cycle, MOU creation W/F, Project planning W/F | 16 | 2
Auto reminders on pending approvals | 24 | 3
Customizable email messages | 24 | 3
Detailed audit log / history | 24 | 3
Legacy documents |  | 0
Scan legacy document (integration only) | 24 | 3
Create digital assets that can be searched and tagged | 24 | 3
Associate the assets with existing engagements or retired engagements | 24 | 3
Quality Assurance |  | 0
QA & Bug Fixing | 504.6 | 63.075
UAT
Deployment per instance |  | 0
Total Effort |  | 316.25
Assumptions
Application does not support Accounting or financial transactions
Does not include integration of Alfresco or Email campaign software
Note on A15: MOU’s are standard templated documents. However it will have placeholders to add additional clauses as well as costs agreed upon for various services

## Guest Mobile
Login and registration
Event info
contact information
details of other participants
rate events
customized Quizzes

## Customer Mobile
Customer Mobile shall be split into multiple modules
Verbat will deliver a hybrid mobile application
All master data entries shall be done via the Web. The mobile version shall have no legacy document integration features
Verbat will deliver the Mobile as seperate applications in the following order chronologically
Event management High level view. This will be a view only version
vendor Management
Store management
Facility management
Security management
FNB + Housekeeping
IT facility Management
Customer Web View
Event management editable version with workflow integration and approval process
Oprations management