## PWC
PWC Venue Management App
Module
Initiation
Business Analysis
Project Management
Documentation (SRS, FS, Weekly Reports)
Development
UI design
Prototyping
Responsive Web Application
Master Data Management (Templated and configurable, Quatifiable MOU’s)
Service Master
Service Master details (Maps services to service details)
Venue Master
Client Master
Venue – service master (Maps the venue to services offered at venue)
Floor Plans & quantitative floor plan descriptions (upload site plans and capture space availability via forms)
IT Facility service master
Security master
House keeping service master
Vendor service categories
Vendor master
Vendor-service master
Manage Empaneled vendors
FNB service master
Service approval master
Data Collection templates for each service
User authorization and entitlements linked to approval workflow
MOU Approval Process (Generic module inherited by all services)
Generic 3 Tiered approval process for MOU (Develop framework)
Manage MOU (Add clauses and assosiated costs; Imports information from service masters)
Create workflow triggers (includes order approval and legal approval)
Generate documentation based on MOU parameters
MOU Customer approval
Project Management (Generic module inherited by all Services)
Create task list and Schedules
Assign resources
Export Project schedule for presentation purpose (PDF or Excel)
Schedule reminders via email
Project Kick off meetings (MOM, Attendees, additional references)
Project approval workflow with triggers (3 tiered)
project signoffs (customer signoffs)
Project updates (scheduled vs Actuals). Mark executions
Track project progress (via reports)
Calendar integration
Event Booking
Integrate and customize approvals and overall project plan for the event
Capture event requirments (Based on advertised services created from master data)
Floor area, IT requirments, Security requirments House keeping FNB. Multiple forms that are dynamically generated based on information contained in master data
Capture client details, event details, Offer period, misc data
Generate documents that capture the requirments listed. Confirmation letter etc
Generate MOU to receive approval from the client
Capture attendee list
Customer approved MOU
Check in and attendee tracking
Email campaigns (integrate with external marketing tools) / Verify guest attendance
Import legacy information on already booked events
Import legacy information of completed events
Generate reports related to event (services ordered, Event schedule with important dates, client details, SPOC details, Space requiremenst, changes requested etc)
Customer web view
Customer Login & registration
Initial online registration for events (assuming the MOU has already been signed off)
Customers may also fill out a templated spreadsheet with requirements (made available to them via web or email) and email it. RPA can be utilized to process such emails and the information can be enetered into the application without human assistance
Available services that can be configured based on the MOU
Floor plans and site details (View and update plan With service specific forms)
IT Facilities (View and update plan With service specific forms)
Security Facilities (View and update plan With service specific forms)
House keeping (View and update plan With service specific forms)
FNB (View and update plan With service specific forms)
Financial Impact Assesment (Since customers configure the service based on already accepted MOU, the price change can be calculated on the fly)
Change management (When customer requests services that were not part of the MOU)
Workflow for change and approvals based on triggers
Summary of feedback (Various reports ranging from schedules, costs, changes requested etc)
Integrations
Tally integration (generate formatted documents that can be uploaded to Tally)
Integration for Lead Generation via website and emails
DMS Integration using open source tools (eg. Alfresco)
Marketing tool integration (Extrenal marketing service plugins)
SMS & email integration
PM and Workflow integrations( already mentioned)
Operations
Initiate operations (reminder emails to concerned parties)
Assign SPOC for services
Capture MOM for various activities
Assimilate Project plans to create the master project plan
Link SPOC with Client Representatives
SPOC performance |  | B
Operational reports (Equipment:IT arrival reports, Human resource requirment reports, FnB Requirement, Menu requirements etc)
Consumption Sheets
Vendor management
Create Vendor selection criteria
vendor onboarding
Create Bid Document (RFI, RFP, RFQ)
Receive offers
Evaluate offers
Approve Offer
Store quotes received
Reports (vendor supply list : material and resources)
Link Vendor supply to store management
Link vendor supply schedules with project plans
Reports on quotes floated / quotes received per event. Criteria for selection etc
Store management | ?
Integrate with vendor management for material management
Daily collection/return report
Security Inspection Results
Receipt and tally of incoming materials
Record damages and shortages (Quality Control)
Material inspection report
Generate and print goods receipt note
Preparation of ‘goods rejection memo’ (in case of rejection of materials)
Material issue or material transfer receipts (intra department)
Verify material return (intra departments), tallying
Material return / stock verification (outgoing)
Facility Management
Link facility with venue and client
Car Park reservation and Visitor Management integration
Manage space inventory
Reports (Space available, utilization by client, date, event etc)
Security Management
Security requirment for the event (Type, No., dates, events etc.)
link security requirement with rented space, venues etc
Link security with vendor provider (Multiple vendors)
information on security personell being recruited
Related Reports
FNB + Housekeeping
FNB requirment per venue / event / client (service timings, menu/cuisine selections, vendors):Multiple
House keeping requirments +linked vendors + # availability + Schedules etc
Cuisine details (veg/nonveg/vegan etc)
Menu details for each cuisine
link to vendor / vendor timings / schedules / servers / no of guests etc
Corelate with expected attendance from event booking module
Corelated reports on FNB Vendors, venues, schedules, menus in any combinations
IT Facility Management
Determine IT requirements per venue based on master data (Routers, computers, laptops, flatscreens power outlets, bandwidth etc)
Link IT vendor with venue / event / client
link vendors and store
Reports for security requirments corelated to clients / venues / events / dates etc
System Features
Set up complex workflow rules and logics as per needs
Procurement cycle, MOU creation W/F, Project planning W/F
Auto reminders on pending approvals
Customizable email messages
Detailed audit log / history
Legacy documents
Scan legacy document (integration only)
Create digital assets that can be searched and tagged
Associate the assets with existing engagements or retired engagements
Quality Assurance
QA & Bug Fixing
UAT
Deployment per instance
Total Effort
Assumptions
Application does not support Accounting or financial transactions
Does not include integration of Alfresco or Email campaign software
Note on A15: MOU’s are standard templated documents. However it will have placeholders to add additional clauses as well as costs agreed upon for various services

## Guest Mobile
Login and registration
Event info
contact information
details of other participants
rate events
customized Quizzes

## Customer Mobile
Customer Mobile shall be split into multiple modules
Verbat will deliver a hybrid mobile application
All master data entries shall be done via the Web. The mobile version shall have no legacy document integration features
Verbat will deliver the Mobile as seperate applications in the following order chronologically
Event management High level view. This will be a view only version
vendor Management
Store management
Facility management
Security management
FNB + Housekeeping
IT facility Management
Customer Web View
Event management editable version with workflow integration and approval process
Operations management