## AndroidDev
PHARMACY MOBILE APP |  | 2018-03-05
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 4 | 0.5
Splash Screen
Design and Development | 4 | 0.5
Login Page
Design ,Development and Api integration | 8 | 1
Registration |  | 0
Design ,Development and Api integration | 8 | 1
OTP Verification code |  | 0
Design ,Development and Api integration | 4 | 0.5
Store locator |  | 0
Design ,Development and Api integration | 2 | 0.25
Customer profile with medical information, insurance and lists of scanned medical prescriptions |  | 0
Design ,Development and Api integration | 8 | 1
Display of the vouchers list for redemption |  | 0
Design ,Development and Api integration | 8 | 1
Contact Us |  | 0
Design ,Development and Api integration | 8 | 1
Payment |  | 0
Design ,Development ,Api integration and payment gate way | 32 | 4
Local ID scan(Using Camera) |  | 0
Design ,Development and Api integration | 8 | 1
QR code scanner and product details |  | 0
Design ,Development and Api integration | 6 | 0.75
Camera access so the client can take a picture |  | 0
Design ,Development and Api integration | 6 | 0.75
Camera access to take a picture of the ID |  | 0
Design ,Development and Api integration | 4 | 0.5
Camera access to take a picture insurance card |  | 0
Design ,Development and Api integration | 4 | 0.5
The client will choose the way of delivery |  | 0
Design ,Development and Api integration | 4 | 0.5
Select the store of his choice |  | 0
Design ,Development and Api integration | 4 | 0.5
Chooses home delivery: he will have to fill up his address details with a pinpoint on a map |  | 0
Design ,Development and Api integration | 16 | 2
When the prescription is received by the pharmacy the user will get an “in progress” notification |  | 0
Api integration and push notification | 16 | 2
News about the brands, products, events, promotions |  | 0
Design ,Development and Api integration | 16 | 2
Reminder notification on the phone when he has to take his medicine |  | 0
Design ,Development and Api integration | 8 | 1
A chat answered by Pharmacy staff(Offline Server) |  | 0
Design ,Development and Api integration | 16 | 2
total effort |  | 24.25
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode