## Pharmacy
Online Pharmacy |  | 2017-05-23
Tuesday
Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  | No Hrs | Rate/Hr | Total
Initiation |  |  | Designer | 1 | 10 | 10 |  |  | 80 | 687.5 | 55000
Business analysis | 32 | 4 | Sr Developer | 1 | 44 | 44 | 89 | 88 | 352 | 1000 | 352000
Project Management | 71.2 | 8.9 | Jr Developer | 1 | 44 | 44 |  |  | 352 | 875 | 308000
Project Documentation (SRS, Scope, WBS etc.) | 32 | 4 | Android | 1 | 24.25 | 24.25 |  |  | 194 | 1000 | 194000
Complete running prototype (Web+IOS+Android) | 80 | 10 | IOS | 1 | 30.3125 | 30.3125 |  |  | 242.5 | 875 | 212187.5
Development |  |  | PM | 1 | 8.9 | 8.9 |  |  | 71.2 | 1250 | 89000
Login Via Mobile # & email | 16 | 2 | BA | 1 | 8 | 8 |  |  | 64 | 687.5 | 44000
Registration | 8 | 1 | Tech writer | 1 |  | 0 |  |  | 0 | 562.5 | 0
OTP via SMS | 8 | 1 | QA | 3 | 12.2 | 36.6 |  |  | 292.8 | 562.5 | 494100
App download link via SMS for new users | 8 | 1 | Total |  |  | 206.0625 |  |  |  |  | 1748287.5
App download link via SMS for customers who brought product without app (Pushed from ERP System |  | 0
Store locator in app | 8 | 1
Gift Voucher (redeemed & used) | 24 | 3 | Total Delivery days | 66.2
Customer profile | 24 | 3 | Total Effort | 206.0625 | (+1 Day deployment)
Medical information (History) |  | 0
Insurance information |  | 0
Scanned medical prescriptions |  | 0
Voucher list for redemption (pushed from ERP) | 16 | 2
Contact Us (Pharmacy hotline no, email address, PO address) | 16 | 2
Ecommerce solution including payment and delivery | 0 | 0
Pedometre activation of gift voucher - link to wearable device | 0 | 0
Local ID Scan and OCR of data | 16 | 2
QR code scanner to access product info, promotions and more | 16 | 2
Medical Prescription preorder | 16 | 2
Take picture of prescription,Local ID, Insurance info and upload to device via app | 32 | 4
Select delivery options (Home delivery, pickup) | 40 | 5
If Pickup, select store |  | 0
If delivery, add delivery address details with landmarks |  | 0
Send prescription information, insurance etc to staff (Web and mobile app) |  | 0
Pharmacy location on map |  | 0
Pharmacy acknowledges receipt and customer receives an in progress status |  | 0
News, product alerts, events, promotions | 16 | 2
reminders for prescription renewals, medical alerts based on the pharmacy reccomended dosages entered when the prescription was issued) |  | 0
Chat application for messaging the pharmacy staff | 32 | 4
Staff Interface |  | 0
Staff receives a prescription alert | 16 | 2
Updates the prescription with various status' | 24 | 3
look up patient records | 16 | 2
Enter prescription schedules based on prescription | 16 | 2
Prescription management | 32 | 4
Receive prescription renewal notices | 16 | 2
Admin |  | 0
maintain store locations( Address, email, phone, operational hours, manager) | 16 | 2
Manage customer records (documents, profile, medical history, prescriptions) | 24 | 3
Manage Pharmacy technicians | 16 | 2
Site updates via CMS | 16 | 2
Assign Pharmacy Tech to store | 12 | 1.5
Reroute prescriptions to a new store | 12 | 1.5
create vouchers & coupons | 32 | 4
Coupon redemtions (manual) | 24 | 3
Application Features |  | 0
Logging and auditing | 8 | 1
Exception Handling | 8 | 1
folders & file management | 8 | 1
API Layer |  | 0
Integration with ERP (Create API service layer) | 16 | 2
Payment Gateway integration | 12 | 1.5
QR code scanner integration (Coupons) | 16 | 2
OCR Integration (prescription, ID) | 16 | 2
Wearable device integration | 0 | 0
SMS & email integration | 12 | 1.5
Barcode scanner (Local ID) | 12 | 1.5
Generate alerts | 12 | 1.5
Reports & Analytics | 24 | 3
ecommerce cart & product listings | 0 | 0
Quality Assurance
QA & Bug Fixing | 284.8 | 35.6
UAT | 8 | 1
Deployment | 8 | 1
Total Effort | 1228 | 153.5
Assumptions
Does not include ecommerce integration
Does not include pedometer integration
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode

## Sheet2
Module |  | No | Man Days | Total Effort | No Hrs | Rate/Hr | Total
Initiation | Designer | 1 | 10 | 10 | 80 | 687.5 | 55000
Business analysis | Sr Developer | 1 | 44 | 44 | 352 | 1000 | 352000
Project Management | Jr Developer | 1 | 44 | 44 | 352 | 875 | 308000
Project Documentation (SRS, Scope, WBS etc.) | Android | 1 | 24.25 | 24.25 | 194 | 1000 | 194000
Complete running prototype (Web+IOS+Android) | IOS | 1 | 30.3125 | 30.3125 | 242.5 | 875 | 212187.5
Development | PM | 1 | 8.9 | 8.9 | 71.2 | 1250 | 89000
Login Via Mobile # & email | BA | 1 | 8 | 8 | 64 | 687.5 | 44000
Registration | Tech writer | 1 |  | 0 | 0 | 562.5 | 0
OTP via SMS | QA | 3 | 12.2 | 36.6 | 292.8 | 562.5 | 494100
App download link via SMS for new users | Total |  |  | 206.0625 |  |  | 1748287.5
App download link via SMS for customers who brought product without app (Pushed from ERP System
Store locator in app
Gift Voucher (redeemed & used) | Total Delivery days | 66.2
Customer profile | Total Effort | 206.0625 | (+1 Day deployment)
Medical information (History)
Insurance information
Scanned medical prescriptions
Voucher list for redemption (pushed from ERP)
Contact Us (Pharmacy hotline no, email address, PO address)
Local ID Scan and OCR of data
QR code scanner to access product info, promotions and more
Medical Prescription preorder
Take picture of prescription,Local ID, Insurance info and upload to device via app
Select delivery options (Home delivery, pickup)
If Pickup, select store
If delivery, add delivery address details with landmarks
Send prescription information, insurance etc to staff (Web and mobile app)
Pharmacy location on map
Pharmacy acknowledges receipt and customer receives an in progress status
News, product alerts, events, promotions
reminders for prescription renewals, medical alerts based on the pharmacy reccomended dosages entered when the prescription was issued)
Chat application for messaging the pharmacy staff
Staff Interface
Staff receives a prescription alert
Updates the prescription with various status'
look up patient records
Enter prescription schedules based on prescription
Prescription management
Receive prescription renewal notices
Admin
maintain store locations( Address, email, phone, operational hours, manager)
Manage customer records (documents, profile, medical history, prescriptions)
Manage Pharmacy technicians
Site updates via CMS
Assign Pharmacy Tech to store
Reroute prescriptions to a new store
create vouchers & coupons
Coupon redemtions (manual)
Application Features
Logging and auditing
Exception Handling
folders & file management
API Layer
Integration with ERP (Create API service layer)
Payment Gateway integration
QR code scanner integration (Coupons)
OCR Integration (prescription, ID)
Wearable device integration
SMS & email integration
Barcode scanner (Local ID)
Generate alerts
Reports & Analytics
ecommerce cart & product listings
Quality Assurance
QA & Bug Fixing
UAT
Deployment
Total Effort
Assumptions
Does not include ecommerce integration
Does not include pedometer integration
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode
API subscription charges paid by client
Payument gateway, SMS, hosting etc provided by client
Android and IOS developer accounts paid by client
HTML templates will be provided by client

## Mobile
PHARMACY MOBILE APP |  | 2018-03-05
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 4 | 0.5
Splash Screen
Design and Development | 4 | 0.5
Login Page
Design ,Development and Api integration | 8 | 1
Registration |  | 0
Design ,Development and Api integration | 8 | 1
OTP Verification code |  | 0
Design ,Development and Api integration | 4 | 0.5
Store locator |  | 0
Design ,Development and Api integration | 2 | 0.25
Customer profile with medical information, insurance and lists of scanned medical prescriptions |  | 0
Design ,Development and Api integration | 8 | 1
Display of the vouchers list for redemption |  | 0
Design ,Development and Api integration | 8 | 1
Contact Us |  | 0
Design ,Development and Api integration | 8 | 1
Payment |  | 0
Design ,Development ,Api integration and payment gate way | 32 | 4
Local ID scan(Using Camera) |  | 0
Design ,Development and Api integration | 8 | 1
QR code scanner and product details |  | 0
Design ,Development and Api integration | 6 | 0.75
Camera access so the client can take a picture |  | 0
Design ,Development and Api integration | 6 | 0.75
Camera access to take a picture of the ID |  | 0
Design ,Development and Api integration | 4 | 0.5
Camera access to take a picture insurance card |  | 0
Design ,Development and Api integration | 4 | 0.5
The client will choose the way of delivery |  | 0
Design ,Development and Api integration | 4 | 0.5
Select the store of his choice |  | 0
Design ,Development and Api integration | 4 | 0.5
Chooses home delivery: he will have to fill up his address details with a pinpoint on a map |  | 0
Design ,Development and Api integration | 16 | 2
When the prescription is received by the pharmacy the user will get an “in progress” notification |  | 0
Api integration and push notification | 16 | 2
News about the brands, products, events, promotions |  | 0
Design ,Development and Api integration | 16 | 2
Reminder notification on the phone when he has to take his medicine |  | 0
Design ,Development and Api integration | 8 | 1
A chat answered by Pharmacy staff(Offline Server) |  | 0
Design ,Development and Api integration | 16 | 2
total effort |  | 24.25
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode