## SMS- Web
| Scheduler Management System (SMS) | 2018-02-25
Wednesday
Sl. No. | Module | Man Days
Exploration and Discovery
1 | Create Use case
2 | Survey and freeze the proposed use case
3 | Conduct planning meetings to discuss and finalize project scope/details
4 | Analysis and Planning
7 | Design
11 | Create prototype of the website (different layouts) | 5
12 | Confirm Prototype | 0
13 | Development and Production
15 | Set up development environment and server - PHP | 0.5
Home
| Product and Service Home Page | 2
| Admin Dashboard Page | 2
| Manger Dashboard Page | 2
| Student Dashboard Page | 2
| Register | 5
| Admin Interface | 2
| Course | 8
| Payment API | 4
| Schedule | 8
Punch-In
| Meeting Request | 5
| Reports | 10
| Master Setup | 3
19 | Testing and training
20 | Test for full functionality on all major and active browsers | 4
26 | Total | 62.5
Assumptions
Only one language available (English)
Need clarification
integration with biometric machine

## Sheet2
SCTDA |  | 2017-05-23
Tuesday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 5 | 5
Business analysis | 0 | 0 | Sr Developer | 1 | 18 | 18 | 36 | 36
Project Management | 0 | 0 | Jr Developer | 1 | 18 | 18
Project Documentation (SRS, Scope, WBS etc.) | 0 | 0 | Android | 1 | 21.6 | 21.6
Complete running prototype (Web+IOS+Android) | 40 | 5 | IOS | 1 | 21.6 | 21.6
Development |  |  | PM | 1 |  | 0
Login (FB, Google) | 8 | 1 | BA | 1 | 0 | 0
Home page | 8 | 1 | Tech writer | 1 |  | 0
product and svc page | 8 | 1 | QA | 2 | 6.675 | 13.35
Admin Dashboard (attendance roster, class schedules, Payments received, Meeting requests, feedback) | 16 | 2 | Total |  |  | 97.55
Manager Dashboard(students, classes taken etc.) | 8 | 1
Student Dashboard(Upcoming classes, classes taken, classes missed, payment receipts, meeting requests, F/B received) | 16 | 2
Register Client interface (Register, create multiple profiles, view classes scheduled and attendance, school migration req) | 16 | 2 | Total Delivery days | 29.675
Register Admin Interface (view student profiles, approve school migrations, award additional classes) | 16 | 2 | Total Effort | 97.55 | (+1 Day deployment)
book courses (apply booking rules, pause booking) | 16 | 2
pay online | 16 | 2
Map students, courses and course schedules | 8 | 1
attendance penalty rules | 8 | 1 | Resource Loading
cancellation policy | 8 | 1 | Resource/Skill | Month 1 | Month 2 | Month 3
biometric attendance register (with Attendance rules) | 32 | 4 | Proj. Manager | 48 | 40 | 32
meeting request | 6 | 0.75 | Business Analyst | 80 | 8 | 8
reports | 24 | 3 | User Experience | 64 | 16 | 16
Master data (city, school, course master) | 8 | 1 | Architect | 24 | 8 | 8
Admin |  | 0 | Lead Developer | 80 | 160 | 80
Create Group class | 6 | 0.75 | Developer | 80 | 160 | 120
Create Individual class | 6 | 0.75 | DB Architect | 24 | 8 | 8
manage users | 6 | 0.75 | Android Developer | 0 | 120 | 80
manage class schedule | 6 | 0.75 | QA | 40 | 40 | 240
create courses | 6 | 0.75 | Tech Writer |  |  | 24
course list | 6 | 0.75 | Total Effort | 202 |  | 1616
course details | 6 | 0.75
mark class cancelled (due to teacher absence) | 6 | 0.75 | Total Effort Variation : | 180 - 200 days
Mobile App development (Android) | 0 | 0
Android API Development | 0 | 0
System features
Authentication & authorization | 6 | 0.75 |  |  | 1736/8
Auditing & logging | 6 | 0.75
Exception handling | 6 | 0.75
Quality Assurance
QA & Bug Fixing | 100.8 | 12.6
UAT | 6 | 0.75
Deployment | 6 | 0.75
Total Effort | 440.8 | 55.1
#REF!

## Sheet1
Login (FB, Google)
Home page
product and svc page
Admin Dashboard (attendance roster, class schedules, Payments received, Meeting requests, feedback)
Manager Dashboard(students, classes taken etc.)
Student Dashboard(Upcoming classes, classes taken, classes missed, payment receipts, meeting requests, F/B received)
Register Client interface (Register, create multiple profiles, view classes scheduled and attendance, school migration req)
Register Admin Interface (view student profiles, approve school migrations, award additional classes)
book courses (apply booking rules, pause booking)
pay online
Map students, courses and course schedules
attendance penalty rules
cancellation policy
biometric attendance register (with Attendance rules)
meeting request
reports
Master data (city, school, course master)
Admin
Create Group class
Create Individual class
manage users
manage class schedule
create courses
course list
course details
mark class cancelled (due to teacher absence)